SOP 9.41.070 – Prepare Layout & Sequencing Plan

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.065 – Develop Labor Budget; 9.41.075 – Develop Project Schedule
Reference: GSL Pre-Construction Planning – Layout & Sequencing

Purpose

To establish a coordinated layout and sequencing plan that supports efficient installation, minimizes trade conflicts, and ensures project milestones are achieved.

Scope

This SOP applies to Project Managers, Field Supervisors, and General Superintendents during the pre-construction planning phase.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops initial sequencing plan and integrates into the Project Execution Plan (PEP). |
| Field Supervisor | Reviews constructability and provides sequencing feedback. |
| General Superintendent | Confirms manpower allocations and critical path activities. |
| Safety Coordinator | Identifies safety risks associated with layout and sequencing. |

Required Documents and Tools

- Current project drawings and specifications

- Site logistics plan

- BIM models or coordination drawings (if available)

- Sequencing plan template

Procedure

Step 1: Collect Inputs

- Gather drawings, logistics plans, and BIM/coordination models.

Step 2: Define Work Layout

- Map work areas, access points, and material staging zones.

Step 3: Develop Sequencing Plan

- Break work into logical phases tied to contract milestones.

- Identify dependencies and potential trade overlaps.

Step 4: Validate Plan

- Review plan with Superintendent, Field Supervisor, and Safety Coordinator.

- Adjust based on manpower availability and site logistics.

Step 5: Document & Distribute

- Save plan in the project folder.

- Share with project team during turnover and kickoff discussions.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Layout & Sequencing Plan | Project Manager | Project Folder |
| Updated PEP | PM | Project Folder |
| Field Logistics Notes | Field Supervisor | PEP File |

Compliance & Review

| KPI | Target |
| --- | --- |
| Sequencing plan completed prior to mobilization | 100% |
| Reviewed by Superintendent and Safety Coordinator | 100% |
| Distributed to project stakeholders | 100% |

References

- GSL Pre-Construction Planning – Section 4.7 Layout & Sequencing

Appendix

- Sequencing Plan Template

- Example Layout Diagram

- Logistics Checklist