SOP 9.41.075 – Develop Project Schedule

Department: Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.070 – Prepare Layout & Sequencing Plan; 9.41.080 – Establish Tracking & Control Systems
Reference: GSL Pre-Construction Planning – Schedule Development

Purpose

To develop a baseline project schedule that integrates procurement, labor budgets, sequencing, and contractual milestones, providing a roadmap for project execution and monitoring.

Scope

This SOP applies to Project Managers and General Superintendents for all awarded projects during the pre-construction phase.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops and maintains the baseline schedule; ensures compliance with contractual requirements. |
| General Superintendent | Provides input on manpower phasing and field execution feasibility. |
| Purchasing | Confirms procurement and delivery dates for long-lead items. |
| Branch Manager | Reviews and approves final baseline schedule. |

Required Documents and Tools

- Contract schedule and milestone requirements

- Labor budget (SOP 9.41.065)

- Procurement schedule (SOP 9.41.050 / 9.41.055)

- Scheduling software (MS Project, Primavera, or Smartsheet)

Procedure

Step 1: Review Contract Requirements

- Identify required completion dates, phasing requirements, and penalties for delays.

Step 2: Build Baseline Schedule

- Develop activities covering submittals, procurement, installation, testing, and closeout.

- Include all long-lead items and major milestones.

Step 3: Integrate Resources

- Add manpower forecasts, equipment needs, and field logistics.

Step 4: Validate Schedule

- Review with General Superintendent, Purchasing, and Safety for feasibility.

Step 5: Approve & Issue

- Submit final baseline schedule to Branch Manager for approval.

- Distribute to project stakeholders and upload to project folder.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Baseline Project Schedule | Project Manager | Project Folder |
| Schedule Review Notes | PM / Superintendent | PEP File |
| Schedule Updates | PM | Shared Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Baseline schedule developed before mobilization | 100% |
| Reviewed by Superintendent and Purchasing | 100% |
| Approved by Branch Manager | 100% |

References

- GSL Pre-Construction Planning – Section 4.8 Schedule Development

Appendix

- Baseline Schedule Template

- Example Milestone Map

- Schedule Update Log