SOP 9.41.140 – Setup Equipment Staging

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area
Reference: GSL Project Manager Procedures – Mobilization

Purpose

To establish designated areas for equipment staging, ensuring safe and efficient deployment of construction equipment.

Scope

This SOP applies to Project Managers, Field Supervisors, and Equipment Operators during mobilization.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Approves staging area location based on site logistics. |
| Field Supervisor | Directs setup and coordinates equipment deliveries. |
| Equipment Operators | Position equipment safely in staging area. |
| Safety Coordinator | Ensures OSHA compliance for equipment storage. |

Required Documents and Tools

- Site logistics plan

- Equipment delivery schedule

- Material handling plan (SOP 9.41.060)

Procedure

- Select Staging Location – Accessible area that avoids disrupting traffic flow.

- Prepare Area – Clear ground, provide mats if needed, mark parking/maneuvering zones.

- Position Equipment – Organize by size/type, ensure emergency access.

- Apply Safety Controls – Provide barriers near public access, lockout/tagout idle equipment.

- Document – Maintain log of staged equipment and inspections.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Equipment Staging Log | Field Supervisor | Project Folder |
| Updated Site Logistics Plan | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Staging area established prior to equipment arrival | 100% |
| Safety barriers/signage in place | 100% |
| Weekly inspection log maintained | 100% |

References

- GSL Project Manager Procedures – Mobilization

Appendix

- Equipment Staging Log Template

- Site Logistics Plan Example