SOP 9.41.145 – Setup Parking

Department: Project Management / Safety
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.035 – Conduct Site Visit; 9.41.060 – Prepare Material Handling Plan; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging
Reference: GSL Project Manager Procedures – Mobilization

Purpose

To designate and manage parking areas for workers, visitors, and deliveries, ensuring safety and minimizing disruption to site operations.

Scope

This SOP applies to Project Managers, Field Supervisors, and Safety Coordinators during mobilization.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Approves parking plan per site logistics. |
| Field Supervisor | Establishes parking areas and installs signage. |
| Safety Coordinator | Ensures traffic flow and pedestrian safety compliance. |

Required Documents and Tools

- Site logistics plan

- Parking layout plan

- Signage package

- Material handling plan (SOP 9.41.060)

Procedure

- Identify Parking Areas – Assign zones for employees, visitors, and deliveries; include ADA-compliant spaces.

- Prepare & Mark Areas – Grade, mark spaces, define lanes and walkways.

- Install Signage – Provide clear directional and restriction signs; designate visitor parking.

- Safety & Security – Add barriers near construction zones; install lighting for night use.

- Maintain Parking – Inspect weekly, repair damage, and adjust as site changes.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Parking Plan | Project Manager | Project Folder |
| Inspection Log | Field Supervisor | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Parking established before mobilization | 100% |
| ADA compliance verified | 100% |
| Weekly inspections maintained | 100% |

References

- GSL Project Manager Procedures – Mobilization

Appendix

- Parking Plan Template

- Inspection Log Example