SOP 9.41.155 – Conduct Subcontractor Coordination Meetings

Department: Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.075 – Develop Project Schedule; 9.41.135 – Setup Laydown Area; 9.41.140 – Setup Equipment Staging
Reference: GSL Project Manager Procedures – Coordination

Purpose

To lead regular subcontractor coordination meetings to ensure subcontractor activities align with project schedule, logistics, and safety requirements.

Scope

This SOP applies to Project Managers, Field Supervisors, and all subcontractors assigned to the project.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares and distributes meeting agenda; tracks subcontractor action items. |
| Subcontractors | Provide progress updates, manpower forecasts, and coordination requirements. |
| Field Supervisor | Reports logistics needs and field conditions. |
| Safety Coordinator | Reviews safety performance and compliance. |

Required Documents and Tools

- Subcontractor coordination agenda template

- Updated project schedule

- Site logistics plan

- Safety compliance logs

Procedure

- Schedule Meetings – Weekly or per GC/owner requirements.

- Prepare Agenda – Include schedule, manpower, logistics, safety, and open issues.

- Conduct Meeting – Document subcontractor progress and risks.

- Resolve Issues – Coordinate sequencing and site logistics conflicts.

- Record Outcomes – Issue minutes and update subcontractor action log.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Subcontractor Meeting Agenda | Project Manager | Project Folder |
| Meeting Minutes | PM | Project Folder |
| Subcontractor Action Log | PM | Shared Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Weekly subcontractor meetings conducted | 100% |
| Minutes issued within 48 hrs | ≥95% |
| Action items closed prior to next meeting | ≥90% |

References

- GSL Project Manager Procedures – Coordination

Appendix

- Subcontractor Meeting Agenda Template

- Subcontractor Action Log Template