SOP 9.41.205 – Manage RFIs (Requests for Information)

Department: Project Management / Pre-Construction
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.1
Related SOPs: 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.080 – Establish Tracking & Control Systems; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Documentation Management

Purpose

To standardize the RFI process to ensure issues are documented, submitted, tracked, and resolved in a timely manner.

Scope

This SOP applies to Project Managers, Field Supervisors, and Subcontractors.
All RFI documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Creates, submits, and tracks RFIs. |
| Field Supervisor | Identifies issues and provides field input. |
| Estimator | Provides clarification when required. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- RFI log template

Procedure

- Identify issue or conflict.

- Draft RFI form with references.

- Submit for response.

- Track in RFI log.

- File responses per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| RFI Log | Project Manager | Per SOP 190A |
| Submitted RFIs | PM | Per SOP 190A |
| Responses | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| RFI log created within 5 days of turnover | 100% |
| Responses received before affected work begins | ≥95% |
| RFI log updated within 24 hrs of response | 100% |

References

- GSL Project Manager Procedures – Documentation Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- RFI Log Template

- Sample Completed RFI