SOP 9.41.220 – Manage Drawing Logs

Department: Project Management / Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.1
Related SOPs: 9.41.020 – Project Manager Reviews Plans, Specifications & Schedule; 9.41.030 – Create List of Issues & Begin RFI Process; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Documentation Management

Purpose

To maintain an accurate and up-to-date drawing log, ensuring the field team works from the latest approved drawings.

Scope

This SOP applies to Project Managers, Site Administrators, and Field Supervisors.
All drawing logs and revisions must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews and publishes new drawing sets. |
| Site Administrator | Updates log and organizes revisions. |
| Field Supervisor | Confirms field crews access the latest drawings. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Drawing log template

- Revision tracking system

Procedure

- Create initial drawing log.

- Update log with new revisions, dates, and numbers.

- Distribute updated drawings within 24 hrs of receipt.

- Archive superseded drawings.

- File log per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Drawing Log | Site Administrator | Per SOP 190A |
| Updated Drawing Sets | PM / SA | Per SOP 190A |
| Revision Archive | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Drawing log established within 5 days of turnover | 100% |
| Updates issued within 24 hrs of receipt | 100% |
| Monthly log audit performed | ≥95% |

References

- GSL Project Manager Procedures – Documentation Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Drawing Log Template

- Revision Tracking Sheet Example