SOP 9.41.250 – Manage As-Built Drawings

Department: Project Management / Quality / Closeout
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.1
Related SOPs: 9.41.220 – Manage Drawing Logs; 9.41.245 – Manage Punch Lists; 9.41.235 – Manage Permits; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Documentation Management

Purpose

To prepare and maintain accurate as-built drawings reflecting field changes for submission to the owner at project completion.

Scope

This SOP applies to Project Managers, Field Supervisors, and Subcontractors.
All as-built drawings must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Compiles final as-builts and submits to owner. |
| Field Supervisor | Records field changes and updates drawings. |
| Subcontractors | Provide redline markups of installed work. |
| Site Administrator | Organizes drawing sets per SOP 190A. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Drawing markup templates

- Contract specifications

Procedure

- Document field changes throughout project.

- Update redline drawings regularly.

- Compile revisions into final as-built set.

- Review and approve with owner.

- File and transmit per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Redline Drawings | Field Supervisor / Subs | Per SOP 190A |
| Final As-Built Set | Project Manager | Per SOP 190A |
| Owner Copy | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| As-builts updated monthly | 100% |
| Final set submitted prior to turnover | 100% |
| Owner acceptance documented | 100% |

References

- GSL Project Manager Procedures – Documentation Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- As-Built Drawing Checklist

- Redline Example