SOP 9.41.300 – Manage Architect / Engineer Communications

Department: Project Management / Design Coordination
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.205 – Manage RFIs; 9.41.220 – Manage Drawing Logs; 9.41.225 – Manage Specifications; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Communication

Purpose

To document and manage all communications with architects and engineers to ensure design clarifications, RFIs, and revisions are properly tracked.

Scope

This SOP applies to Project Managers, Field Supervisors, and Site Administrators.
All architect/engineer communications must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Issues RFIs, receives design clarifications, and maintains official records. |
| Field Supervisor | Identifies design conflicts and communicates to PM. |
| Site Administrator | Logs architect/engineer correspondence. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- RFI log

- Drawing and specification logs

Procedure

- Route all A/E communications through the Project Manager.

- Submit RFIs and track responses in log.

- Document design clarifications in writing.

- Update drawings/specifications as revisions are issued.

- File all correspondence and records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Architect/Engineer Communication Log | Site Administrator | Per SOP 190A |
| RFIs and Responses | Project Manager | Per SOP 190A |
| Design Revisions | PM / SA | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of A/E communications logged | 100% |
| RFIs responded to before affected work begins | ≥95% |
| Design revisions filed within 24 hrs of receipt | 100% |

References

- GSL Project Manager Procedures – Communication

- SOP 9.41.190A – Document Filing Standards

Appendix

- AHJ Communication Log Template

- Inspection Report Example