SOP 9.41.320 – Update Project Schedule

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.150 – Conduct Project Coordination Meetings; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scheduling

Purpose

To update the project schedule regularly, reflecting actual progress, changes, and delays, ensuring alignment with field execution.

Scope

This SOP applies to Project Managers, Superintendents, and Site Administrators.
All schedule updates must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Updates schedule with progress and changes. |
| Superintendent | Provides weekly field progress and manpower updates. |
| Site Administrator | Files updated schedules. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Current project schedule

- Field progress reports

Procedure

- Collect weekly field progress from Superintendent.

- Input progress into scheduling software.

- Update logic ties and forecasted dates.

- Review changes with project team.

- File updated schedule per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Updated Project Schedule | Project Manager | Per SOP 190A |
| Progress Narrative | PM | Per SOP 190A |
| Lookahead Schedule | Superintendent | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Weekly schedule updates completed | 100% |
| Forecast reflects actual field progress | ≥95% |
| Updated schedule filed within 24 hrs | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Progress Update Template

- Lookahead Example