SOP 9.41.340 – Manage Resource-Loaded Schedules

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.315 – Develop Project Schedule; 9.41.335 – Prepare Lookahead Schedules; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scheduling

Purpose

To integrate labor, equipment, and material resources into the project schedule to provide realistic forecasts and improve resource management.

Scope

This SOP applies to Project Managers, Superintendents, and Branch Managers.
All resource-loaded schedules must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Builds resource-loaded schedule using input from field. |
| Superintendent | Confirms labor and equipment availability. |
| Branch Manager | Reviews forecasts and resource impacts. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Scheduling software (Primavera P6, MS Project)

- Labor, equipment, and material logs

Procedure

- Identify resource requirements for each activity.

- Input labor, equipment, and materials into scheduling software.

- Validate resource forecasts with field management.

- Update resource-loaded schedule monthly.

- File per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Resource-Loaded Schedule | Project Manager | Per SOP 190A |
| Forecast Reports | PM | Per SOP 190A |
| Review Notes | Branch Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of activities resourced in schedule | 100% |
| Monthly resource-loaded updates completed | 100% |
| Reports filed per SOP 190A | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Resource Forecast Example

- Labor/Equipment Tracking Template