SOP 9.41.355 – Manage Project Scope

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.010 – Project Turnover Meeting; 9.41.315 – Develop Project Schedule; 9.41.350 – Manage Schedule Change Requests; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

Purpose

To define, communicate, and control the contractual scope of work, ensuring all team members and subcontractors understand project requirements.

Scope

This SOP applies to Project Managers, Estimators, and Field Supervisors.
All scope documentation and changes must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Interprets contract scope, communicates requirements to the team. |
| Estimator | Provides original bid scope clarifications. |
| Field Supervisor | Ensures field crews execute work according to scope. |
| Site Administrator | Files scope documentation. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Contract and specifications

- Scope matrix

Procedure

- Review contract documents and specifications.

- Develop scope matrix for major systems and responsibilities.

- Communicate scope to field supervisors and subcontractors.

- Monitor execution for scope compliance.

- File scope documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Scope Matrix | Project Manager | Per SOP 190A |
| Scope Clarifications | Estimator | Per SOP 190A |
| Execution Notes | Field Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Scope matrix completed within 15 days of turnover | 100% |
| Scope communicated to all field supervisors | 100% |
| Variances documented and addressed | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Scope Matrix Template

- Example Clarification Log