SOP 9.41.360 – Manage Change Orders

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.205 – Manage RFIs; 9.41.240 – Manage Inspection Reports; 9.41.355 – Manage Project Scope; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

Purpose

To document, price, submit, and track all change orders (COs) to ensure contractual and financial accuracy.

Scope

This SOP applies to Project Managers, Estimators, and Accounting.
All change order requests and approvals must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Initiates and tracks change orders. |
| Estimator | Prepares cost impacts. |
| Accounting | Logs approved COs in financial system. |
| Site Administrator | Maintains CO log. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Change Order Request form

- RFI responses and supporting documentation

Procedure

- Identify scope change through RFIs, directives, or client request.

- Prepare change order request with cost/time impact.

- Submit CO to owner/GC for review.

- Track status until approval.

- File CO documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Change Order Log | Project Manager | Per SOP 190A |
| CO Requests | PM / Estimator | Per SOP 190A |
| Approved COs | Accounting | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of COs documented in log | 100% |
| Pricing issued within 10 days of request | ≥95% |
| Approved COs filed prior to billing | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Change Order Request Form

- CO Log Example