SOP 9.41.365 – Manage Potential Change Orders (PCOs)

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.360 – Manage Change Orders; 9.41.205 – Manage RFIs; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

Purpose

To identify, log, and track potential change orders (PCOs) before they become formal change orders, allowing proactive risk management.

Scope

This SOP applies to Project Managers, Estimators, and Site Administrators.
All PCO documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Identifies and logs PCOs, communicates with owner/GC. |
| Estimator | Provides preliminary pricing. |
| Site Administrator | Maintains PCO log. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- PCO log template

- Supporting RFI or directive

Procedure

- Identify potential changes during project execution.

- Log PCO in tracking system.

- Prepare preliminary pricing and impact assessment.

- Discuss with owner/GC for approval path.

- File per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| PCO Log | Site Administrator | Per SOP 190A |
| Preliminary Pricing | Estimator | Per SOP 190A |
| Owner/GC Discussion Notes | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| PCOs logged within 2 days of identification | 100% |
| Preliminary pricing issued within 5 days | ≥95% |
| Logs reviewed weekly | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- PCO Log Template

- Example Pricing Worksheet