SOP 9.41.375 – Manage Scope Clarifications

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.355 – Manage Project Scope; 9.41.205 – Manage RFIs; 9.41.370 – Manage Owner Directives; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

Purpose

To capture, track, and communicate scope clarifications arising during design interpretation, RFIs, or owner/GC discussions.

Scope

This SOP applies to Project Managers, Estimators, and Field Supervisors.
All scope clarifications must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Documents clarifications and communicates to team. |
| Estimator | Confirms consistency with original bid scope. |
| Field Supervisor | Implements clarifications in the field. |
| Site Administrator | Logs clarifications. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Clarification log template

- Contract documents

Procedure

- Record clarification in log with reference to contract documents.

- Confirm interpretation with owner/GC or design team if needed.

- Communicate clarification to field team.

- Update scope matrix and execution plan.

- File clarification records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Clarification Log | Site Administrator | Per SOP 190A |
| Clarification Notes | Project Manager | Per SOP 190A |
| Updated Scope Matrix | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Clarifications logged within 2 days of issue | 100% |
| Clarifications communicated to field | 100% |
| Records filed and archived | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Clarification Log Template

- Sample Clarification Record