SOP 9.41.385 – Manage Force Account Work

Department: Project Management / Contract Administration / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.360 – Manage Change Orders; 9.41.365 – Manage Potential Change Orders; 9.41.380 – Manage Backcharges; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Scope & Change Control

Purpose

To document, track, and bill for force account work performed outside the contract scope but directed by the owner or GC.

Scope

This SOP applies to Project Managers, Field Supervisors, and Accounting.
All force account documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Authorizes force account work, prepares documentation. |
| Field Supervisor | Tracks labor, material, and equipment used. |
| Accounting | Processes billing and records financial impacts. |
| Site Administrator | Logs and files all records. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Force account log template

- Daily labor/equipment tickets

Procedure

- Receive written directive authorizing force account work.

- Track daily labor, equipment, and material usage on force account tickets.

- Review tickets with owner/GC representative for signature.

- Submit tickets to Accounting for billing.

- File all documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Force Account Log | Project Manager | Per SOP 190A |
| Signed Force Account Tickets | Field Supervisor | Per SOP 190A |
| Billing Records | Accounting | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Force account tickets signed daily by GC/owner | 100% |
| Force account work billed within 15 days | 100% |
| All tickets filed and cross-referenced with CO log | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Force Account Ticket Template

- Force Account Log Example