SOP 9.41.420 – Manage Actual Costs

Department: Project Management / Accounting
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.400 – Monitor Project Costs; 9.41.415 – Manage Committed Costs; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Cost Management

Purpose

To record, verify, and report actual costs incurred on the project for accurate financial tracking and reporting.

Scope

This SOP applies to Project Managers, Accounting, and Site Administrators.
All actual cost records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews actual costs and investigates variances. |
| Accounting | Records actual costs in financial system. |
| Site Administrator | Assists with documentation and filing. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Invoices and receipts

- Payroll and labor reports

Procedure

- Collect invoices, receipts, and payroll reports.

- Verify costs against commitments and budget.

- Record actual costs in accounting system.

- Review weekly with Project Manager.

- File supporting documents per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Actual Cost Reports | Accounting | Per SOP 190A |
| Verified Invoices | PM / Accounting | Per SOP 190A |
| Variance Records | Project Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Actual costs updated weekly | 100% |
| Variances documented within 5 days | 100% |
| Supporting records filed consistently | 100% |

References

- GSL Project Manager Procedures – Cost Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Invoice Review Checklist

- Cost Report Example