SOP 9.41.570 – Manage Material Allocation

Department: Project Management / Procurement / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.055 – Procurement of Large Feeder Wire; 9.41.335 – Prepare Lookahead Schedules; 9.41.340 – Manage Resource-Loaded Schedules; 9.41.565 – Manage Equipment Allocation; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Resource Management

Purpose

To manage allocation and delivery of materials to ensure availability at the right time and location while minimizing waste and storage costs.

Scope

This SOP applies to Project Managers, Purchasing, and Field Supervisors.
All material allocation and usage records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Forecasts material needs and coordinates deliveries. |
| Purchasing | Places orders and confirms delivery schedules. |
| Field Supervisor | Receives and tracks materials on-site. |
| Branch Manager | Reviews material allocation during project audits. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Material allocation log

- Delivery schedules

Procedure

- Forecast material requirements during planning.

- Issue purchase orders per procurement procedures.

- Schedule deliveries aligned with lookahead schedules.

- Track receipt and usage of materials.

- File material records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Material Allocation Log | Project Manager | Per SOP 190A |
| Delivery Records | Purchasing | Per SOP 190A |
| Usage Reports | Field Supervisor | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Material forecasts updated monthly | 100% |
| Deliveries scheduled per lookahead | 100% |
| Usage records filed weekly | 100% |

References

- GSL Project Manager Procedures – Resource Management

- SOP 9.41.190A – Document Filing Standards

Appendix

- Material Allocation Log Template

- Delivery Tracking Form