SOP 9.41.700 – Track Equipment Utilization

Department: Field Operations / Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.565 – Manage Equipment Allocation; 9.41.685 – Manage Daily Reports; 9.41.595 – Prepare Resource Reports; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Field Execution

Purpose

To track equipment usage daily to ensure proper allocation, cost control, and productivity.

Scope

This SOP applies to Field Supervisors, Equipment Managers, and Project Managers.
All equipment utilization records must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Records daily equipment usage and idle time. |
| Equipment Manager | Tracks availability and maintenance needs. |
| Project Manager | Reviews equipment utilization against budget. |
| Site Administrator | Logs data into project system. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Equipment tracking log

- Daily reports

Procedure

- Record equipment usage and hours daily.

- Track idle time and downtime reasons.

- Compare actual usage to allocation and budget.

- Summarize weekly for PM review.

- File utilization records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Equipment Tracking Log | Field Supervisor | Per SOP 190A |
| Weekly Utilization Summary | Equipment Manager | Per SOP 190A |
| Variance Reports | Project Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of equipment usage logged daily | 100% |
| Weekly summaries reviewed by PM | 100% |
| Idle time <10% of allocated hours | ≥90% compliance |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- Equipment Tracking Log Template

- Weekly Summary Example