SOP 9.41.710 – Manage Workface Planning

Department: Project Management / Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.41.705 – Manage Work Packaging; 9.41.335 – Prepare Lookahead Schedules; 9.41.675 – Conduct Daily Huddles; 9.41.190A – Document Filing Standards
Reference: GSL Project Manager Procedures – Field Execution

Purpose

To implement workface planning (WFP) by providing crews with all information, materials, and tools needed before starting field tasks.

Scope

This SOP applies to Project Managers, Field Supervisors, and Foremen.
All workface planning documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Oversees WFP process and reviews readiness. |
| Field Supervisor | Confirms workface readiness before assigning tasks. |
| Foremen | Execute tasks only once resources are fully available. |
| Site Administrator | Maintains WFP checklists and logs. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- WFP readiness checklist

- Lookahead schedules

Procedure

- Identify upcoming tasks from lookahead schedule.

- Verify availability of drawings, materials, tools, and labor.

- Complete WFP checklist before task start.

- Assign tasks to crews with confirmed readiness.

- File WFP documentation per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| WFP Checklist | Field Supervisor | Per SOP 190A |
| Workface Readiness Log | Site Administrator | Per SOP 190A |
| Task Assignment Records | Foremen | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of tasks readiness verified | 100% |
| Checklists filed before task start | 100% |
| Zero work stoppages due to missing resources | ≥95% compliance |

References

- GSL Project Manager Procedures – Field Execution

- SOP 9.41.190A – Document Filing Standards

Appendix

- WFP Checklist Template

- Readiness Log Example