GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: Section 1.2: Administrative Setup
Department: Operations / Project Management / Administration
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

Pre-Construction Planning Activities

Section 1.3: Administrative Setup

1. Purpose

To establish a standardized administrative system that supports efficient project tracking, documentation, communication, and change control throughout the life cycle of the project.

2. Scope

This SOP applies to project startup procedures managed by Project Managers and supported by administrative personnel. It covers file setup, change management, RFI tracking, and system configuration required for effective project administration.

3. Procedure

Activity 1: Set Up Project Files and Create Contact List

- Create standardized paper files using the File System Checklist (Table 4.10)

- Create a project contact list including names, roles, and contact info for:

  - Owner, Architect, Engineer, General Contractor

  - Consultants, Inspectors, Facility Contacts

  - Internal team (PM, Project Leadership, Admin Team)

Responsible Parties: Assistant Project Manager, Project Coordinator, and/or Project Administrator (whichever is available)

Activity 2: Set Up Computerized Tracking and Control Systems

- Submit Job Number Request. Confirm a project number has been issued and loaded in the accounting system

- Create New Project in Procore using the File System Checklist

- Initialize the project in project management tools such as Procore

- Set up project schedule if using software such as MS Project or Procore’s scheduling module

Responsible Parties: Project Manager, Assistant Project Manager, and/or Project Coordinator (whichever is available)

Activity 3: Initiate a Change Management System

- Review contract for change order and field change requirements

- Implement GSL’s standard change management procedures

  - Track all COs using sequential log (Table 4.11)

  - Apply templates and protocols defined in company standards

- Include RFQs, Field Change Directives, and Disputed Changes in the log

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 4: Initiate RFI Tracking and Processing System

- Create an RFI log with sequential tracking numbers (Table 4.12)

- Identify method of submission (email, fax, postal mail, or software)

- Use company standard RFI process and ensure all RFIs include:

  - Proposed solution

  - Cost or schedule impact, if applicable

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

4. Documentation and Tools

- File System Checklist (Table 4.10)

- Change Order Log Template (Table 4.11)

- RFI Log Template (Table 4.12)

- Project Management Software (e.g., Procore, Excel)

5. Compliance

All administrative setup tasks must be completed prior to mobilization. Digital and paper systems must be maintained throughout the project to ensure traceability, efficiency, and compliance with internal standards.

| SOP | Project Manager | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing | Assistant PM |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Set Up Project Files and Create Contact List | x |  |  |  |  |  |  |  |  | x |
| Activity 2: Set Up Computerized Tracking and Control Systems | x |  |  |  |  |  |  |  |  | x |
| Activity 3: Initiate a Change Management System | x |  |  |  |  |  |  |  |  | x |
| Activity 4: Initiate RFI Tracking and Processing System | x |  |  |  |  |  |  |  |  | x |