GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: Section 1.4: Buyout Process

Department: Operations / Purchasing
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

Activity 1: Buyout Process

Purpose: To procure all necessary materials, equipment, and subcontractor services required for project execution.

Scope: This activity encompasses evaluating vendor qualifications, negotiating contracts, issuing purchase orders, and initiating the submittal process.

Activity 1: Request and/or Review Subcontractor/Supplier/Vendor Prices and Qualifications

Steps:

- Solicit Pricing: Request updated pricing from subcontractors, suppliers, and vendors if not previously obtained during the bidding phase.

- Scope Verification: Compare the actual scope of work with the submitted bids to identify discrepancies.

- Evaluate Qualifications: Assess the experience, past performance, and capacity of each subcontractor, supplier, and vendor.

- Price and Qualification Comparison: Utilize spreadsheets or project management software to compare pricing and qualifications.

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 2: Negotiate Pricing and Contract Conditions, and Select Subcontractors/Suppliers/Vendors

Steps:

- Discuss Cost Savings: Engage in discussions with potential subcontractors, suppliers, and vendors to explore cost-saving opportunities.

- Review Terms and Conditions: Examine contract or purchase order terms, including delivery schedules, inventory procedures, and liability clauses.

- Approval for Changes: Any change of subcontractors, suppliers, or vendors from those used in the estimate must first be approved by the Branch Manager.

- Issue Letter of Intent: After selection, issue a letter of intent to authorize commencement of work or procurement while formal contracts are processed.

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 3: Develop and Issue Purchase Orders and Contracts for Materials and Equipment

Steps:

- Prepare Documents: Draft purchase orders or contracts detailing scope, pricing, and terms.

- Process and Issue: Ensure all documents are signed by authorized company officers and specify delivery or hold instructions.

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 4: Order Long-Lead-Time Materials and Equipment  Approved submittals first?

Steps:

- Identify Long-Lead Items: Review project schedule and scope to pinpoint materials and equipment with extended lead times.

- Prioritize Orders: Negotiate and issue purchase orders or subcontracts for these items ahead of standard procurements.

- Issue Letter of Intent: Expedite ordering by issuing letters of intent or purchase orders immediately for long-lead items.(storage.googleapis.com)

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 5: Request Submittals, Cut Sheets, and Shop Drawings

Steps:

- Request Submittals: Upon contract issuance, request necessary submittals from subcontractors, suppliers, and vendors.

- Set Deadlines: Establish clear deadlines for submission to ensure timely review and approval.

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Activity 6: Develop and Process Log and Book of Submittals, Cut Sheets, and Shop Drawings

Steps:

- Create Tracking Log: Develop a sequentially numbered log to monitor all submittals.

- Assemble Binders: Compile both draft and approved submittals into organized binders for office and field use.

- Track and Follow-Up: Utilize the submittal log to track approvals and issue follow-ups as necessary.

Responsible Parties: Project Manager, Assistant Project Manager, or Project Coordinator

Documentation and Tools:

- Standardized digital folders in Procore

- Submittal tracking logs

- Purchase order and contract templates

| SOP | Project Manager | Assistant PM | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Request and/or Review Subcontractor /Supplier /Vendor Prices and Qualifications | x | x |  |  |  |  |  |  |  |  |
| Activity 2: Negotiate Pricing and Contract Conditions, and Select Subcontractors/ Suppliers/ Vendors | x | x |  |  |  |  |  |  |  |  |
| Activity 3: Develop and Issue Purchase Orders and Contracts for Materials and Equipment | x | x |  |  |  |  |  |  |  |  |
| Activity 4: Order Long-Lead-Time Materials and Equipment | x | x |  |  |  |  |  |  |  |  |
| Activity 5: Request Submittals, Cut Sheets, and Shop Drawings | x | x |  |  |  |  |  |  |  |  |