GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: Section 1.5: Material Handling Plan
Department: Operations / Field Management / Logistics
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

Pre-Construction Planning Activities

## Section 1.5: Material Handling Plan

### 1. Purpose

To ensure that all materials and equipment are delivered, received, stored, and staged efficiently and safely, enabling maximum productivity and preventing delays, damage, or loss.

### 2. Scope

This SOP applies to the planning and management of material deliveries, handling processes, storage arrangements, and on-site logistics. It is primarily directed at Project Leadership and Logistics Coordinators.

### 3. Procedure

#### Activity 1: Develop Material Delivery and Handling Plan

Steps:

- Review the “Material Delivery/Storage and Site Logistics Best Practices” (Table 4.17).

- Establish and maintain a file of delivery receipts and packing slips.

  - Ensure that any individual receiving shipments forwards receipts to the Project Supervisor.

- Create and maintain a material and equipment delivery and storage log (Table 4.18).

- Develop a material and equipment delivery schedule.

  - Annotate planned delivery dates during scope/schedule review and buyout.

- Establish standard receiving, handling, and storage procedures, including:

  - Delivery hours and access points.

  - Unloading points and handling protocols.

  - Roles for receiving and signing for deliveries.

  - Documentation of delivery, inspection, acceptance, and final storage.

Responsible Parties: Project Manager, Assistant Project Manager, Project Coordinator, Project Leadership

#### Activity 2: Develop Material Storage and Staging Plan

Steps:

- Complete the Site Logistics Review Checklist (Table 4.19).

- Reassess the “Material Delivery/Storage and Site Logistics Best Practices” (Table 4.17).

- Develop a storage site layout that shows:

  - Designated areas for key material categories and equipment.

  - Consolidated storage and staging zones.

Responsible Parties: Project Leadership

### 4. Documentation and Tools

- Material Delivery & Storage Log (Table 4.18).

- Site Logistics Review Checklist (Table 4.19).

- Material Delivery/Storage Best Practices Guide (Table 4.17).

- Storage Site Layout Plan.

- Project Management Software (e.g., Procore, Excel).

### 5. Compliance

All materials and equipment must be received, tracked, and stored according to this SOP. Non-adherence can lead to inefficiencies, safety issues, or financial loss and must be reported to the Project Manager.

| SOP | Project Manager | Assistant PM | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| #### Activity 1: Develop Material Delivery and Handling Plan | x | x | x |  |  |  |  |  |  |  |
| #### Activity 2: Develop Material Storage and Staging Plan |  |  | x |  |  |  |  |  |  |  |