GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: Section 1.6: Layout and Sequencing Plan
Department: Operations / Field Execution / Prefabrication
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

Pre-Construction Planning Activities

Section 1.6: Layout and Sequencing Plan

1. Purpose

To develop clear, efficient work sequences and layout drawings that streamline field execution and maximize crew productivity, including the use of CAD and prefabrication instruction sets.

2. Scope

This SOP applies to project managers, field leadership, CAD operators (if available), and prefabrication teams responsible for organizing, sequencing, and communicating field work plans.

3. Procedure

Activity 1: Develop Installation Sequence and Layout Drawings

Steps:

- Organize the project by area, floor, or system to manage scope and labor assignment.

- Conduct planning meetings to brainstorm and mentally visualize the complete work sequence.

- Decide whether to use hand-marked drawings or generate CAD layouts based on project needs and available resources.

- Prepare daily installation drawings at least one day ahead of execution to distribute to field crews.

- Review and adjust sequencing weekly based on actual field progress and schedule updates.

Responsible Parties: Project Manager, Assistant Project Manager, Field Leadership, CAD Operator (if available)

Activity 2: Develop Field Instructions (Panel, Pull, or Conduit Schedules)

Steps:

- Analyze the sequence and identify additional details needed to eliminate field confusion and boost productivity.

- Prepare panel, pull, or conduit schedules and package them with layout drawings for the field teams.

- Where repetitive work is present, develop a consistent instruction and drawing set for those repeating units (e.g., hotel rooms).

Responsible Parties: Project Manager, Assistant Project Manager, Field Leadership, CAD Operator (if available)

Activity 3: Develop Prefabrication Drawings for Field Use (if applicable)

Steps:

- Create shop-level assembly and field installation drawings for prefabricated systems.

- Label all prefabricated parts clearly and match labels to assembly sequences shown in the drawings.

- If on-site prefabrication is planned, produce detailed assembly drawings for shop work and separate installation drawings for field use.

- Distribute prefabrication instructions and drawings to the responsible field crews.

Responsible Parties: Prefab Superintendent, CAD Operator (if available), Project Manager, Field Leadership

4. Documentation and Tools

- Installation Layout Drawings (CAD or Hand-Sketch)

- Panel, Pull, or Conduit Schedules

- Prefabrication Instruction Sets

- Project Management Software (e.g., Procore, AutoCAD, Bluebeam)

5. Compliance

Field work must follow the approved sequencing plans, installation drawings, and prefabrication instructions. Variations should be coordinated with the Project Manager and documented in writing.

| SOP | Project Manager | Assistant PM | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Develop Installation Sequence and Layout Drawings | x | x | x |  |  |  |  |  |  |  |
| Activity 2: Develop Field Instructions (Panel, Pull, or Conduit Schedules) | x | x | x |  |  |  |  |  |  |  |
| Activity 3: Develop Prefabrication Drawings for Field Use (if applicable) | x | x | x |  |  |  |  |  | x |  |