GSL ELECTRIC
Standard Operating Procedure (SOP)

Title: Section 1.7: Schedule Development and Tracking
Department: Operations / Project Management
Effective Date: [Insert Date]
Approved By: [Insert Approving Authority]
Reviewed By: [Insert Reviewer Name]
Document Owner: [Insert Name]
Next Review Date: [Insert Review Cycle]
Version: 1.0

Pre-Construction Planning Activities

Section 1.7: Schedule Development and Tracking

1. Purpose

To establish a standardized process for developing, coordinating, and maintaining a comprehensive project schedule that supports field operations, ensures timely procurement, and facilitates ongoing tracking and control.

2. Scope

This SOP applies to Project Managers, Assistant Project Managers, Schedulers, and Project Leadership involved in planning, coordinating, and tracking the progress of electrical construction activities.

3. Procedure

Activity 1: Review Customer’s Project Schedule

- Review the general contractor’s schedule using the Customer Schedule Review Checklist (Table 4.26).

- Attend customer schedule meetings to clarify requirements and address any critical timing issues.

Responsible Parties: Project Manager, Assistant Project Manager

Activity 2: Identify Electrical Work and Conflicts

- Annotate electrical scope requiring coordination with other trades.

- Identify and resolve equipment wiring issues or system conflicts.

- Submit RFIs and initiate coordination meetings as needed.

Responsible Parties: Project Manager, Project Leadership

Activity 3: Align Work Sequence and Delivery

- Develop a draft electrical schedule from the installation plan.

- Coordinate material and equipment delivery with the sequence of work.

- Resolve discrepancies between the delivery schedule and installation plan.

Responsible Parties: Project Manager, Assistant Project Manager

Activity 4: Coordinate with Contract Schedule

- Align the draft schedule with the general contractor's schedule.

- Seek written or verbal approval.

- Provide the general contractor with a digital file for integration if required.

Responsible Parties: Project Manager

Activity 5: Customize Tracking & Control System

- Select control tools based on the project type (Table 4.30).

- Customize Procore, Excel, or other software for tracking labor, materials, and schedules.

Responsible Parties: Project Manager, Assistant Project Manager

4. Documentation and Tools

- Customer Schedule Review Checklist (Table 4.26)

- Electrical Schedule Draft and Final Versions

- Tracking and Control Tools Checklist (Table 4.30)

5. Compliance

The electrical schedule must be maintained and tracked throughout the project. All conflicts or deviations must be documented and communicated to the Project Manager. Failure to do so can affect cost, delivery, and jobsite performance.

| SOP | Project Manager | Assistant PM | Project Foreman | Business Manager | Contract Manager | Branch Manager | Estimator | General Superintendent | Pre-Fab Superintendent | Purchasing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Review Customer’s Project Schedule | x | x |  |  |  |  |  |  |  |  |
| Activity 2: Identify Electrical Work and Conflicts | x | x | x |  |  |  |  |  |  |  |
| Activity 3: Align Work Sequence and Delivery | x | x |  |  |  |  |  |  |  |  |
| Activity 4: Coordinate with Contract Schedule | x | x |  |  |  |  |  |  |  |  |
| Activity 5: Customize Tracking & Control System | x | x |  |  |  |  |  |  |  |  |