# Daily Log SOP

| Scope: | This SOP outlines the information that needs to be captured in a Daily Log at the end of a working day. The purpose is to establish a standardized method to ensure consistency, efficiency, and transparency in project execution. |
| --- | --- |
| Why: | - Maintain good documentation and accountability. - Ensure quality control. - Enhance communication and collaboration. - Serve as valuable evidence in dispute resolution. - Improve project monitoring and decision-making. - Increase knowledge retention for future projects. - Provide the means to train new team members. |
| User: | The Daily Log is to be completed by the Field Leader. |

# Project Information

☐ Job name.

☐ Job number.

☐ Job location.

☐ Date.

☐ Start & Finish Time.

☐ Daily log completed by:

# Project Conditions

## Weather

☐ Temperature.

☐ Precipitation.

☐ Humidity.

☐ Windspeed.

☐ Notes (Elaborate on any weather-related issues that impacted the work).

## Team

### Your Company Manpower

| Name | Rank (i.e., foreman, journeyman, inspector, etc.) | Cost Code (if available) | Work Location | Hours | Hours missed | Overtime Hours | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

### Subcontractors

| Subcontractor name | Scope of work being performed | Hours worked | Work Location | Comments |
| --- | --- | --- | --- | --- |

### Visitors

| Name | Company | Visit Time (start-end) | Purpose | Comments |
| --- | --- | --- | --- | --- |

### Equipment/Tooling

| ID Number | Description | Status (i.e., transferred, stolen, misplaced, lost, returned) |
| --- | --- | --- |

## Safety

☐ Confirm team’s compliance with safety procedures.

☐ Report safety hazards.

| Description | Location | Involved personnel | Comments | Attachments |
| --- | --- | --- | --- | --- |

☐ Report safety violations.

| Description | Time | Issued to | Compliance due | Comments |
| --- | --- | --- | --- | --- |

☐ Report near misses and recordables

| Description | Location | Involved personnel | Company/ Trade | Comments | Attachment |
| --- | --- | --- | --- | --- | --- |

☐ Outline any preventive measures taken.

Report (5W’s)

☐ Why action is needed.

☐ What the action is.

☐ Who is to act.

☐ Where the action is.

☐ When the action is.

# Project Status

## Activities

☐ Report on the work.

| Work category (installation, preparation, etc.) | Work description | Work location | Responsible party | picture | Work status compared to planned |
| --- | --- | --- | --- | --- | --- |

☐ Report on any additional work that was performed.

| Work description | Work location | Party authorizing work | Party performing work | Cost information | Work status |
| --- | --- | --- | --- | --- | --- |

## Materials

☐ Document ordered materials.

☐ Document received deliveries (add reference document).

☐ Document any issues with materials (elaborate).

☐ Management.

☐ Quality.

☐ Availability.

☐ Storage.

## Productivity

- A factor with Minor Impact results in a less than 10% impact on productivity loss.

- A factor with Average Impact results in 10%-20% impact on productivity loss.

- A factor with Severe Impact results in a more than 20% impact on productivity loss.

### Working space

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Congestion |  |  |  |  |  |  |
| Stacking of trades |  |  |  |  |  |  |
| Working in an operating environment |  |  |  |  |  |  |
| Joint Occupancy |  |  |  |  |  |  |
| Beneficial Occupancy |  |  |  |  |  |  |
| Site Access Challenges |  |  |  |  |  |  |
| Site Size challenges |  |  |  |  |  |  |

### Schedule

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Overtime (Schedule and unscheduled) |  |  |  |  |  |  |
| Accelerated or compressed schedules |  |  |  |  |  |  |
| Schedule changes/lack of schedule |  |  |  |  |  |  |

### Changes

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Influx of design changes |  |  |  |  |  |  |
| Design issues (erroneous, incomplete or inconsistent) |  |  |  |  |  |  |
| Rework due to changes |  |  |  |  |  |  |
| Change in scope of work |  |  |  |  |  |  |

### Production

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Out of sequence work |  |  |  |  |  |  |
| Piecemeal work |  |  |  |  |  |  |
| Learning curve is interrupted – crew pulled off from one operation to perform another |  |  |  |  |  |  |
| Work interruptions during peak production |  |  |  |  |  |  |
| Inspection delays |  |  |  |  |  |  |
| Inadequate crew size |  |  |  |  |  |  |

### Materials/Equipment/Tools

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Delays in order supplied material and equipment |  |  |  |  |  |  |
| Relocation of assigned lay down area |  |  |  |  |  |  |
| Excessive man lift delays |  |  |  |  |  |  |
| Unplanned off site storage due to acceleration |  |  |  |  |  |  |
| Additional tools and equipment due to increased labor |  |  |  |  |  |  |
| Damages/lost equipment (apparent/concealed) |  |  |  |  |  |  |
| Arrival of major shipments (fixtures, switchgear, etc.) |  |  |  |  |  |  |
| Additional on-site equipment maintenance due to excessive use (unscheduled 2nd or 3rd shift) |  |  |  |  |  |  |
| Increases or decreases in quantities |  |  |  |  |  |  |
| Theft |  |  |  |  |  |  |

### Information

| Factor | Not Applicable | Minor Impact | Average Impact | Severe Impact | Action Taken | Notes |
| --- | --- | --- | --- | --- | --- | --- |
| Lack of information |  |  |  |  |  |  |
| Incomplete or incorrect information |  |  |  |  |  |  |
| Our own errors and Omissions |  |  |  |  |  |  |
| Conversations with other trades/GC |  |  |  |  |  |  |

# Signature

☐ Add signature and date.