# Procurement SOP

| Scope: | This SOP establishes a standardized process for procurement on a construction project. |
| --- | --- |
| Why: | - Streamline the procurement process. - Provide better visibility into the process and responsible parties. - Increase time efficiency. - Increase transparency and accountability. - Provide the means to tarin new team members. |
| Users: | This Procurement SOP is to be used by Electrical Contractor Personnel involved in the procurement process (including estimators, Project Managers, Field Leaders, Pre-fab managers, Purchasing Agents, and Warehouse Managers) |
| Tools: | Two interactive excel tools are provided with this SOP: - Vendor Evaluation Tool (VET): A tool designed to evaluate different vendors. - Excess Materials Handling Tool: A tool designed to facilitate the decision-making on how to handle excess materials on a construction project. |

# Acronyms

| E: Estimator | PA: Purchasing Agent |
| --- | --- |
| PM: Project Manager | V: Vendor |
| FL: Field Leader | W: Warehouse Manager |
| PR: Pre-fab Manager | S: Surplus Scrap Dealer |

# Notes

- Project has been awarded.

- The “Understand” and “Source” phases depend on the time available to plan for the project after award.

- “Procurement” is added as separate entity here. Could be removed or modified for organizations that don’t have a separate purchasing department.

- This format was used so that contractors can easily tweak the list of activities as well as modify the engagement of the different stakeholders.

# Understand your project and materials.

## Step 1: What project characteristics are present?

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
| X | X | X | X | X |  |  | ☐ Hold a turnover meeting from estimating. |
|  | X |  |  |  |  |  | ☐ Review project scope and contract. |
|  | X | X |  |  |  |  | ☐ Determine if any owner specific requests are made. |
|  | X | X |  |  |  |  | ☐ Distinguish between performance specs and design specs. |
|  | X | X |  |  |  |  | ☐ Identify any constraints such as restricted site access and lay down areas. |
|  | X | X | X |  |  |  | ☐ Identify any challenging logistics. |
|  | X | X |  |  |  |  | ☐ Understand contractual relationships. |
|  | X |  |  | X |  |  | ☐ Understand diverse business requirements. |
|  | X |  |  | X |  |  | ☐ Understand federal requirements. |
|  | X |  |  | X |  |  | ☐ Understand warranty requirements. |
|  | X | X |  |  |  |  | ☐ Review the submittal process. |

## Step 2: What materials to procure?

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
| X | X | X |  |  |  |  | ☐ Pull material requirements from the Estimate. |
|  | X | X |  | X |  |  | ☐ Evaluate specs for "Comply", "Deviate", and "Exclude" (C, D, E): - Check materials in specification for "comply" – do as stated in specs; "deviate" - deviate from what is stated in the specs; and "exclude" – remove from specs. - Specs revised for CDEs are to be sent with submittals for the engineer to approve. |
|  | X | X |  |  |  |  | ☐Identify hazardous materials (need to have Safety Data Sheets). |
|  | X | X | X |  |  |  | ☐ Identify pre-fab opportunities. |
|  | X | X | X | X |  | X | ☐ Identify long lead items. |
|  | X | X | X | X |  | X | ☐ Identify item risk level (availability, delivery, etc.). |
|  | X | X | X | X |  |  | ☐ Review who has the authority to order materials. |
|  | X | X | X | X |  |  | ☐ Consolidate a list of what to procure. |

### OUTCOME:

| Code | Description | C, D, E | Prefab Y/N | Long lead Y/N | Risk Level |
| --- | --- | --- | --- | --- | --- |

*Could connect to WBS.

## Step 3: How much to procure?

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
| X | X | X | X |  |  |  | ☐ Update Bill of Material (BOM) with feedback from the field. |
|  | X | X |  | X | X |  | ☐ Check inventory internally for available materials to avoid unnecessary purchases. |
|  | X | X |  | X |  | X | ☐ Check inventory externally for available materials. |
|  | X | X |  | X |  |  | ☐ Check BOM of other projects and consider combining POs later. |
|  | X | X |  | X |  |  | ☐ Determine if Bulk Buy is needed (take advantage of discounts if possible). |

### OUTCOME:

| Code | Description | C, D, E | Prefab Y/N | Long lead Y/N | Risk Level | Quantity (available & needed) | Combine Y/N | Bulk Buy Y/N |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Step 4: When to procure?

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X |  |  |  |  |  | ☐ Connect the BOM to project schedule. |
|  | X | X |  | X |  |  | ☐ Discuss release dates and delivery dates (what part of the job will the materials be used). |
|  | X | X |  | X |  |  | ☐ Discuss when it makes the most sense to source quotes for materials. |
|  | X | X | X | X |  | X | ☐ Be aware of market conditions. |
|  | X | X |  | X |  | X | ☐ Connect with Vendors for feedback. |
|  | X | X |  |  |  | X | ☐ Add delivery notes. |

### OUTCOME:

| Code | Description | C, D, E | Prefab Y/N | Long lead Y/N | Risk Level | Quantity (available & needed) | Combine Y/N | Bulk Buy Y/N | Delivery notes | Sourcing Timeline |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# Source materials

## Step 5: Where to procure?

### Options to choose from:

Materials are classified as commodities or major materials.

Both material groups can be procured through either blanket contract or competitive bidding.

#### Commodities/Blanket Contract in place

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X |  |  | X |  | X | ☐ Review contract conditions. |
|  | X | X |  | X |  | X | ☐ Discuss storage options for bulk items. |
|  |  |  |  |  |  |  | ☐ Ensure blanket pricing is in line with project budget. |
|  | X | X |  | X |  | X | ☐ Buy commodity items under contract from the particular vendor/supplier. |

#### Commodities/Competitive Bidding

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X | X |  | X |  |  | ☐ Create potential bid list (build on the OUTCOME of the previous step). |
|  | X | X |  | X |  |  | ☐ Specify bid requirements (due date, information to provide with quote, delivery date, warranty & training requirements, submittal requirements, pricing break outs, etc.). |
|  |  |  |  | X |  |  | ☐ Create and address RFIs as needed. |
|  |  |  |  | X |  |  | ☐ Create RFQs. |
|  | X | X |  | X |  |  | ☐ Review, finalize, and send RFQs to bidders. ☐ Include 80%-90% of original estimated material needed to avoid material surplus. |
|  |  |  |  |  |  | X | ☐ Submit response to RFQs (bids). |
|  | X |  |  | X |  |  | ☐ Analyze received bids. **analyze bids – Vendors Evaluation Process |
|  | X |  |  | X |  |  | ☐ Determine negotiation strategy. ☐ Discuss storage options for bulk items. |
|  | X |  |  | X |  |  | ☐ Select successful bidder. ☐ [If needed] Down select and go through additional bid rounds. |
|  |  |  |  | X |  | X | ☐ Notify successful and unsuccessful bidders. |
|  | X |  |  | X |  |  | ☐ Set expectations: Create Performance Metrics. |
|  |  |  |  | X |  |  | ☐ Create and send contract. |
|  |  |  |  | X |  | X | ☐ Negotiate and revise contract as needed until reaching agreement on contract language. |
|  |  |  |  | X |  | X | ☐ Receive signed contract by vendor/supplier. |
|  |  |  |  | X |  |  | ☐ File certificate of insurance. |
|  | X | X |  | X |  |  | ☐ Be notified of the agreement. |

#### Major Material/Competitive Bidding

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X | X |  | X |  |  | ☐ Create potential bid list (build on the OUTCOME of the previous step). |
|  | X | X |  | X |  |  | ☐ Specify bid requirements (due date, information to provide with quote, delivery date, warranty & training requirements, submittal requirements, pricing break outs, etc.). |
|  |  |  |  | X |  |  | ☐ Create and address RFIs as needed. |
|  |  |  |  | X |  |  | ☐ Create RFQs. |
|  | X | X |  | X |  |  | ☐ Review, finalize, and send RFQs to bidders. |
|  |  |  |  |  |  | X | ☐ Submit response to RFQs (bids). |
|  | X |  |  | X |  |  | ☐ Analyze received bids. **analyze bids using the Vendor Evaluation Tool (VET) |
|  | X |  |  | X |  |  | ☐ Determine negotiation strategy. |
|  | X |  |  | X |  |  | ☐ Select successful bidder. ☐ [If needed] Down select and go through additional bid rounds. |
|  |  |  |  | X |  | X | ☐ Notify successful and unsuccessful bidders. |
|  | X |  |  | X |  |  | ☐ Set expectations: Create Performance Metrics. |
|  |  |  |  | X |  | X | ☐ Elaborate on warranty information and consideration for extended warranties with certified training. |
|  |  |  |  | X |  | X | ☐ Discuss storage options. |
|  |  |  |  | X |  | X | ☐ Prepare Contract and send to vendor for signature. ☐ Negotiate Contract as needed. |
|  |  |  |  | X |  | X | ☐ Revise Contract as needed and send to vendor for signature. |
|  |  |  |  | X |  |  | ☐ Receive signed Contract. |
|  | X | X |  | X |  |  | ☐ Be notified of the agreement. |

### OUTCOME:

| Code | Description | C, D, E | Prefab Y/N | Long lead Y/N | Risk Level | Quantity (available & needed) | Combine Y/N | Bulk Buy Y/N | Delivery notes | Sourcing Timeline | Sourcing Method | Selected Vendor(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |

# Procure Materials

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | ☐ Create a submittal log. |
|  | X |  |  | X |  | X | ☐ Request submittals from vendors. ☐ Submittals’ timeline depends on the release dates and delivery dates of the materials. |
|  | X |  |  | X |  | X | ☐ Receive and review submitted submittals for conformance with specs. |
|  | X |  |  | X |  |  | ☐ Send submittals (including CDEs if any) to GC for submission to Engineer/Owner’s Rep. |
|  | X |  |  | X |  | X | ☐ Revise submittals and resubmit as needed. |

# Execution

## Material Order

### Step 6: How to purchase?

#### Options to choose from (based on material selection from the Source phase):

##### Office/Centralized Procurement/Normal Process

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | ☐ Understand the project schedule and the delivery requirements of major items. |
|  | X | X |  |  |  |  | ☐ Use a two-week lookahead schedule to plan for the materials needed. |
|  | X | X |  |  |  |  | ☐ Prepare a material requisition form. |
|  | X | X | X |  |  |  | ☐ Prepare request for material release. |
|  | X |  |  | X |  |  | ☐ Send material requests to the purchasing department. |
|  |  |  |  | X |  |  | ☐ Review requests across different projects (for potential combination). |
|  | X |  |  | X |  |  | ☐ Review and approve requisition. |
|  |  |  |  | X |  |  | ☐ Create Purchase Order (PO) log |
|  |  |  |  | X |  |  | ☐ Create PO. **Purchase only submitted and approved items. **PO creation and approval may depend on the PO value. |
|  | X |  |  | X |  |  | ☐ Send copy of PO to PM. |
|  |  |  |  | X | X |  | ☐ Send PO to warehouse manager to check if surplus inventory is available (closest warehouse). |
|  |  |  |  |  | X |  | ☐ Check inventory for items required. |
|  |  |  |  |  | X |  | ☐ If inventory is to be used, send information to Procurement. |
|  |  |  |  |  | X |  | ☐ Update PO based on information received from the warehouse manager. |
|  |  |  |  | X |  |  | ☐ Send PO to vendor (per Step 5). |
|  |  |  |  | X |  | X | ☐ Receive acknowledgement from vendor (PO#, Terms and Conditions). ☐ Vendor approves T&C’s as is. ☐ Vendor proposes revisions. |
|  |  |  |  | X |  |  | ☐ Send notification of received acknowledgment. |

## Material Delivery

### Step 7: Where and how to deliver?

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X |  |  |  |  | X | ☐ Monitor PO status. |
|  |  |  |  | X |  | X | ☐ Periodically check-in with vendors to ensure delivery is on schedule. |
|  | X | X |  | X |  | X | ☐ Resolve delivery issues. |
|  | X | X |  | X |  | X | ☐ Reconfirm delivery date and logistics. |
|  | X | X |  | X |  | X | ☐ Receive notification from vendors prior to shipment. |
|  | X | X |  |  |  |  | ☐ Ensure material handling equipment is onsite to receive as necessary. |
|  |  |  |  |  |  | X | ☐ Ship items per PO. |
|  | X | X |  |  |  |  | ☐ Inspect delivery for order accuracy (type of material, quantity, and condition). |
|  | X | X |  |  |  | X | ☐ Document any non-conformance with vendor. |
|  | X | X |  |  |  |  | ☐ Refuse damaged materials. |
|  | X | X |  |  |  |  | ☐ Sign packing slip if there are no issues with the delivery. ☐ For any issues with the order, sign and explain. |
|  | X |  |  | X |  |  | ☐ Send delivery acknowledgement to the purchasing department. ☐ For any issues with the order, dispute with the vendor. |
|  |  |  |  |  |  | X | ☐ Prepare warranty and O&M documents and for closeout and schedule training (if required). |
|  | X |  |  | X |  | X | ☐ Receive warranty and O&M documents for closeout and perform training (if required). |
|  |  |  |  |  |  |  | ☐ Ensure all warranty and O&M documents have been provided and training (if required) have been performance prior to releasing full payment. |
|  | X |  |  |  |  |  | ☐ Send warranty and O&M documents training (if required) to customer. |

## Material Return

### Step 8: How to return?

Material Return Flowchart

>> Download the Excess Materials Handling Tool

##### Jobsite returns to vendors.

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X | X |  | X |  |  | ☐ Send request of material return to Procurement. |
|  | X | X |  | X |  |  | ☐ Send a copy of the PO to the requester to highlight the items to be returned. |
|  | X | X |  |  |  |  | ☐ Note the list and quantities of items to be returned on the PO and send to Procurement. ☐ Prior to project completion and de-mobilization of the job. |
|  |  |  |  | X |  |  | ☐ Contact vendor to initiate the return process. |
|  |  |  |  |  |  | X | ☐ Verify the list of returned items. |
|  |  |  |  |  |  | X | ☐ Issue Return Material Authorization RMA#. ☐ Timeline depends on the type of materials being returned (hours vs days). |
|  | X | X |  | X |  | X | ☐ Coordinate material pickup and timely return. ☐ Material must be in original containers, if possible, and in re-sellable condition. |
|  |  |  |  | X |  | X | ☐ Receive confirmation of material pickup. |

##### Material returns to Warehouse.

| E | PM | FL | PR | PA | W | S | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X | X |  |  |  |  | ☐ Note the list and quantities of items to be returned to the warehouse. |
|  | X | X |  |  |  |  | ☐ Send list to other projects and check if material can be sent there. |
|  | X | X |  | X |  |  | ☐ [If no project can receive the material] Evaluate your option using the flowchart and provided Excess Materials Handling Tool tool. |
|  | X | X |  | X |  |  | ☐ [If material to be sent to warehouse] Send list to warehouse. |
|  | X | X |  |  | X |  | ☐ Receive material at warehouse and send a note to all project managers and foremen. |
|  | X | X |  |  | X |  | ☐ Ship the newly claimed material to jobsite. |
|  |  |  |  |  | X |  | ☐ Divide balance of materials not claimed into sell and scrap categories. |
|  |  |  |  |  | X | X | ☐ Contact material surplus suppliers and negotiate best price for material to be sold. |
|  |  |  |  |  |  | X | ☐ Pick up surplus material from the warehouse. |
|  |  |  |  |  | X |  | ☐ Scrap unsold material. |

## Change

### Step 9: How to handle changes?

#### Changes requested by owner or due to design issues.

| E | PM | FL | PR | PA | W | V | Activities |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | X |  |  |  |  |  | ☐ Create a Change Order log. |
|  | X | X |  |  |  |  | ☐ Determine type of pricing (Lum sum, T&M, Unit price). |
|  | X | X |  |  |  |  | ☐ Outline the activities to be performance along with direct costs (labor, equipment, materials, subcontractors (if any)). |
|  |  |  |  |  |  |  | ☐ Send Change Order to the Customer for approval. |
|  | X |  |  | X |  |  | ☐ Create a separate PO for needed materials. |
|  |  |  |  | X | X |  | ☐ Send PO to warehouse manager to check inventory. |
|  |  |  |  |  |  |  | ☐ Follow same process as Step 7. |