# Lookahead SOP

| Scope: | This SOP establishes a standardized process for lookahead schedule during construction project execution. |
| --- | --- |
| Why: | - Improve project planning and coordination. - Proactively mitigate risks. - Allocate resources effectively and prevent bottlenecks. - Increase transparency and accountability. - Provide the means to adapt to change more effectively. |
| Users: | This Lookahead SOP is to be used by Electrical Contractor Project Managers, Superintendents, and Foremen. |

# Project Information

☐ Job name.

☐ Job number.

☐ Job location.

☐ Date.

☐ Start Date.

☐ Duration.

## Team

### Your Company Manpower

| Name | Rank (i.e., foreman, journeyman, inspector, etc.) | Cost Code (if available) | Work Location | Hours | Hours missed | Overtime Hours | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |

### Subcontractors

| Subcontractor name | Scope of work being performed | Hours worked | Work Location | Comments |
| --- | --- | --- | --- | --- |

# Planning

☐ Job conditions/status have been reviewed.

☐ Pre-requisite work has been verified.

☐ Access to work is granted/clear.

☐ Density/Congestion factors for this work have been considered to minimize stacking of trades.

☐ Pre-fab opportunities have been considered (if applicable).

☐ PM/Field leader have coordinated with pre-fab coordinator to ensure that needed worked is being built (if applicable).

☐ Work has been evaluated for any potential rework.

☐ Critical activities for this work have been identified and communicated to the field.

☐ External conditions (i.e., weather) have been properly evaluated.

☐ Submittals have been evaluated as "comply", "deviate", and "exclude".

☐ PM/Field leader have carefully considered the logistics for material handling.

☐ Long-lead items have been procured.

☐ Purchasing agent/PM/Field Leader have coordinated material delivery with suppliers.

☐ Underground utility locators have been notified within the required timeline (if required).

# Information

## Coordination and Detailing

☐ Details for the work have been coordinated through the shop drawings/BIM.

☐ All submittals and shop drawings have been approved.

☐ The revision/date of the drawings is the most up to date.

☐ Work has been coordinated with adjacent trades.

☐ Work has been coordinated with the General Contractor.

## RFI's

☐ There are no open RFI's for this work.

☐ There is no additional information required for work to be executed.

## Changes

☐ There are no design changes that have affected the work.

☐ There are no open or pending change orders requiring approval for this work.

# Flow

☐ Clashes and interference checks have been completed.

☐ Work can start and be completed without interruption.

☐ The work plan has been clearly communicated to the field.

☐ Handoffs for this work are clear.

# Resources

## Labor

☐ Skilled labor needed for this work is available.

☐ Proper crew has been assigned.

☐ Crew meets required ratios (journeyman, apprentice, construction electrician, construction wireman).

☐ Crew composition is within the estimated rate.

## Materials

☐ All material needed for this work has been approved and released.

☐ Material inventory has been checked before ordering any materials.

☐ Materials needed for this work have been ordered for Just-in-Time delivery.

☐ Materials already received for the work have been checked for accuracy and any other issues have been noted and documented.

## Equipment

☐ All tools and equipment have been procured and are available for this work.

# Safety

☐ All safety documentation has been submitted and approved.

☐ Workers have completed all required training, certifications, drug testing, background test, etc.

# Quality

☐ Pre-installation/preparatory meetings have been held for this work.

☐ All required mockups have been completed and approved.

☐ Required inspections have been arranged.

# Completion Records

☐ Date SOP is filled out.

☐ List of individuals who completed the SOP.

☐ List of individuals who participated in the meeting.