# Handling Change and Additional Tickets SOP

| Scope: | This SOP establishes a standardized process to handle change and document additional tickets. |
| --- | --- |
| Why: | - Establish accountability. - Ensure the proper management of additional tickets. - Promote consistency in the documentation process. - Serve as a training material. |
| Users: | This change and additional tickets SOP is to be used by Project Managers and Foremen. |

# Project Information

☐ Project name.

☐ Project number.

☐ Project location.

☐ Party responsible for payment.

☐ Ticket number.

☐ Date the ticket was initiated.

# Understand the Change

## Reasons

☐ Additions

☐ Change in codes/standards/laws

☐ Deletions

☐ Design changes

☐ Design coordination

☐ Design error/insufficient/incomplete

☐ Manpower problem/availability

☐ Material handling constraints

☐ Material problem/availability

☐ Inspection-induced changed

☐ Schedule compression

☐ Site layout

☐ Unknown conditions (asbestos, etc.)

☐ Value engineering

☐ Weather

☐ Others (specify)

ELABORATE:

## When the Change Occurred

Relative to project percent complete.

## Work Description

Provide a description of the change: Location, type of activities to be performed.

# Identify Change Impact

☐ Impact on schedule (delay the progress of other parts of the job).

☐ Impact on materials (price, availability, delivery timeline).

☐ Impact on labor productivity.

| Factors | Low impact | Average impact | Sever impact | Note |
| --- | --- | --- | --- | --- |
| ☐ Stacking of trades |  |  |  |  |
| ☐ Morale and attitude (absenteeism) |  |  |  |  |
| ☐ Morale and attitude (turnover) |  |  |  |  |
| ☐ Reassignment of manpower |  |  |  |  |
| ☐ Crew size inefficiency |  |  |  |  |
| ☐ Concurrent operations |  |  |  |  |
| ☐ Dilution of supervision |  |  |  |  |
| ☐ Learning curve |  |  |  |  |
| ☐ Errors and omissions |  |  |  |  |
| ☐ Beneficial occupancy |  |  |  |  |
| ☐ Joint occupancy |  |  |  |  |
| ☐ Access constraints |  |  |  |  |
| ☐ Overtime |  |  |  |  |
| ☐ Season and weather change |  |  |  |  |
| ☐ Second shift |  |  |  |  |
| ☐ out-of-sequence work |  |  |  |  |
| ☐ AE coordination prior to construction |  |  |  |  |
| ☐ AE support during construction |  |  |  |  |

☐ Impact on project schedule (alter the original completion date).

☐ Impact on profit (change results in credit for overhead and profit for work reduction changes).

☐ Impact in manpower planning (disrupt manpower planning by changing the sequence of job activities).

☐ Impact on cost (increase the cost of work in base contract).

☐ Impact on other trades (interfere with the work of other trades).

☐ Impact on supervision costs.

☐ Impact on overhead costs (increase direct and indirect costs).

# Price/Estimate the Change (T&M)

## Labor

| Activity | Detailed Description | Labor Type | Working Time (R/O/DS) | Crew Size | Names/Codes | Hours per person | Rate per hour | Total Cost |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |

## Material

| Material Code or Class | Material Description | Quantity | Cost | Procurement Process (i.e., documentation of PO) |
| --- | --- | --- | --- | --- |

## Equipment

| Equipment Code | Equipment Description | Quantity | Cost | Procurement Process (i.e., documentation of PO) |
| --- | --- | --- | --- | --- |

## Markup

☐ Overhead and Profit

☐ Bonds if applicable

# Obtain Change Order Approval

☐ Ensure that the individual you are in contact with from the party responsible for payment is authorized to order additional work and approve the ticket.

☐ Follow-up to get the change approved and signed.

☐ Make sure to get the signature, printed name, and date of the person authorizing the change.

# Document and Track the Work while Performing the Change Order

☐ Use the Daily Log SOP to document the work performed.

☐ Track labor, materials, and equipment.

☐ Document any unexpected events that impacted the work.

# Receive Verification

☐ Make sure to receive confirmation/verification from the party responsible for payment that the work was performed.

# Completion Records

☐ Date SOP is filled out.

☐ List who completed the SOP.

☐ List who participated in filling out the SOP.