## Handling T&M & CO
#VALUE! | Handling Change and Additional Tickets SOP
Scope: |  | This SOP establishes a standardized process to handle change and document additional tickets.
Why: |  | 1. Establish accountability. 2. Ensure the proper management of additional tickets. 3. Promote consistency in the documentation process. 4. Serve as a training material.
User: |  | This change and additional tickets SOP is to be used by Project Managers and Foremen.
Project Information
Project name: | [5 empty] | Project number:
Project location: | [5 empty] | Party responsible for payment:
Ticket number: | [5 empty] | Date the ticket was initiated:
Understand the Change
Reasons
Additions
Notes (optional):
Change in codes/standards/laws
Notes (optional):
Deletions
Notes (optional):
Design changes
Notes (optional):
Design coordination
Notes (optional):
Design error/insufficient/incomplete
Notes (optional):
Manpower problem/availability
Notes (optional):
Material handling constraints
Notes (optional):
Material problem/availability
Notes (optional):
Inspection-induced changed
Notes (optional):
Schedule compression
Notes (optional):
Site layout
Notes (optional):
Unknown conditions (asbestos, etc.)
Notes (optional):
Value engineering
Notes (optional):
Weather
Notes (optional):
Others (specify)
Notes (optional):
ELABORATE:
When the Change Occurred (relative to project percent complete)
Work Description
Location:
Type of activities to be performed:
Identify Change Impact
Impact on schedule (delay the progress of other parts of the job).
Notes (optional):
Impact on materials (price, availability, delivery timeline).
Notes (optional):
Impact on labor productivity.
Notes (optional):
Factors |  |  |  | Low impact |  | Average impact |  | Sever impact |  | Note
Stacking of trades
Morale and attitude (absenteeism)
Morale and attitude (turnover)
Reassignment of manpower
Crew size inefficiency
Concurrent operations
Dilution of supervision
Learning curve
Errors and omissions
Beneficial occupancy
Joint occupancy
Access constraints
Overtime
Season and weather change
Second shift
out-of-sequence work
AE coordination prior to construction
AE support during construction
Impact on project schedule (alter the original completion date).
Notes (optional):
Impact on profit (change results in credit for overhead and profit for work reduction changes).
Notes (optional):
Impact on manpower planning (disrupt manpower planning by changing the sequence of job activities).
Notes (optional):
Impact on cost (increase the cost of work in base contract).
Notes (optional):
Impact on other trades (interfere with the work of other trades).
Notes (optional):
Impact on supervision costs.
Notes (optional):
Impact on overhead costs (increase direct and indirect costs).
Notes (optional):
Price/Estimate the Change (T&M)
Labor
Activity | Detailed Description |  | Labor Type |  | Working Time (R/O/DS) | Crew Size | Names/Codes |  | Hours per person | Rate per hour | Total Cost
1 -
2 -
3 -
4 -
5 -
Material
Material Code or Class | Material Description |  |  | Quantity |  | Cost |  | Procurement Process (i.e., documentation of PO)
1 -
2 -
3 -
4 -
5 -
Equipment
Equipment Code | Equipment Description |  |  | Quantity |  | Cost |  | Procurement Process (i.e., documentation of PO)
1 -
2 -
3 -
4 -
5 -
Markup
Overhead and Profit
Notes (optional):
Bonds if applicable
Notes (optional):
Obtain Change Order Approval
Ensure that the individual you are in contact with from the party responsible for payment is authorized to order additional work and approve the ticket.
Notes (optional):
Follow-up to get the change approved and signed.
Notes (optional):
Make sure to get the signature, printed name, and date of the person authorizing the change.
Notes (optional):
Document and Track the Work while Performing the Change Order
Use the Daily Log SOP to document the work performed.
Notes (optional):
Track labor, materials, and equipment.
Notes (optional):
Document any unexpected events that impacted the work.
Notes (optional):
Receive Verification
Make sure to receive confirmation/verification from the party responsible for payment that the work was performed.
Notes (optional):
Completion Records
Date SOP is filled out:
Notes (optional):
List of individuals who completed the SOP:
Notes (optional):
List of individuals who participated in the meeting:
Notes (optional):