## SOP_Matrix_RACI
SOP Title | SOP Number | SOP Action
Project Turnover Meeting | 9.2.015 | Schedule meeting within five business days of project award.
Project Turnover Meeting | 9.2.015 | Invite all required participants (Estimator, PM, Contract Manager, General Superintendent, Field Leadership, Prefab Lead, Safety Coordinator, Branch Manager).
Project Turnover Meeting | 9.2.015 | Gather bid documents, vendor/sub commitments, and risk items.
Project Turnover Meeting | 9.2.015 | Pull the latest Smartsheet Turnover Template as the official agenda.
Project Turnover Meeting | 9.2.015 | Lead turnover meeting using the Smartsheet agenda.
Project Turnover Meeting | 9.2.015 | Cover contractual scope and assumptions.
Project Turnover Meeting | 9.2.015 | Cover budget (labor and materials).
Project Turnover Meeting | 9.2.015 | Cover schedule and milestones.
Project Turnover Meeting | 9.2.015 | Cover subcontractor and vendor commitments.
Project Turnover Meeting | 9.2.015 | Cover field operations and logistics.
Project Turnover Meeting | 9.2.015 | Cover prefabrication opportunities.
Project Turnover Meeting | 9.2.015 | Cover safety and compliance requirements.
Project Turnover Meeting | 9.2.015 | Cover quality and document control.
Project Turnover Meeting | 9.2.015 | Cover communication protocols.
Project Turnover Meeting | 9.2.015 | Confirm action items and assignments.
Project Turnover Meeting | 9.2.015 | Record minutes, action items, and assignments.
Project Turnover Meeting | 9.2.015 | Upload meeting minutes and the Smartsheet agenda to the project folder within 48 hours.
Procurement of Large Feeder Wire | 9.2.020 | Export feeder information from Accubid and load the Feeder Wire Procurement & Release Log upon award or LOI.
Procurement of Large Feeder Wire | 9.2.020 | Confirm submittal requirements.
Procurement of Large Feeder Wire | 9.2.020 | Confirm feeder size, quantity, and length.
Procurement of Large Feeder Wire | 9.2.020 | Confirm conductor material (CU/AL).
Procurement of Large Feeder Wire | 9.2.020 | Confirm color coding, labeling, and insulation type as applicable.
Procurement of Large Feeder Wire | 9.2.020 | Issue RFQs to at least two vendors including type/size, quantity, delivery terms, reel specs, freight, taxes, and reel return policy.
Procurement of Large Feeder Wire | 9.2.020 | Collect vendor responses within 2-3 business days.
Procurement of Large Feeder Wire | 9.2.020 | Obtain vendor acknowledgment of GSL Wire Release Conditions.
Procurement of Large Feeder Wire | 9.2.020 | Review quotes and select vendor(s) based on best value (price, availability, lead time, spool sizes, approved manufacturers, vendor performance).
Procurement of Large Feeder Wire | 9.2.020 | PM sign-off and Purchasing issues purchase order (billed upon release, not procurement).
Procurement of Large Feeder Wire | 9.2.020 | Assemble submittal package per project specifications.
Procurement of Large Feeder Wire | 9.2.020 | Do not release wire until submittals are approved.
Procurement of Large Feeder Wire | 9.2.020 | Plan with Field Supervision for logistics, routing, material handling, and installation timelines.
Procurement of Large Feeder Wire | 9.2.020 | Prepare BOM and Conduit/Wire Pull Schedule using scaled drawings.
Procurement of Large Feeder Wire | 9.2.020 | Require vendor to store procured wire until GSL issues release notice.
Procurement of Large Feeder Wire | 9.2.020 | Verify submittal approval before any release.
Procurement of Large Feeder Wire | 9.2.020 | Upon release, direct vendor to cut and bundle feeders to single spools (or coils for short runs) including colored phase/neutral conductors and ground as required.
Procurement of Large Feeder Wire | 9.2.020 | Prefer standard inventory stock to minimize waste and ensure usable lengths.
Procurement of Large Feeder Wire | 9.2.020 | Expect vendors to manage spool usage to provide practical lengths for releases.
Procurement of Large Feeder Wire | 9.2.020 | Confirm wire and cable are billed upon release, not at initial procurement.
Setup Office Trailer | 9.3.010 | Review site logistics plan and determine trailer placement.
Setup Office Trailer | 9.3.010 | Ensure safe access for staff and deliveries separated from construction zones.
Setup Office Trailer | 9.3.010 | Arrange power, water, and sewer connections.
Setup Office Trailer | 9.3.010 | Install HVAC as needed for climate control.
Setup Office Trailer | 9.3.010 | Set up internet, phones, and networking; verify functionality before occupancy.
Setup Office Trailer | 9.3.010 | Equip trailer with desks, chairs, filing, printers/copiers, whiteboards, and stock supplies.
Setup Office Trailer | 9.3.010 | Install safety equipment: fire extinguishers, first aid kits, and emergency exit signage.
Setup Storage Trailer | 9.3.020 | Place storage trailer per logistics plan with safe access for deliveries/equipment.
Setup Storage Trailer | 9.3.020 | Install locks, lighting, and security measures.
Setup Storage Trailer | 9.3.020 | Install shelving, racks, and bins; designate areas by material type.
Setup Storage Trailer | 9.3.020 | Set up inventory tracking and assign responsibility for updates.
Setup Storage Trailer | 9.3.020 | Provide fire extinguishers and ensure ventilation if storing chemicals.
Setup Site Fencing and Access Control | 9.3.030 | Identify perimeter fencing requirements from the site plan.
Setup Site Fencing and Access Control | 9.3.030 | Determine vehicle, delivery, and personnel access points.
Setup Site Fencing and Access Control | 9.3.030 | Erect perimeter fencing and secure gates with locks or electronic access.
Setup Site Fencing and Access Control | 9.3.030 | Post entry/exit protocols and assign security if required.
Setup Site Fencing and Access Control | 9.3.030 | Post required safety signage and verify OSHA/local compliance.
Setup Temporary Power | 9.3.040 | Review project scope and determine temporary power requirements.
Setup Temporary Power | 9.3.040 | Identify required voltage, amperage, and distribution points.
Setup Temporary Power | 9.3.040 | Submit utility applications for temporary service.
Setup Temporary Power | 9.3.040 | Confirm installation timeline with owner/utility.
Setup Temporary Power | 9.3.040 | Install panels, feeders, and distribution boxes per plan.
Setup Temporary Power | 9.3.040 | Ground systems and provide GFCI protection.
Setup Temporary Power | 9.3.040 | Inspect for hazards (trip hazards, exposed conductors, improper grounding) and correct deficiencies.
Setup Temporary Power | 9.3.040 | Record inspection results and utility confirmations; maintain usage/inspection log.
Setup Temporary Water | 9.3.045 | Determine project water needs (mixing, cleaning, sanitary).
Setup Temporary Water | 9.3.045 | Apply for temporary water meter or hydrant connection and confirm availability.
Setup Temporary Water | 9.3.045 | Connect to utility and install pipes/hoses with shutoff valves and backflow prevention.
Setup Temporary Water | 9.3.045 | Test flow and pressure at distribution points.
Setup Temporary Water | 9.3.045 | Protect hoses/lines from damage and verify environmental compliance.
Setup Sanitary Facilities | 9.3.050 | Identify accessible, evenly distributed facility locations and provide ADA-compliant unit as required.
Setup Sanitary Facilities | 9.3.050 | Contract portable toilet/wash station vendor and set service/cleaning schedule.
Setup Sanitary Facilities | 9.3.050 | Place and anchor units per logistics plan.
Setup Sanitary Facilities | 9.3.050 | Ensure vendor provides regular cleaning; Safety Coordinator inspects weekly.
Setup Sanitary Facilities | 9.3.050 | Maintain sanitation inspection log and record corrective actions.

## Sheet1
SOP Ref | SOP Action | Role | RACI | Directive Sec. | Coverage Status
'9.41.010 | Schedule estimator-led project turnover meeting within 5 business days of project award | Estimator | R | Directive Sec. 9.5 – Project Management Directives – Project Turnover Meetings | Covered
'9.41.010 | Schedule estimator-led project turnover meeting within 5 business days of project award | Project Manager | A | Directive Sec. 9.5 – Project Management Directives – Project Turnover Meetings | Covered
'9.41.010 | Schedule estimator-led project turnover meeting within 5 business days of project award | Branch Manager | C | Directive Sec. 9.5 – Project Pre-Planning and Construction Plan | Covered
'9.41.010 | Schedule estimator-led project turnover meeting within 5 business days of project award | Contract Manager | I | Directive Sec. 9.14 – Contract Managers’ Role in Contract Review | Covered
'9.41.010 | Prepare turnover materials (bid documents, vendor commitments, risk items, turnover Smartsheet agenda) | Estimator | R | Directive Sec. 9.7 – Estimating Post-Award Directives – Project Turn-Over Meeting participation | Covered
'9.41.010 | Prepare turnover materials (bid documents, vendor commitments, risk items, turnover Smartsheet agenda) | Project Manager | C | Directive Sec. 9.5 – Project Pre-Planning and Developing the Construction Plan | Covered
'9.41.010 | Prepare turnover materials (bid documents, vendor commitments, risk items, turnover Smartsheet agenda) | Contract Manager | C | Directive Sec. 9.14 – Ensure Contract Summary for Prime and Subcontract | Covered
'9.41.010 | Prepare turnover materials (bid documents, vendor commitments, risk items, turnover Smartsheet agenda) | Branch Manager | I | Directive Sec. 9.13 – Branch Management Directives – Contracts | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Estimator | R | Directive Sec. 9.7 – Estimating Post-Award Directives – Review means, methods, exclusions in Turn-Over Meeting | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Project Manager | A | Directive Sec. 9.5 – Project Management Directives – Project Turnover Meetings | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | General Superintendent | C | Directive Sec. 9.4 – Coordinate manpower and field leadership assignments | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Field Leadership | C | Directive Sec. 9.3 – Field Leadership Pre-Planning and Execution of the Plan | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Prefabrication Lead | C | Directive Sec. 9.5 – Prefabrication planning on each project | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Safety Coordinator | C | Directive Sec. 9.3 – Field Leadership responsibilities to document safety impacts and schedule issues | Covered
'9.41.010 | Conduct project turnover meeting using standardized Smartsheet agenda (scope, budget, schedule, vendor commitments, logistics, prefab, safety, quality, communication, action items) | Branch Manager | C | Directive Sec. 9.13 – Project Management Directives – Project Turnover Meetings | Covered
'9.41.010 | Document turnover meeting minutes, action items, assignments, and upload Smartsheet agenda and attendance within 48 hours | Estimator | R | Directive Sec. 9.5 – Job Monitoring and Weekly Project Status Reports (documentation expectations) | Covered
'9.41.010 | Document turnover meeting minutes, action items, assignments, and upload Smartsheet agenda and attendance within 48 hours | Project Manager | A | Directive Sec. 9.5 – Job Monitoring and Document Control responsibilities | Covered
'9.41.010 | Document turnover meeting minutes, action items, assignments, and upload Smartsheet agenda and attendance within 48 hours | Contract Manager | I | Directive Sec. 9.14 – Review Weekly Project Status and Notice Letters | Covered
'9.055.190 | Populate Feeder Procurement & Release Log from Accubid feeder data upon Notice of Award or LOI | Project Manager | A | Directive Sec. 9.16 – Purchasing Vision and Pre-Planning Process | Covered
'9.055.190 | Populate Feeder Procurement & Release Log from Accubid feeder data upon Notice of Award or LOI | Assistant Project Manager / Project Coordinator | R | Directive Sec. 9.16 – PM to work with Foreman and develop takeoff reflecting how job will be built | Covered
'9.055.190 | Populate Feeder Procurement & Release Log from Accubid feeder data upon Notice of Award or LOI | Field Leadership | C | Directive Sec. 9.3 – Field Leadership Pre-Planning and Job Plans | Covered
'9.055.190 | Validate feeder sizes, quantities, lengths, conductor material, and labeling before RFQs | Assistant Project Manager / Project Coordinator | R | SOP 9.055.190 Responsibilities – verify feeder sizes and lengths from drawings | Covered
'9.055.190 | Validate feeder sizes, quantities, lengths, conductor material, and labeling before RFQs | Project Manager | A | Directive Sec. 9.5 – Project Manager responsible for budget and procurement decisions | Covered
'9.055.190 | Validate feeder sizes, quantities, lengths, conductor material, and labeling before RFQs | Field Leadership | C | SOP 9.055.190 – Field Leadership confirms spool sizes and delivery timing | Covered
'9.055.190 | Issue RFQs, obtain 2+ vendor quotes including reel specs, terms, and agreement to GSL Wire Release Conditions | Purchasing / Buyer | R | Directive Sec. 9.16 – Master Purchase Orders and volatile material escalation controls | Covered
'9.055.190 | Issue RFQs, obtain 2+ vendor quotes including reel specs, terms, and agreement to GSL Wire Release Conditions | Project Manager | A | Directive Sec. 9.16 – PM accountable to pre-plan and control commodity procurement | Covered
'9.055.190 | Issue RFQs, obtain 2+ vendor quotes including reel specs, terms, and agreement to GSL Wire Release Conditions | Assistant Project Manager / Project Coordinator | C | SOP 9.055.190 – APM/PC prepares submittals and supports documentation | Covered
'9.055.190 | Select vendor based on best value (price, availability, lead time, spool sizes, approved manufacturers, vendor performance) and approve PO with pricing lock | Project Manager | A | Directive Sec. 9.16 – PM to verify PO cost, tax, and scope before issue | Covered
'9.055.190 | Select vendor based on best value (price, availability, lead time, spool sizes, approved manufacturers, vendor performance) and approve PO with pricing lock | Purchasing / Buyer | R | Directive Sec. 9.16 – Purchasing to issue POs and manage terms | Covered
'9.055.190 | Select vendor based on best value (price, availability, lead time, spool sizes, approved manufacturers, vendor performance) and approve PO with pricing lock | Branch Manager | C | Directive Sec. 9.13 – Business Management Directives – contract and financial oversight | Covered
'9.055.190 | Prepare and submit feeder wire submittals per project specifications; do not release wire until submittals are approved | Assistant Project Manager / Project Coordinator | R | SOP 9.055.190 Step 4 – Submittal Preparation | Covered
'9.055.190 | Prepare and submit feeder wire submittals per project specifications; do not release wire until submittals are approved | Project Manager | A | Directive Sec. 9.5 – Submittals and Purchasing responsibilities | Covered
'9.055.190 | Prepare and submit feeder wire submittals per project specifications; do not release wire until submittals are approved | Purchasing / Buyer | C | Directive Sec. 9.16 – Submittal requirements included with POs | Covered
'9.055.190 | Collaborate with Field Supervision to define logistics, routing, material handling, installation timelines, BOM and conduit/wire pull schedule | Project Manager | A | Directive Sec. 9.5 – Project Pre-Planning and Construction Plan | Covered
'9.055.190 | Collaborate with Field Supervision to define logistics, routing, material handling, installation timelines, BOM and conduit/wire pull schedule | Field Leadership | R | Directive Sec. 9.3 – Execution of the Plan and Productivity responsibilities | Covered
'9.055.190 | Collaborate with Field Supervision to define logistics, routing, material handling, installation timelines, BOM and conduit/wire pull schedule | Assistant Project Manager / Project Coordinator | C | SOP 9.055.190 Step 5 – Pre-Planning with Field Supervision | Covered
'9.055.190 | Enforce storage and release conditions: vendor warehouse storage, submittal approval prior to release, bundled spools, and responsible spool length management | Project Manager | A | SOP 9.055.190 Step 6 – Storage and Release Conditions | Covered
'9.055.190 | Enforce storage and release conditions: vendor warehouse storage, submittal approval prior to release, bundled spools, and responsible spool length management | Purchasing / Buyer | R | Directive Sec. 9.16 – Volatile material escalation controls and pre-buyout advantages | Covered
'9.055.190 | Enforce storage and release conditions: vendor warehouse storage, submittal approval prior to release, bundled spools, and responsible spool length management | Field Leadership | C | SOP 9.055.190 – Field Leadership provides spool sizes and timing preferences | Covered
'9.41.090 | Confirm office trailer location per site logistics plan with safe access for staff and deliveries | Project Manager | R | Directive Sec. 9.5 – Project Pre-Planning and site logistics | Covered
'9.41.090 | Confirm office trailer location per site logistics plan with safe access for staff and deliveries | General Superintendent | C | Directive Sec. 9.4 – Coordinate manpower and logistics with Branch Management | Covered
'9.41.090 | Confirm office trailer location per site logistics plan with safe access for staff and deliveries | Branch Manager | I | Directive Sec. 9.6 – Branch Management oversight of operations (branch-level) | Covered
'9.41.090 | Secure utilities for office trailer (power, water, sewer, HVAC as needed) | Project Manager | A | SOP 9.41.090 – PM secures trailer and ensures utilities and internet setup | Covered
'9.41.090 | Secure utilities for office trailer (power, water, sewer, HVAC as needed) | General Superintendent | C | Directive Sec. 9.4 – Support enforcement of safety and site policies | Covered
'9.41.090 | Install and verify communications (internet, phones, network) for office trailer before occupancy | IT / Communications | R | SOP 9.41.090 – IT/Communications ensures phone, internet, networking operational | Covered
'9.41.090 | Install and verify communications (internet, phones, network) for office trailer before occupancy | Project Manager | A | Directive Sec. 9.5 – Job Monitoring and communication with GC/Owner | Covered
'9.41.090 | Equip office trailer with furniture, equipment, documentation systems, and office supplies | Site Administrator | R | SOP 9.41.090 – Site Administrator sets up furniture, equipment, documentation | Covered
'9.41.090 | Equip office trailer with furniture, equipment, documentation systems, and office supplies | Project Manager | A | Directive Sec. 9.5 – Project Management responsible for project administration infrastructure | Covered
'9.41.090 | Install trailer safety equipment (extinguishers, first aid kits, emergency exit signage) | Site Administrator | R | SOP 9.41.090 – Safety Setup step | Covered
'9.41.095 | Approve storage trailer placement per site logistics plan | Project Manager | A | SOP 9.41.095 – PM approves trailer placement | Covered
'9.41.095 | Approve storage trailer placement per site logistics plan | Field Supervisor | R | Directive Sec. 9.3 – Field Leadership responsible for execution and layout | Covered
'9.41.095 | Secure storage trailer (locks, lighting, security measures) | Field Supervisor | R | SOP 9.41.095 – Secure Trailer step | Covered
'9.41.095 | Secure storage trailer (locks, lighting, security measures) | Project Manager | C | Directive Sec. 9.5 – Job Monitoring and protection of materials and equipment | Covered
'9.41.095 | Organize interior with shelving, racks, bins, and designated material zones | Field Supervisor | R | SOP 9.41.095 – Organize Interior step | Covered
'9.41.095 | Organize interior with shelving, racks, bins, and designated material zones | Project Manager | C | Directive Sec. 9.5 – Job Plans and productivity monitoring | Covered
'9.41.095 | Implement inventory tracking system (manual or digital) and assign update responsibility | Field Supervisor | R | SOP 9.41.095 – Implement Inventory System step | Covered
'9.41.095 | Implement inventory tracking system (manual or digital) and assign update responsibility | Project Manager | A | Directive Sec. 9.5 – Job Cost / Estimates report shared with Field Leadership | Covered
'9.41.095 | Verify storage trailer safety (fire extinguishers, ventilation for chemicals) | Safety Coordinator | R | SOP 9.41.095 – Safety Coordinator verifies compliance with fire and access safety standards | Covered
'9.41.095 | Verify storage trailer safety (fire extinguishers, ventilation for chemicals) | Field Supervisor | C | Directive Sec. 9.3 – Field Leadership to document and report hazards and damage | Covered
'9.41.095 | Verify storage trailer safety (fire extinguishers, ventilation for chemicals) | Project Manager | A | Directive Sec. 9.5 – Safety and compliance requirements in project execution | Covered
'9.41.100 | Plan perimeter fencing and access layout based on site logistics plan and required access points | Project Manager | A | SOP 9.41.100 – PM approves fencing plan and access compliance | Covered
'9.41.100 | Plan perimeter fencing and access layout based on site logistics plan and required access points | Field Supervisor | R | SOP 9.41.100 – Field Supervisor oversees installation of fencing, gates, signage | Covered
'9.41.100 | Plan perimeter fencing and access layout based on site logistics plan and required access points | Safety Coordinator | C | Directive Sec. 9.3 – Daily reports must capture schedule and safety impacts | Covered
'9.41.100 | Install site fencing and secure gates with locks or electronic access systems | Field Supervisor | R | SOP 9.41.100 – Install Fencing step | Covered
'9.41.100 | Install site fencing and secure gates with locks or electronic access systems | Project Manager | C | Directive Sec. 9.5 – Job Monitoring and coordination with GC/Owner on access | Covered
'9.41.100 | Implement access control (entry/exit protocols, controlled access points, security coverage if applicable) | Security Personnel | R | SOP 9.41.100 – Security Personnel monitor controlled access points | Covered
'9.41.100 | Implement access control (entry/exit protocols, controlled access points, security coverage if applicable) | Field Supervisor | C | SOP 9.41.100 – Implement Access Control step | Covered
'9.41.100 | Implement access control (entry/exit protocols, controlled access points, security coverage if applicable) | Project Manager | A | Directive Sec. 9.5 – Project Management responsible for schedule and logistics | Covered
'9.41.100 | Post safety signage at all entries and verify fencing meets OSHA and local requirements | Safety Coordinator | R | SOP 9.41.100 – Safety and Compliance step | Covered
'9.41.100 | Post safety signage at all entries and verify fencing meets OSHA and local requirements | Field Supervisor | C | Directive Sec. 9.3 – Field Leadership documentation of schedule/safety impacts | Covered
'9.41.100 | Post safety signage at all entries and verify fencing meets OSHA and local requirements | Project Manager | A | Directive Sec. 9.5 – Safety and compliance requirements in execution | Covered
'9.41.105 | Assess temporary power requirements (voltage, amperage, distribution points) from scope and drawings | Project Manager | A | SOP 9.41.105 – Step 1 Assess Requirements | Covered
'9.41.105 | Assess temporary power requirements (voltage, amperage, distribution points) from scope and drawings | Field Supervisor | R | SOP 9.41.105 – Field Supervisor oversees installation and verifies distribution points | Covered
'9.41.105 | Assess temporary power requirements (voltage, amperage, distribution points) from scope and drawings | Electrical Subcontractor | C | SOP 9.41.105 – Electrical Subcontractor installs panels, wiring, grounding | Covered
'9.41.105 | Coordinate temporary power service with owner/utility and confirm installation timeline | Project Manager | R | SOP 9.41.105 – Step 2 Coordinate with Utility | Covered
'9.41.105 | Install temporary panels, feeders, distribution boxes, and grounding per plan and code with GFCI protection | Electrical Subcontractor | R | SOP 9.41.105 – Step 3 Install Distribution System | Covered
'9.41.105 | Install temporary panels, feeders, distribution boxes, and grounding per plan and code with GFCI protection | Field Supervisor | C | Directive Sec. 9.3 – Field Leadership responsible for execution and quality | Covered
'9.41.105 | Inspect temporary power for trip hazards, exposed conductors, and proper grounding; correct deficiencies before use | Safety Coordinator | R | SOP 9.41.105 – Step 4 Safety Review | Covered
'9.41.105 | Inspect temporary power for trip hazards, exposed conductors, and proper grounding; correct deficiencies before use | Field Supervisor | C | Directive Sec. 9.3 – Daily reports to capture schedule and safety impacts | Covered
'9.41.105 | Inspect temporary power for trip hazards, exposed conductors, and proper grounding; correct deficiencies before use | Project Manager | A | Directive Sec. 9.5 – Safety and compliance requirements during execution | Covered
'9.41.105 | Record inspection results, utility confirmations, and maintain temporary power usage and inspection log | Field Supervisor | R | SOP 9.41.105 – Step 5 Document and File; Safety Inspection Log | Covered
'9.41.105 | Record inspection results, utility confirmations, and maintain temporary power usage and inspection log | Safety Coordinator | C | Directive Sec. 9.3 – Daily Reports and administration support for documentation | Covered
'9.41.105 | Record inspection results, utility confirmations, and maintain temporary power usage and inspection log | Project Manager | A | Directive Sec. 9.5 – Document Control and Job Monitoring | Covered