## Mobilization
MOBILIZATION CHECKLIST FOR PROJECT MANAGEMENT
1 - Setup office trailer in a timely manner and in a convenient location
Meet with the General Contractor’s representative to identify a location on the site for placing the office trailer.
Set up the office trailer before the crews begin execution.
Locate the trailer to minimize walking between the trailer, crew locations, toilets, and the General Contractor’s office trailer, when possible. This will be beneficial for numerous reasons, including accident reduction (many small accidents occur during walking) and increased productivity.
Ensure the office trailer has power, communications (phone/internet), and a copy of the plans, files, a computer, and other tools necessary for managing the work.
Make sure, desks enable enough space to read drawings. It is important to be able to display at least two big size documents on the same set of desks. It might also be helpful to display the most important documents on the walls for easy reading.
Arrange for regular cleaning service for the office trailer.
It might be necessary to give workers access to a “dry shack”: a place where they can change, take breaks, and have meals. These areas should be arranged through the GC.
Access to water and toilets is very important. Location of a potable water source is necessary for health and safety, especially during hot weather months. Workers should also have access to clean toilets within 200 feet of the work area and on every third floor for multi-story construction.
The job trailer should have a basic first aid kit to handle small injuries, such as cuts and scrapes. Splints and temporary devices necessary for larger injuries should also be available.
2 - Setup storage trailer and lay down area in a convenient location
Meet with the General Contractor’s representative to identify a location on the site for placing the storage trailer and lay down area.
Locate the storage trailer to minimize walking between the trailer, crew locations, and toilets, when possible.
Ensure the storage trailer and lay down areas can be secured to prevent theft of materials and tools.
If the electrical contractor plans to pre-fabricate items on site and transport them to the installation location, a covered area may be necessary to perform the pre-fabrication operations. This site may also need to be accessible by the crane if the pre-fabricated items are very large or very heavy or at an elevated location.
3 - Setup a communication system, such as phone and internet
Contact the phone company and have a phone/fax line installed for the trailer.
Contact the cable company and have internet service established for the computers in the trailer.
4 - Secure access to site
Install a fence, if necessary, with gated entries and locks to limit access to the jobsite.
For renovation projects and other projects in secure areas, consider changing the locks to the areas under construction to prevent entry by unauthorized personnel.
Post appropriate signs to warn potential visitors and the public of the hazards associated with the site.
Implement procedures for checking in and checking out of the jobsite.
5 - Bring in the labor, tools and materials that are needed to get started with the work
Examine the plans and specifications to identify the first work task to be performed.
After identifying the first task, develop a list of personnel, tools, and materials that will be needed to implement the first task.
Establish a three-week look ahead schedule and ensure enough personnel and materials will be available to build up momentum.
6 - Walk through the jobsite to evaluate and document conditions
Review the contract to identify the requirements for conducting a pre-execution site visit to establish existing site conditions.
Use Figure 4.1 as a starting point for documenting existing conditions on the jobsite, especially conditions that will negatively impact execution.
Submit the results of the walk-through to the general contractor in writing so that the general contractor has been formally made aware of any issues that need to be resolved so the work can proceed.
7 - Make sure the foreman has everything he or she needs to get started with the work
Ensure the foreman has the information, materials, tools, and personnel to execute the work.
8 - Attend jobsite meetings and coordinate with other trades
The Project Manager, site supervisor, and/or the foreman should attend jobsite coordination meetings to work out conflicts with other trades before the conflicts delay the work.
For conflicts that will delay the work without immediate resolution, the site supervisor should work directly with the other trade(s) to resolve the conflict.
Daily coordination among trades has the potential to reduce or eliminate delays, increase teamwork, and improve the flow of work. As a result, daily coordination is strongly recommended.
9 - Visit the site regularly to identify issues that need coordination
The Project Manager should visit the jobsite, walk the job with the site supervisor, and document issues that will impact, or are already impacting, the work.