## PROJECT MANAGEMENT CHECKLIST
ACTIVITY CATEGORY | ACT. NO. | COMPLETION DATE | þ | ACTIVITY
Mobilization | 1 |  | FALSE | Setup office trailer in a timely manner and in a convenient location
| 2 |  | FALSE | Setup storage trailer and lay down area in a convenient location
| 3 |  | FALSE | Setup a communication system, such as phone and internet
| 4 |  | FALSE | Secure access to the site
| 5 |  | FALSE | Bring in the labor, tools and materials that are needed to get started with the work
| 6 |  | FALSE | Walk through the jobsite to evaluate and document conditions
| 7 |  | FALSE | Make sure the foreman has everything he or she needs to get started with the work
Coordination | 8 |  | FALSE | Attend jobsite meetings and coordinate with other trades
| 9 |  | FALSE | Visit the site regularly to identify issues that need coordination
Documentation Management | 10 |  | FALSE | Develop and implement a project file system
| 11 |  | FALSE | Implement a documentation control system
| 12 |  | FALSE | Implement an RFI tracking and processing system
| 13 |  | FALSE | Implement a submittal tracking and processing system
| 14 |  | FALSE | Implement a change order tracking and processing system
| 15 |  | FALSE | Keep a record of all schedules and updates, including delays
| 16 |  | FALSE | Update as-built drawings as portions of the work get completed
| 17 |  | FALSE | Keep records of meeting minutes
Communication | 18 |  | FALSE | Implement procedures to communicate frequently with the foreman, especially to resolve problems
| 19 |  | FALSE | Implement procedures to communicate frequently with vendors and subcontractors
| 20 |  | FALSE | Implement procedures to communicate frequently with the General Contractor and Owner
| 21 |  | FALSE | Keep the CEO/VP informed of progress and involved with the project through reports, meetings, etc.
Scheduling | 22 |  | FALSE | Review the schedule regularly and identify milestone dates that must be met
| 23 |  | FALSE | Review the schedule routinely with field personnel to ensure all parties understand the milestones
| 24 |  | FALSE | Identify work that impacts electrical activities
| 25 |  | FALSE | Give the General Contractor input on the schedule and activities
| 26 |  | FALSE | Update the schedule regularly to track progress
| 27 |  | FALSE | Review or establish a look-ahead scheduling process
Scope & Change Control | 28 |  | FALSE | Review and understand the scope of the project
| 29 |  | FALSE | Identify problems with the drawings and specifications and develop RFIs
| 30 |  | FALSE | Submit change order requests and cost proposals in a timely manner
| 31 |  | FALSE | Schedule specific meetings with the GC to discuss change orders and change issues
| 32 |  | FALSE | Implement a value engineering system to suggest alternate processes or materials
| 33 |  | FALSE | Document official change orders and incorporate them into the budget and schedule
| 34 |  | FALSE | Purchase materials or subcontracts and inform the field about the selections
| 35 |  | FALSE | Track change orders separately from the original scope
| 36 |  | FALSE | Use cost codes to account for activities
| 37 |  | FALSE | Track labor costs and compare actual costs to estimated costs
Cost & Billing Control | 38 |  | FALSE | Track material and subcontractor costs and compare actual costs to estimated costs
| 39 |  | FALSE | Once issued change orders have been approved, include them in the billing process
| 40 |  | FALSE | Compare the actual project costs to the budget to track progress
| 41 |  | FALSE | Use the schedule of values to track progress
| 42 |  | FALSE | Use a pre-bill process to seek preliminary approval of the invoice from the GC
| 43 |  | FALSE | Submit invoices of your costs in a timely manner
Subcontractors Management | 44 |  | FALSE | Review the scope and document the subcontractors’ scope of work
| 45 |  | FALSE | Make sure the subcontractors are licensed and are qualified to do the job
| 46 |  | FALSE | Implement subcontracts
| 47 |  | FALSE | Determine the subcontractors’ schedule based on input from the subcontractors
| 48 |  | FALSE | Provide information to the site supervisor and foreman about the subcontractors and the point of contact
| 49 |  | FALSE | Schedule onsite visits and walk through the jobsite with the subcontractors
| 50 |  | FALSE | Request submittals and shop drawings from the subcontractors
Materials Management | 51 |  | FALSE | Re-check bid documents to verify required materials and identify potential vendors and vendor responsibilities
| 52 |  | FALSE | Establish delivery dates for materials and equipment
| 53 |  | FALSE | Develop and issue purchase orders for materials and equipment
| 54 |  | FALSE | Lock in the pricing for materials and equipment
| 55 |  | FALSE | Document purchase orders and keep them in a file system
| 56 |  | FALSE | Communicate all material information to field personnel
| 57 |  | FALSE | Request submittals, cut sheets and shop drawings from vendors
| 58 |  | FALSE | Check material packaging, labels, and status regularly as part of an onsite materials management system
| 59 |  | FALSE | Reconcile the invoice with the estimated material costs
| 60 |  | FALSE | Implement an effective material handling system on site
| 61 |  | FALSE | Schedule material delivery using staged releases to the site based on phases
Tools Management | 62 |  | FALSE | Review contract drawings, specifications, and the bid to identify and purchase special tools
| 63 |  | FALSE | Schedule regular delivery and pickup of tools
| 64 |  | FALSE | Implement a tool tracking system and track tool usage
Labor Management | 65 |  | FALSE | Identify and maintain the correct crew mix and manpower level
| 66 |  | FALSE | Ensure labor hours are turned in by workers in a timely manner
Safety Management | 67 |  | FALSE | Implement a jobsite general safety program
| 68 |  | FALSE | Identify safety concerns associated with specific job activities
| 69 |  | FALSE | Identify and purchase additional safety equipment as needed
| 70 |  | FALSE | Update the safety log regularly and document all incidents
| 71 |  | FALSE | Perform job walks regularly to ensure that the safety procedures are being followed
Quality Management | 72 |  | FALSE | Clarify quality requirements for field personnel
| 73 |  | FALSE | Check and document the quality of installation through regular site visits
| 74 |  | FALSE | Develop and implement commissioning and testing procedures
| 75 |  | FALSE | Use a pre-punchlist to identify unresolved quality issues before completion
Project Closeout | 76 |  | FALSE | Review specifications as part of the project closeout process
| 77 |  | FALSE | Ensure that all punchlist items are completed and signed off in a timely manner
| 78 |  | FALSE | Ensure that all change orders and purchase orders are closed before job completion
| 79 |  | FALSE | Turn all project closeout documents over to the General Contractor
| 80 |  | FALSE | Receive final payment and retainage
| 81 |  | FALSE | Demobilize

## MOBILIZATION
MOBILIZATION CHECKLIST FOR PROJECT MANAGEMENT
Site Preparation & Logistics
Set up a secure staging area for materials, equipment, and storage to prevent congestion.
Obtain all required permits and approvals before mobilization.
Control site access with designated entry points, fencing, and security measures.
Install a jobsite office with power, internet, furniture, and supplies for management tasks.
Position storage trailers in convenient locations to improve workflow and efficiency.
Designate laydown areas to maximize space and allow easy access to materials and equipment.
Workforce & Equipment Readiness
Schedule labor, tools, and material arrivals to ensure crews are prepared to start work efficiently.
Provide foremen with required tools, materials, and plans before beginning construction.
Distribute tools, PPE, and site maps to workers to ensure readiness and compliance.
Conduct safety training and site orientations for all personnel before work begins.
Assign crews based on skillsets to optimize workforce productivity and efficiency.
Inspect all equipment for safety compliance and operational readiness before deployment.
Communication & Coordination
Install communication systems, including radios, phones, and internet for coordination.
Set up regular project updates between managers, field teams, and subcontractors.
Attend coordination meetings with GC representatives and subcontractors
Provide foremen with work schedules, assignments, emergency contacts, and updates.
Develop a jobsite organization chart showing key personnel and responsibilities.
Safety & Compliance
Set up first aid stations with medical supplies and establish emergency response procedures.
Conduct a site safety walkthrough before work begins to identify potential hazards.
Ensure compliance with OSHA and project-specific safety regulations.
Place fire extinguishers and emergency kits at key locations throughout the site.
Provide workers with PPE, including helmets, gloves, eye protection, and high-visibility gear.
Establish muster points for emergency evacuations and conduct safety drills.
Documentation & Tracking
Maintain logs tracking workforce, deliveries, equipment, and material inventory.
Develop an organized tracking system for RFIs, submittals, and change orders.
Assign staff to document site conditions, work progress, and changes in jobsite status.
Implement a system for tracking labor hours, attendance, and payroll records.
Assign personnel to oversee inventory and track material usage throughout the project.
Material & Resource Management
Confirm material orders are verified and scheduled for delivery per project timeline.
Secure storage areas with access control to prevent theft and material damage.
Inspect deliveries to ensure compliance with project specifications and quality standards.
Coordinate pre-fabrication to reduce on-site work time and improve efficiency.
Schedule phased material deliveries to minimize site congestion and handling issues.
Assign personnel to oversee inventory and track material usage throughout the project.
Ongoing Site Monitoring & Adjustments
Conduct daily inspections to track progress and resolve jobsite issues.
Adjust workforce allocation based on work progress and project needs.
Update project schedules regularly to reflect changes and work completion.
Monitor weather conditions and adjust work plans for safety and efficiency.
Hold weekly meetings to review mobilization progress and coordinate resolutions.

## SITE EXISTING CONDITIONS
SITE EXISTING CONDITIONS CHECKLIST
Completed | Item | Condition
FALSE | Access routes into and out of the site
FALSE | Circulation routes throughout the site
FALSE | Material and equipment delivery routes
FALSE | Material storage and staging locations
FALSE | Office trailer or office space location
FALSE | Presence/location of the crane
FALSE | Presence/location of the personnel lift
FALSE | Presence/location of the materials lift
FALSE | Housekeeping conditions
FALSE | Special site conditions
FALSE | Progress of the other trades
FALSE | Work completed to date
FALSE | Potential coordination issues with others
FALSE | Weather problems
FALSE | Delays or potential causes of delay
FALSE | Safety issues or concerns

## COORDINATION CHECKLIST
COORDINATION CHECKLIST FOR PROJECT MANAGEMENT
8. Attend jobsite meetings and coordinate with other trades
FALSE | The Project Manager, site supervisor, and/or the foreman should attend jobsite coordination meetings to work out conflicts with other trades before the conflicts delay the work.
FALSE | For conflicts that will delay the work without immediate resolution, the site supervisor should work directly with the other trade(s) to resolve the conflict.
FALSE | Daily coordination among trades has the potential to reduce or eliminate delays, increase teamwork, and improve the flow of work. As a result, daily coordination is strongly recommended.
9. Visit the site regularly to identify issues that need coordination
FALSE | The Project Manager should visit the jobsite, walk the job with the site supervisor, and document issues that will impact, or are already impacting, the work.

## DOCUMENTATION MANAGEMENT
DOCUMENTATION MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
10. Develop and implement a project file system
FALSE | Use the Project File System checklist (Table 4.4) as a starting point for establishing a paper and/or digital Project File.
11. Implement a documentation control system
FALSE | Once the Project File System has been established, implement procedures for controlling documents/information during execution.
FALSE | The process of control necessarily involves reviewing outstanding dates and tracking the progress of responses to questions. Hence, regularly review the outstanding issues, and follow-up to seek solutions.
12. Implement an RFI tracking and processing system
FALSE | Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for sample RFI procedures and logs that should be employed during project execution.
FALSE | Use a log to track all requests for information (RFIs).
FALSE | Ensure each RFI identifies the plan sheet, specification section, scope element, or contract clause that needs more information, and propose a solution to a problem, when possible.
FALSE | Ensure each RFI clearly identifies a date when the information is needed and the impact on the progress if the information is not received by the requested date.
FALSE | Conduct regular reviews of the outstanding issues, and follow-up to seek solutions.
13. Implement a submittal tracking and processing system
FALSE | Use a log to track all submittals, including those of vendors and subcontractors (Figure 4.11).
FALSE | Implement your company’s standard procedures for processing submittals. Submittals that include a product (e.g., sample, cut sheet, shop drawing, etc.) are typically dropped off at the General Contractor’s office and documented through the computer submittal tracking system.
FALSE | Verify that each submittal processing form identifies a “respond no later than” date, and make sure the General Contractor understands the consequences if the date is not met.
FALSE | Verify that each submittal processing form identifies a “respond no later than” date, and make sure the General Contractor understands the consequences if the date is not met.
FALSE | Conduct regular reviews of the outstanding issues, and follow-up to seek solutions.
14. Implement a change order tracking and processing system
FALSE | Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for sample change procedures and logs that should be employed during project execution.
FALSE | Use a log to track all changes, including change orders, field changes, and time-and-materials requests.
FALSE | Implement your company’s standard procedures for initiating, requesting, and processing change orders and field changes.
FALSE | If the change order is disputed among the parties, be sure to submit timely written notice to the General Contractor informing them that additional work has been performed and that you expect compensation for the work. You will essentially reserve your right to file a claim.
FALSE | Conduct regular reviews of the outstanding change order requests, and follow-up weekly.
15. Keep a record of all schedules and updates, including delays
FALSE | Establish a baseline schedule and have the General Contractor approve the baseline schedule.
FALSE | Track the schedule weekly, documenting the current progress each week and any changes that have occurred.
FALSE | During weekly update meetings, present your schedule and provide a copy to the General Contractor. This will provide constructive notice to the General Contractor if your work is being delayed or impacted.
16. Update as-built drawings as portions of the work get completed
FALSE | Each day or each week, the foreman or site supervisor should red-line a set of drawings to represent the work that has actually been completed.
FALSE | Any changes from the original drawings should be annotated daily or weekly on the official “as-built” drawings.
17. Keep records of meeting minutes and project progress.
FALSE | The meeting minutes should be checked for accuracy and correctness before filing them. Any discrepancies should be brought to the attention of the General Contractor and corrected promptly.
FALSE | Ensure the meetings minutes are received in a timely manner and get filed so that they can be retrieved later if necessary.
FALSE | Keep records of project progress.

## FILE SYSTEM CHECKLIST
FILE SYSTEM CHECKLIST
Completed | File Number | File Description
Project Information and Contacts
Cost Estimate and Bid Submission
Contract Agreement
Contract Documents
Budget and Pay Requests
Purchase Orders
Subcontracts
Materials Folders (Fixtures, Switchgear, Fire Alarm, Low Voltage)
Requests for Information
Submittals
Change Orders – Pending
Change Orders – Approved
Correspondence
Meeting Minutes
Daily/Weekly Field Report
Progress Reports
Other

## COMMUNICATION CHECKLIST
COMMUNICATION CHECKLIST FOR PROJECT MANAGEMENT
18. Implement procedures to communicate frequently with the foreman, especially to resolve problems
o | The site supervisor should arrange a formal daily meeting with the foreman to exchange information and address issues
o | Implement informal communication procedures to supplement the formal meetings
19. Implement procedures to communicate frequently with vendors and subcontractors
The site supervisor should arrange a formal weekly or bi- weekly phone call with vendors and subcontractors to provide an update on the progress of the work and the status of materials and services that have been ordered
o | Vendors and subcontractors should receive copies of the most current schedule and meeting minutes as one method for keeping them updated on the progress of the work
20. Implement procedures to communicate frequently with the General Contractor and Owner
The site supervisor should attend the formal weekly update and progress meetings with the General Contractor and/or owner to provide (and receive) an update on the progress of the work and current issues
o | The site supervisor should arrange a formal daily meeting with the General Contractor to exchange information and address issues
o | Implement informal communication procedures with the General Contractor to supplement the formal meetings
21. Keep the CEO/VP informed of progress and involved with the project through reports, meetings, etc.
The CEO/VP should receive an update report monthly or weekly that identifies progress of the work, work hours expended versus work hours earned, open issues, pending change orders, and sources of delay
o | The CEO/VP should be invited to, and should attend, the project update meeting at least once per month to demonstrate their support and assist with resolving issues

## SCHEDULING PROCESS
SCHEDULING PROCESS CHECKLIST FOR PROJECT MANAGEMENT
22. Review the schedule regularly and identify milestone dates that must be met
As mentioned under Activity 15, current progress should be annotated weekly on the schedule and any changes should be brought to the attention of the General Contractor if the change resulted from a delay, changed condition, or additional work.
o | Short-term milestone dates that must be met, should be annotated for further discussion with the site supervisor, foreman, vendors, and subcontractors.
o | As mentioned under Activity 15, present your schedule during weekly update meetings with the General Contractor, and provide a copy to the General Contractor.
Keep an archive of all weekly schedules with comments and annotations in order to understand what went right/wrong and what needs to be improved. This documentation will also be useful in case a claim arises against the General Contractor or from a Subcontractor.
23. Review the schedule routinely with field personnel to ensure all parties understand the milestones
During the formal meeting of the Project Manager, site supervisor, and foreman, the schedule should be reviewed to determine the short and long-term milestones that must be met.
o | The short-term milestones should be given special attention to ensure the dates are achievable.
24. Identify work that impacts electrical activities
Each week, and sometimes each day, the Project Manager and site supervisor should identify activities that must be coordinated with other trades, and the proper coordination should be implemented.
If an upcoming (but not immediate) coordination issue is identified the Project Manager should introduce the issue at the Weekly Coordination Meeting with the General Contractor to initiate coordination.
25. Give the General Contractor input on the main schedule and the activities that need to be reviewed by all parties
Each week at the Weekly Update Meeting, the Project Manager should review the electrical schedule with the customer, general contractor, other trade contractors, and suppliers to resolve any conflicts.
The Project Manager should ensure the electrical schedule has been integrated into the General Contractor’s overall project schedule each week so that their requirements are properly taken into consideration.
26. Update the schedule regularly to track progress
o | Weekly updates to the schedule should be made to ensure tasks are being completed as planned and, if not, the reasons for task incompletion is identified and corrected.
o | The schedule should be used to document progress and identify corrections that need to be made
The schedule should also be used to document delays in the work caused by other parties which might result in a claim. Hence, weekly schedule updates are an important part of the control process.
27. Review or establish a look-ahead scheduling process
o | The look-ahead scheduling process should use the project schedule to look ahead to the work that must be completed in the next one, two, or three weeks.
Once the Project Manager, site supervisor, and foreman have established the current look-ahead schedule, the workers, materials, and equipment that are needed to complete the work should be ordered or arranged.
As part of the look-ahead scheduling process, the site supervisor should talk to the foremen to determine whether they have the tools and materials needed to complete the work and to discuss possible ways to improve productivity.
o | The look-ahead schedule should also be used to identify specific coordination issues that will need attention during the schedule timeframe.
o | Because some activities may be on the critical path, the look- ahead schedule should be compared to the baseline schedule to identify any activities that are particularly important.
27. Review or establish a look-ahead scheduling process (continued)
o | Because some activities may be on the critical path, the look- ahead schedule should be compared to the baseline schedule to identify any activities that are particularly important.
For repetitive tasks, maintaining the same crew will often result in an improvement in productivity. This improvement can be tracked and, as a result of the improvement, the duration of tasks can be revised.
o | Be sure to account for the possibility of bad weather for those tasks that will be performed outside during the look-ahead period.
If needed, the electrical contractor may be able to negotiate more time for completing tasks that are not on the critical path. The reasons for the extra time must be explained to the general contractor’s Project Manager and all parties must agree to the no-cost change to the schedule.

## SCOPE & CHANGE CONTROL
SCOPE & CHANGE CONTROL CHECKLIST FOR PROJECT MANAGEMENT
28. Review and understand the scope of the project
o | Consult the Electrical Pre-Construction Planning Process Implementation Manual published by Electri’ International for additional information about conducting a scope review
Complete the Scope Review checklist (Figure 4.18), originally published in the Electrical Pre-Construction Planning Process Implementation Manual, and ensure both the Project Manager and site supervisor understand the scope of work.
o | Review the schedule to understand the timeline for completing work tasks and review the work strategy that has been developed based on the schedule.
29. Identify problems with the drawings and specifications and develop RFIs
o | Review the plans and specifications together to identify any discrepancies that require clarification. Develop Requests for Clarification for scope items that are not clearly defined.
o | Also identify any items that are not included in the scope that ordinarily would be a scope item. These excluded items should be verified by the General Contractor.
30. Submit change order requests and cost proposals in a timely manner
Change orders may take time to process, and work performed under a change order cannot be billed until the change order has become official Therefore, change order requests should be submitted as soon as the change has been identified.
31. Schedule specific meetings with the GC to discuss change orders and change issues
Although numerous meetings are scheduled each week, primarily to provide a status update or to coordinate efforts, an entirely separate meeting should be scheduled with the General Contractor to review changes and change orders.
The change order log (Activity 14), with the list of all outstanding change order requests, should be reviewed to determine the progress of receiving the requested change orders
Likewise, new changes should be discussed to determine the General Contractor’s position – for example, does the GC agree or disagree that the extra work is indeed a change? Change order requests should subsequently be developed and submitted for all changes to the work.
32. Implement a value engineering system to suggest alternate processes or materials
Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for additional information about value engineering that may have been performed during planning.
o | Although most value engineering should have occurred during bidding and planning, a process for regularly seeking out cost and time saving changes should be implemented.
o | Present value engineering opportunities to the General Contractor, including cost and time difference between the as-bid and VE options.
33. Document official change orders and incorporate them into the budget and schedule
o | Once change orders have been approved, they should be immediately incorporated into the budget so that they can be billed.
o | Likewise, once change orders have been approved, they should be immediately incorporated into the schedule so that they can be properly integrated with the other work.
34. Purchase materials or subcontracts and inform the field about the selections
Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for additional information about the buyout process that may have been performed during planning.
o | If the buyout process was not completed during planning, the Project Manager should continue buying out the job after executing the work.
o | The field supervisor should be made aware of the vendors and subcontracts that have been awarded contracts during pre-construction planning and after execution
35. Track change orders separately from the original scope
o | The resources expended to complete work under a change order should be tracked separately from the original scope of work.
o | Additional costs incurred because of the changes, which was not captured in the original change request, may need to be filed as a claim.
36. Use cost codes to account for activities
Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for additional information about cost code development that may have been performed during planning.
o | If a cost code scheme was not developed during planning, it should be developed as part of this activity.
o | The cost code scheme should also be used to resource-load your schedule so that activities can be linked to specific cost codes and tracked accordingly.
37. Track labor costs and compare actual costs to estimated costs
o | Actual labor costs that exceed estimated labor costs may be a sign of poor productivity, changes, or scope increases. Hence, any variance should be investigated to find its cause.

## SCOPE AND SCHEDULE REVIEW
SCOPE AND SCHEDULE REVIEW ITEMS
Completed | Completed By? | Date Completed? | Item to Review
Contract
Plans
Specifications
Cost estimate and bid breakdown
Referenced/applicable codes or regulations
Quality requirements
Safety requirements
Special conditions
Addendums
Temporary power and lighting requirements
Owner/CM/GC-furnished materials
Vendor pricing and qualifications
Owner/CM/GC schedule
Internal schedule submitted with bid
Work sequence and work by others
Required coordination with other trades
Material and equipment deliveries
Anticipated weather problems or holidays
Required labor
Labor rates and potential increases
Crew mix
Administrative procedures (submittals/RFIs/changes)
Access doors
Asbestos abatement
Carpentry (miscellaneous)
Clean up
Conduit (sizes and quantities)
Crane
Cutting and patching
Demolition and removal
Electric motors
Electric starters
Excavation and backfill
Fire alarm wiring
Fire alarm devices
Hand dryers
Hoists for personnel
Hoists for materials
Interior layout
Painting
Panels
Scaffolding
Site access
Site surveying
Temporary power
Underground utilities
Wire (and/or pipe and wire)

## COST & BILLING CHECKLIST
COST CONTROL & BILLING CHECKLIST FOR PROJECT MANAGEMENT
þ | SUB-ACTIVITIES
38. Track material and subcontractor costs and compare actual costs to estimated and earned costs
o | Establish a database or spreadsheet to record all material and subcontract costs
o | Set up fields in the spreadsheet to record estimated costs, earned costs, and actual costs
o | Compare actual costs to earned and estimated costs to identify any cost variances that exist
o | Identify mitigation measures to reduce or eliminate any cost variances
39. Once change orders have been approved, include them in the billing process
o | Often, change order work is completed before the official change order has been received. In such cases, the Project Manager should bill for the change order work immediately following receipt of the change order
o | For large changes that span more than one billing cycle, the change order work should be billed along with the regular billing items but payment should be tracked separately
40. Compare the actual project costs to the budget and earned value to track progress
o | As mentioned in Activity 39, a database or spreadsheet should be established to record estimated, actual, and earned costs
o | Compare actual costs to earned and estimated costs to identify any cost variances that exist. The difference between budgeted costs and actual costs is the cost variance – an indication of cost performance
o | Identify mitigation measures to reduce or eliminate any cost variances
41. Use the schedule of values to track progress
o | In addition to comparing budgeted costs to actual costs, the Project Manager should routinely examine the schedule of value to determine whether billed costs are aligned with expected expenditures to date
o | Differences between expected costs billed to date and actual billed costs should be investigated, and corrective actions should be identified if necessary
42. Use a pre-bill process to seek preliminary approval of the invoice from the GC
o | A preliminary invoice should be prepared by the project manager and submitted to the General Contractor so that sufficient time is available to have the invoice reviewed by the General Contractor. This is often called a “pencil copy.”
o | The preliminary invoice may have corrections made by the General Contractor, and these modifications should be resolved prior to submitting the actual invoice
o | In some cases, a meeting with the General Contractor may be helpful to resolve any issues and receive preliminary approval of the invoice
43. Submit invoices of your costs in a timely manner
o | Annotate the due date of all invoices each month, and make sure sufficient time has been built into the invoicing process to allow the invoice to be reviewed by all involved parties
o | A delay in submitting an invoice could mean waiting up to 90 days or longer to get paid, which can negatively impact the cash flow of the company. As a result, all invoices should be submitted on time

## SUBCONTRACTORS MANAGEMENT
SUBCONTRACTORS MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
44. Review the scope and document the subcontractors’ scope of work
o | In conjunction with Activity 28, review the scope of work to identify work that will be performed by subcontractors
o | Determine whether the scope of the subcontracted service includes “labor and equipment” or “”labor, materials and equipment”
o | Ensure the subcontractors’ scope of work has been documented so that the site supervisor and foreman can avoid requesting extra work or they understand when the requested work is outside the scope
45. Make sure the subcontractors are licensed and are qualified to do the job
o | Review critical details of the scope of work prior to award to ensure the subcontractor is capable of doing the work. This will avoid future conflicts and litigation
o | Prior to awarding a contract, check the subcontractor’s references
o | Prior to awarding a contract, check the subcontractor’s license status
46. Implement subcontracts
o | Check to make sure the subcontracts were developed during the pre-construction planning or procurement phase of the project. If they were not, the first step is to develop subcontracts based on the scope of work and bid submitted by the subcontractor
o | Ensure the subcontract has been signed and executed by all parties prior to the subcontractor mobilizing to the jobsite
o | The project manager and site supervisor should review the contract to understand the terms and conditions
o | The project manager and site supervisor should establish a system for verifying that the subcontractor is performing the work in accordance with the contract documents
47. Determine the subcontractors’ schedule based on input from the subcontractors
o | Finalize the subcontractors’ schedules by outlining the tasks that need to be completed and assigning a start date, duration, and completion date to each task
o | Input from the subcontractor will be essential to ensure that the schedule is realistic and that the subcontractor “buys in” to the schedule
48. Provide information to the site supervisor and foreman about the subcontractors and the point of contact
o | Distribute a contact list to the site supervisor and foreman that has the subcontractors’ company names, point of contact, and phone number
49. Schedule onsite visits and walk through the jobsite with the subcontractors
o | A schedule should be established for verifying the subcontractors performance by walking through the site with the subcontractor
o | During the walk-through, conformance with contract documents should be verified and discrepancies should be noted (quality control)
o | Coordination and safety is a subject that should be tackle especially after talking to the superintendant and to the project manager
o | Following each walk-though, the project manager or site supervisor should send a list summarizing the results, with a deadline for correcting any deficiencies
o | Tasks performed and % of completion have to be checked and agreed in order to avoid payment litigation
o | The Schedule has to be checked and reviewed
o | A summary of this meetings has to be made and signed by both parties
50. Request and process submittals and shop drawings from the subcontractors
o | Consult the Electrical Pre-Construction Planning Implementation Manual published by Electri’ International for additional information about processing submittals and shop drawings
o | Develop a list of required submittals and shop drawings and send the list to the subcontractor
o | Track the submission, processing, and approval of submittals and shop drawings using a computerized tracking system
o | Maintain copies of all submittals and shop drawings in the job trailer so that the site supervisor can verify that installed work conforms to the approved documents

## MATERIALS MANAGEMENT
MATERIALS MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
51. Re-check bid documents to verify required materials and identify potential vendors and vendor responsibilities
o | The Project Manager and site supervisor should review the cost estimate to understand the types and quantities of materials that are needed to complete the work
o | If vendor selection was not performed during the pre- construction planning stage, then the Project Manager will need to identify qualified vendors and receive quotations
o | A supplement to the request for quotations that outlines specific responsibilities of vendors is important to reduce confusion, conflicts, and claims
o | In some cases, particular equipment or materials will need to have the cut sheets submitted along with the bid so that approval can be obtained by the architect/designer
52. delivery dates for materials and equipment
o | The Project Manager and Site Supervisor should review the schedule to determine when specific materials and equipment need to be delivered
o | While the vendor should be provided with a copy of the schedule as part of the quotation process, a separate materials and equipment delivery schedule may be necessary to ensure the vendors are clear about required dates
53. Lock in the pricing for materials and equipment
o | After receiving quotations, the Project Manager should contact each vendor to review their quote. Of particular importance is making sure that the vendors have the correct scope of work in their bid
o | Once vendors have been selected and a final price has been negotiated, the project manager should issue a purchase order or letter contract to lock in the pricing
54. Develop and issue purchase orders for materials and equipment
o | As soon as quotes are negotiated and accepted, the project manager or purchasing agent should develop and issue the purchase order
o | The purchase order should contain the scope of work, specific information about the materials, and the required delivery date
55. Document purchase orders and keep them in a file system
o | A copy of all purchase orders should be kept at the jobsite so that the site supervisor can verify the scope of materials and equipment that will be provided by each vendor
o | A separate copy of all purchase orders should be kept by the purchasing agent and will likely be maintained in the Materials Management Information System
56. Communicate all material information to field personnel
o | The site supervisor should discuss scope of work and delivery dates with foremen to make them aware of the timeline for receiving and installing materials and equipment
o | The site supervisor should also make sure that the on-site materials manager can access all purchase orders and can contact all vendors to expedite deliveries or resolve issues
57. Request submittals, cut sheets and shop drawings from vendors
o | If the submittals, cut sheets, and shop drawings were not requested during the pre-construction planning process, they should be requested when a vendor is selected and a purchase order is issued
o | In many cases, material cut sheets for standard items will be submitted along with the quote and these will be processed following the issue of the purchase order
o | Develop a log of required submittals, cut sheets, and shop drawings (if this has not already been done in the planning phase) and use the log to keep track of submissions
58. Check material packaging, labels, and status regularly as part of an onsite materials management system
o | As materials arrive on site, a designated individual must inspect the items to ensure no damaged items have been delivered
o | All items must also be recorded so that a record of delivery and condition are maintained by the electrical contractor
o | If a bar coding system is used, all items must be tagged with a bar code and must be annotated in the materials management information system
59. Reconcile the invoice with the estimated material costs
o | As materials and equipment are received, actual costs (as identified on invoices) should be entered into the accounting system
o | Actual invoices costs should be compared to original estimated costs and should be reconciled with the purchase order
o | Discrepancies between bid/estimated costs and actual invoiced costs should be discussed with the vendor
60. Implement an effective material handling system on
o | A variety of on-site material handling strategies are available. The electrical contractor will need to craft a strategy that best fits the characteristics of the project
61. Schedule material delivery using staged releases to the site based on phases
o | Although nearly all materials and equipment, other than consumables, will be ordered during the buyout phase, arrange delivery based on project phases so that materials do not have to be stored on site
o | Numerous options exist for delivery of materials and equipment, and the Electrical Contractor should understand at what point payment and responsibility for shipment transfers from the vendor to the contractor
o | Make arrangement with vendors to deliver materials directly to the point where they will be installed
o | Ensure the schedule depicts when various materials will be needed based on the project phases

## TOOLS MANAGEMENT
TOOLS MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
62. Review contract drawings, specifications, and the bid to identify and purchase special tools
o | Examine the plans and specifications and assemble a list of standard tools that will be needed for the job
o | Examine the plans and specifications and assemble a list of special tools that will be needed for the job
o | Purchase standard and special tools well ahead of the time they will be needed on the jobsite, and assign responsibility for their management to the site supervisor
63. Schedule regular delivery and pickup of tools
o | Prior to commencing work, arrange to have tools picked up for maintenance or repair, and new, maintained, or repaired tools dropped off, on a regular basis, such as weekly, bi- weekly, or monthly
o | Establish standard procedures for maintenance, repair, or replacement of tools
o | Purchase standard and special tools well ahead of the time they will be needed on the jobsite, and assign responsibility for their management to the site supervisor.
64. Implement a tool tracking system and track tool usage
o | The site supervisor or foreman should implement a tool tracking system that documents: (1) who each tool is assigned to, (2) how long the tool has been in use, (3) when the tool is due for maintenance or replacement, and (4) current status (e.g., in use, in maintenance, in repair, etc)

## LABOR MANAGEMENT
LABOR MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
65. Identify and maintain the correct crew mix and manpower level
o | Review the labor plan and schedule to determine the number and experience level of the electricians needed to perform the work
o | Track whether the labor hours expended are equal to or less than estimated
66. Ensure labor hours are turned in by workers in a timely manner
o | Establish procedures that must be followed by workers for turning in labor hours
o | Once the procedures have been established, a system should be implemented to monitor the submission of labor hours

## SAFETY MANAGEMENT
SAFETY MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
þ | SUB-ACTIVITIES
67. Implement a jobsite general safety program
o | If the Electrical Contractor is implementing a safety program for the first time, consult the Occupational Safety and Health Act (OSHA) for general guidelines
o | Figure 4.35 provides a company safety policy outline developed by OSHA and adapted by Mincks &Johnston, 2004
o | Consider hiring a full-time safety management who can ensure standardization across projects
68. Identify safety concerns associated with specific job activities
o | Conduct on-site meetings with all workers to reinforce the dangers of the jobsite and the consequences of unsafe actions
o | Workers should have the opportunity to express their concern about any unsafe condition on the site during the on- site safety meeting
69. Identify and purchase additional safety equipment as needed
o | Personal protective equipment (PPE) should be a standard part of an overall safety plan
o | Determine whether any other safety equipment is needed in addition to PPE
70. Update the safety log regularly and document all incidents
o | Keep detailed records of all safety incidents or near misses, and document and share lessons learned
71. Perform job walks regularly to ensure that the safety procedures are being followed
o | The jobsite must be inspected regularly in order to identify actual or potential hazards

## QUALITY MANAGEMENT
QUALITY MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
72. Clarify quality requirements for field personnel
o | The Project Manager or site supervisor should review the specifications, identify all references to quality, and list them in a table.
o | The table should be given to the foremen so that they can review the specifications to better understand the specific quality requirements.
o | Quality expectations should be discussed during a meeting between the site supervisor and the foremen, and any company-specific requirements should be identified.
73. Check and document the quality of installation through regular site visits
o | Using the list of specified quality requirements, the site supervisor and/or project manager should walk the site to ensure compliance with the requirements.
o | Any discrepancies should be noted in the table, and the foremen should be made aware of each discrepancy and correct them.
74. Develop and implement commissioning and testing procedures
o | Standardized commissioning and testing procedures for common types of equipment simplifies the process and improves the chances that these processes will be completed with minimum problems.
o | Assigning one person to be responsible for commissioning and testing for all jobs within the company is an efficient way to build up special expertise that can improve the efficiency of commissioning and testing.
75. Use a pre-punch list to identify unresolved quality issues before completion
o | A preliminary punch list (i.e., pre-punch list) precedes the official punch list and is essentially a list of discrepancies that need to be corrected before the final inspection
o | The pre-punch list should be assembled either on a continuous basis so that deficiencies get corrected throughout the course of the project or during the last 5% of the project to ensure very few discrepancies remain before the final inspection.

## PROJECT CLOSEOUT
QUALITY MANAGEMENT CHECKLIST FOR PROJECT MANAGEMENT
þ | SUB-ACTIVITIES
72. Clarify quality requirements for field personnel
o | The Project Manager or site supervisor should review the specifications, identify all references to quality, and list them in a table.
o | The table should be given to the foremen so that they can review the specifications to better understand the specific quality requirements.
o | Quality expectations should be discussed during a meeting between the site supervisor and the foremen, and any company-specific requirements should be identified.
73. Check and document the quality of installation through regular site visits
o | Using the list of specified quality requirements, the site supervisor and/or project manager should walk the site to ensure compliance with the requirements.
o | Any discrepancies should be noted in the table, and the foremen should be made aware of each discrepancy and correct them.
74. Develop and implement commissioning and testing procedures
o | Standardized commissioning and testing procedures for common types of equipment simplifies the process and improves the chances that these processes will be completed with minimum problems.
o | Assigning one person to be responsible for commissioning and testing for all jobs within the company is an efficient way to build up special expertise that can improve the efficiency of commissioning and testing.
75. Use a pre-punch list to identify unresolved quality issues before completion
o | A preliminary punch list (i.e., pre-punch list) precedes the official punch list and is essentially a list of discrepancies that need to be corrected before the final inspection
o | The pre-punch list should be assembled either on a continuous basis so that deficiencies get corrected throughout the course of the project or during the last 5% of the project to ensure very few discrepancies remain before the final inspection.