SOP: 9.2.010 – Team Selection

Department: Project Management / Operations

Related SOPs:

• 9.2.005 - Review Contract for High Risk Clauses

• 9.2.015 - Project Turnover Meeting

• 9.2.020 - Procurement of Large Feeder Wire

• 9.2.030 - Review Contract for Unfavorable or High-Risk Clauses

• 9.2.040 - Project Manager Reviews Plans Specifications & Schedule

• 9.2.057 - Identify VE and Prefabrication Opportunities

• 9.2.060 - Create Issue List and Begin RFI Process

• 9.2.070 - Conduct Site Visit

Purpose

To define the process by which the Branch Manager assigns a Project Manager and selects a Foreman for each newly awarded project, ensuring the right leadership is in place before project planning and mobilization begin.

Scope

This SOP applies to Branch Managers, Project Managers, and General Superintendents for all projects immediately after receipt of a contract for review, Letter of Intent (LOI), or Notice to Proceed (NTP), and prior to the Project Turnover Meeting and mobilization.

Roles & Responsibilities

Branch Manager: Selects the Project Manager based on project complexity, workload, and client requirements. Selects the Foreman with input from the General Superintendent. Confirms all assignments and communicates to the team.

General Superintendent (GS): Provides input on foreman availability, skillset, and suitability for the project. Validates the selection aligns with current field commitments.

Project Manager (PM): Once assigned, reviews the project scope, confirms readiness, and documents assignments in the project file. Coordinates the Project Turnover Meeting (9.2.015).

Requirements

• Contract documents, LOI, or NTP

• Current PM workload and availability summary

• Foreman availability and skills matrix

• Project complexity assessment (size, scope, client)

• Team Assignment Form or project log entry

Procedure

Step 1: Trigger: Project Awarded

• Upon receipt of a contract for review, LOI, or NTP, the Branch Manager initiates team selection.

• The Branch Manager reviews the project scope, size, client, and complexity to determine leadership needs.

Step 2: Assign Project Manager

• The Branch Manager selects a PM based on current workload, project type experience, and client relationship.

• The PM is formally notified and provided with the contract package and award summary.

Step 3: Select Foreman

• The Branch Manager, with input from the General Superintendent, selects a Foreman based on availability, skill set, and project fit.

• The GS confirms the selected Foreman's current commitments and transition timeline.

Step 4: Confirm Roles and Notify Team

• The Branch Manager confirms all assignments (PM, Foreman, and supporting roles if applicable).

• Assignments are documented in the project file or team assignment log.

Step 5: Document and Communicate

• The PM records team assignments in the project folder.

• The PM communicates roles to all stakeholders and begins scheduling the Project Turnover Meeting (9.2.015).

Appendix

Appendix – References & Training Materials

Training Materials (Foreman Training Binder):

• Tab 2: Preplanning & Staging

• Tab 3: Kickoff/Project Turnover Meeting

Job Descriptions (Policy Manual Section 7):

• 7.2.4 Foreman

• 7.2.5 Project Superintendent

• 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

• 9.5 Project Management

• 9.3 Field Leadership

• 9.4 General Superintendents

Reference Documents:

• Team Assignment Form

• PM Workload Summary Template

• Foreman Skills Matrix