SOP: 9.2.030 – Review Contract for Unfavorable or High-Risk Clauses

Department: Project Management / Pre-Construction

Related SOPs:

• 9.2.005 - Review Contract for High Risk Clauses

• 9.2.010 - Team Selection

• 9.2.015 - Project Turnover Meeting

• 9.2.020 - Procurement of Large Feeder Wire

• 9.2.040 - Project Manager Reviews Plans Specifications & Schedule

• 9.2.070 - Conduct Site Visit

• 9.2.120 - Establish Tracking & Control Systems

• 9.2.130 - Construction Execution Kickoff Meeting

Purpose

To ensure all project contracts are reviewed systematically for unfavorable or high-risk clauses that could affect project execution, budget, or liability, and to define mitigation measures prior to mobilization.

Scope

This SOP applies to all Project Managers during the pre-construction phase of awarded projects. It covers all contract types including general conditions, subcontract agreements, and owner-issued contracts.

Roles & Responsibilities

Project Manager: Leads contract review, completes checklist, and escalates risks to Branch Manager.

Estimator: Provides bid assumptions and clarifications for comparison.

Field Supervisor: Identifies field-related risks tied to contractual obligations.

Branch Manager: Approves mitigation strategy for high-risk clauses.

Requirements

• Contract Review Checklist (Table 4.6)

• Executed contract documents (general conditions, terms, scope)

• Bid submission and clarification letters

• Insurance and bonding requirements

Procedure

Step 1: Collect Documents

• Gather executed contracts, specifications, drawings, and bid clarifications.

Step 2: Review Key Clauses

• Complete Contract Review Checklist with focus on:

• • Indemnification and liability allocation

• • Delay clauses and liquidated damages

• • Dispute resolution (ADR, arbitration, mediation)

• • Change order notification procedures

• • Insurance, bonding, and permit requirements

Step 3: Identify Risks

• Flag unfavorable terms and propose mitigation strategies.

• Review risks with Branch Manager for approval.

Step 4: Recordkeeping

• Save completed checklist and notes in the project folder.

• Incorporate findings into turnover meeting agenda (9.2.015 – Project Turnover Meeting).

Appendix

Appendix – References & Training Materials

Training Materials (Foreman Training Binder):

• Tab 2: Preplanning & Staging

• Tab 3: Kickoff/Project Turnover Meeting

• Tab 5: Purchasing Buy out

• Tab 6: Scheduling

• Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

• 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

• 9.5 Project Management

• 9.7 Estimating

• 9.3 Field Leadership

Reference Documents:

• GSL Pre-Construction Planning – Section 4.3 Scope and Contract Review

• Contract Review Checklist (Table 4.6)

• Contract Review Checklist (sample)

• Insurance & Bonding Matrix

• Dispute Resolution Clause Examples