SOP 9.2.050 – Field Supervisor Reviews Plans, Specifications & Schedule

Department: Field Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.015 - Project Turnover Meeting; 9.2.040 - Project Manager Reviews Plans Specifications & Schedule; 9.2.055 - Compare Estimated vs Planned Performance; 9.2.057 - Identify VE and Prefabrication Opportunities; 9.2.100 - Prepare Layout & Sequencing Plan; 9.2.110 - Develop Project Schedule; 9.4.330 - Develop Schedule Recovery Plans
Reference: GSL Pre-Construction Planning – Scope & Schedule Review

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.5 Project Superintendent

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To ensure Field Supervisors conduct a detailed review of project drawings, specifications, and schedules with a focus on constructability, sequencing, and field logistics, supporting accurate execution planning.

Scope

This SOP applies to Field Supervisors assigned to projects during the pre-construction planning phase. It must be completed before site mobilization.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Reviews drawings, specifications, and schedules with a field perspective; identifies constructability and logistics issues. |
| Project Manager | Incorporates feedback into the Project Execution Plan (PEP). |
| General Superintendent | Reviews manpower forecasts and sequencing adjustments. |
| Safety Coordinator | Identifies hazards tied to logistics or sequencing. |

Required Documents and Tools

- Latest drawings and specifications

- Contract schedules and milestones

- Bid labor and logistics assumptions

- Scope & Schedule Review Checklist (Table 4.7)

- Site logistics plan (if available)

Procedure

Step 1: Gather Documents

- Collect current drawings, specifications, schedules, and bid assumptions.

Step 2: Review for Constructability

- Verify installation feasibility of major systems.

- Identify site access issues, workspace conflicts, and constructability risks.

Step 3: Validate Schedule Alignment

- Assess manpower loading requirements.

- Identify risks in durations, sequencing, or milestones.

Step 4: Document Findings

- Record observations in Scope & Schedule Review Checklist.

- Flag issues that may require RFIs.

Step 5: Provide Feedback

- Submit findings to Project Manager and General Superintendent for incorporation into the PEP.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Field Review Notes | Field Supervisor | Project Folder |
| Updated Scope & Schedule Checklist | Field Supervisor / PM | Project Folder |
| Manpower Input | Field Supervisor | PEP File |

Compliance & Review

| KPI | Target |
| --- | --- |
| Field review completed prior to turnover | 100% |
| Constructability issues documented | 100% |
| Findings incorporated into PEP | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 Scope & Contract Review

- Scope & Schedule Review Checklist (Table 4.7)

Appendix

- Sample Field Review Notes

- Manpower Forecast Template

- Site Logistics Checklist