SOP 9.065.41 – Develop Labor Budget

Department: Project Management / Operations
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs:9.1.050 - Prepare Construction Takeoff; 9.2.005 - Review Contract for High Risk Clauses; 9.2.010 - Team Selection; 9.2.015 - Project Turnover Meeting; 9.2.055 - Compare Estimated vs Planned Performance; 9.2.140 - Develop Project Budget; 9.4.400 - Monitor Project Costs; 9.4.560 - Manage Manpower Allocation

- 9.060.41 – Prepare Material Handling Plan

- 9.075.41 – Develop Project Schedule

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 2: Preplanning & Staging

- Tab 3: Kickoff/Project Turnover Meeting

- Tab 5: Purchasing Buy out

- Tab 6: Scheduling

- Tab 7: Job Plans

Job Descriptions (Policy Manual Section 7):

- 7.2.5 Project Superintendent

- 7.3.1 Operations Management

- 7.3.3 Estimating

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.7 Estimating

- 9.3 Field Leadership

================================================================================

Purpose

To establish a standardized process for creating a project-specific labor budget that reflects estimated manhours by phase and supports resource planning, cost tracking, and productivity measurement.

Scope

Applies to all awarded projects and must be completed prior to mobilization. Involves collaboration between the PM, Estimator, General Superintendent, and Field Foreman.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads labor budgeting process and reconciles with project scope and schedule. |
| Estimator | Provides baseline estimate manhours and unit pricing. |
| General Superintendent | Validates manpower loading and sequencing. |
| Field Foreman | Provides input on labor requirements and install complexity. |
| Project Engineer | Assists with formatting, calculations, and data entry. |

Required Documents and Tools

- Bid manhour estimate

- Construction schedule

- Scope breakdown / system list

- GSL Labor Budget Template

- Productivity targets (unit hours per system)

- Prefab plan (if applicable)

Procedure

Step 1: Review Estimate and Scope

- PM and Estimator review bid manhour breakout

- Confirm scope matches awarded contract

- Identify areas with significant risk or assumed productivity

Step 2: Align Budget with Schedule

- PM reviews construction schedule and identifies phases:

  - Underground

  - Rough-in

  - Trim

  - Prefab assemblies

  - Equipment terminations

- Allocate manhours to match duration and crew load

Step 3: Break Down by System and Phase

- Use GSL Labor Budget Template to enter hours by:

  - System (lighting, power, gear, fire alarm, etc.)

  - Phase (underground, rough, finish)

  - Area or floor (if applicable)

- Include general conditions or site labor separately

Step 4: Validate with Field Team

- GS and Foreman review proposed budget

- Adjust based on complexity, productivity, and past performance

- Agree on weekly labor curves or loading plans

Step 5: Finalize and Save

- PM finalizes labor budget

- Uploads to project folder

- Used as the baseline for tracking productivity and labor forecasts

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Labor Budget Worksheet | Project Manager | Job Cost / Labor Folder |
| GS/Foreman Budget Signoff | General Superintendent | Project Folder |
| Labor Curve Chart | Project Engineer | Planning / Forecast Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Labor budget complete before field start | 100% |
| Reviewed and approved by GS and Foreman | 100% |
| Manhours broken down by system and phase | 100% |

References

- Estimating Labor Summary

- Project Schedule

- Historical Productivity Database

Appendix

- GSL Labor Budget Template

- Example Phase Loading Chart

- Unit Rate Reference Sheet