SOP: 9.3.060 – Setup Sanitary Facilities

Department: Project Management / Safety

Related SOPs:

• 9.3.010 - Setup Office Trailer

• 9.3.020 - Setup Storage Trailer

• 9.3.030 - Setup Site Fencing and Access Control

• 9.3.040 - Setup Temporary Power

• 9.3.050 - Setup Temporary Water

Purpose

To provide adequate sanitary facilities (toilets, wash stations) for workers in compliance with OSHA requirements and project specifications.

Scope

This SOP applies to Project Managers and Safety Coordinators during site mobilization and throughout the project.

Roles & Responsibilities

Project Manager: Coordinates contracts with sanitary facility vendors. Approves placement plan.

Field Supervisor: Determines placement for accessibility and logistics. Coordinates delivery and setup.

Safety Coordinator: Ensures OSHA compliance and maintains the sanitation inspection log.

Requirements

• Site logistics plan

• Sanitary facility vendor contract

• OSHA sanitation standards (29 CFR 1926.51)

• Inspection log template

Procedure

Step 1 – Plan Facility Locations

• Identify accessible, evenly distributed locations per the site logistics plan.

• Ensure ADA-compliant units are included if required by project or local regulations.

Step 2 – Secure Vendor Services

• Contract portable toilet and wash station vendor.

• Establish service and cleaning schedule (frequency based on headcount).

Step 3 – Install Facilities

• Place units per site logistics plan in approved locations.

• Anchor units if required for safety (wind, slope, etc.).

Step 4 – Maintain Facilities

• Vendor provides regular cleaning and servicing per contract.

• Safety Coordinator inspects facilities weekly and documents findings.

Step 5 – Document Compliance

• Maintain sanitation inspection log with dates, findings, and corrective actions.

• Report deficiencies immediately and confirm resolution.

Appendix

Appendix – Templates & Checklists

• Sanitary Facilities Setup Checklist

• Inspection Log Template

Appendix – References & Training Materials

Training Materials (Foreman Training Binder):

• Tab 4: Staging & Job Familiarization

• Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

• 7.2.4 Foreman

• 7.2.6 Project Safety Coordinator

• 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

• 9.5 Project Management

• 9.3 Field Leadership

Reference Documents:

• OSHA Sanitation Standards (29 CFR 1926.51)