SOP: 9.4.010 – Conduct Coordination Meetings

Department: Project Management / Field Operations

Related SOPs:

• 9.4.020 - Conduct Subcontractor Coordination Meetings

• 9.4.030 - Conduct Client/Owner Meetings

• 9.4.040 - Conduct Safety Meetings

• 9.4.045 - Identify Value Engineering & Prefabrication Opportunities

• 9.4.050 - Conduct Prefabrication Coordination Meetings

• 9.4.055 - Procurement of Large Feeder Wire

• 9.4.060 - Conduct Quality Meetings

• 9.4.345 - Conduct Schedule Review Meetings

Purpose

To establish a standard process for conducting project coordination meetings to ensure alignment between all project stakeholders, resolve issues, and review progress.

Scope

This SOP applies to Project Managers, Field Supervisors, Subcontractors, and Design Team representatives. All coordination meeting documentation must be filed per Document Filing Standards SOP (SOP # TBD per crosswalk).

Roles & Responsibilities

Project Manager: Schedules and chairs coordination meetings. Sets the agenda and ensures action items are tracked to completion.

Field Supervisor: Provides field updates and identifies coordination issues.

Subcontractors: Share progress updates and upcoming needs.

Design Team / Consultants: Provide design clarifications as required.

Site Administrator: Records minutes, action items, and files records per Document Filing Standards SOP (SOP # TBD per crosswalk).

Requirements

• Document Filing Standards SOP (SOP # TBD per crosswalk)

• Coordination meeting agenda template

• Action item log

• Previous meeting minutes (for follow-up)

Procedure

Step 1 – Schedule Meetings

• Schedule coordination meetings weekly (or as required by project complexity).

• Distribute calendar invites to all required attendees.

Step 2 – Prepare and Distribute Agenda

• Prepare meeting agenda at least 24 hours in advance.

• Include standing items: safety, progress updates, upcoming activities, coordination issues, and action items.

Step 3 – Conduct Meeting

• Review safety topics and any open incidents.

• Discuss progress updates from all trades and disciplines.

• Review upcoming activities, coordination issues (site access, deliveries, manpower, conflicts).

• Assign and review action items with owners and due dates.

Step 4 – Record and Distribute Minutes

• Record attendance and meeting minutes.

• Distribute minutes to all attendees within 48 hours.

Step 5 – Track Action Items and File Records

• Update the action item log with new items and close completed items.

• File minutes and action item log per Document Filing Standards SOP (SOP # TBD per crosswalk).

Appendix

Appendix – Templates & Checklists

• Coordination Meeting Agenda Template

• Action Item Log Example

• Meeting Minutes Template

Appendix – References & Training Materials

Training Materials (Foreman Training Binder):

• Tab 6: Scheduling

• Tab 8: Change Order Process

• Tab 9: Submittals

• Tab 12: Look Ahead

• Tab 14: Daily Reports

• Tab 22: Document Management

• Tab 41: Material Management

• Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

• 7.2.4 Foreman

• 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

• 9.5 Project Management

• 9.3 Field Leadership

• 9.4 General Superintendents