SOP 9.4.020 – Conduct Subcontractor Coordination Meetings

Department: Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.010 - Conduct Coordination Meetings; 9.4.030 - Conduct Client/Owner Meetings; 9.4.040 - Conduct Safety Meetings; 9.4.045 - Identify Value Engineering & Prefabrication Opportunities; 9.4.050 - Conduct Prefabrication Coordination Meetings; 9.4.055 - Procurement of Large Feeder Wire; 9.4.060 - Conduct Quality Meetings; 9.4.290 - Manage Subcontractor Communications
Reference: GSL Project Manager Procedures – Coordination

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To lead regular subcontractor coordination meetings to ensure subcontractor activities align with project schedule, logistics, and safety requirements.

Scope

This SOP applies to Project Managers, Field Supervisors, and all subcontractors assigned to the project.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Prepares and distributes meeting agenda; tracks subcontractor action items. |
| Subcontractors | Provide progress updates, manpower forecasts, and coordination requirements. |
| Field Supervisor | Reports logistics needs and field conditions. |
| Safety Coordinator | Reviews safety performance and compliance. |

Required Documents and Tools

- Subcontractor coordination agenda template

- Updated project schedule

- Site logistics plan

- Safety compliance logs

Procedure

- Schedule Meetings – Weekly or per GC/owner requirements.

- Prepare Agenda – Include schedule, manpower, logistics, safety, and open issues.

- Conduct Meeting – Document subcontractor progress and risks.

- Resolve Issues – Coordinate sequencing and site logistics conflicts.

- Record Outcomes – Issue minutes and update subcontractor action log.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Subcontractor Meeting Agenda | Project Manager | Project Folder |
| Meeting Minutes | PM | Project Folder |
| Subcontractor Action Log | PM | Shared Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Weekly subcontractor meetings conducted | 100% |
| Minutes issued within 48 hrs | ≥95% |
| Action items closed prior to next meeting | ≥90% |

References

- GSL Project Manager Procedures – Coordination

Appendix

- Subcontractor Meeting Agenda Template

- Subcontractor Action Log Template