SOP 9.4.030 – Conduct Client/Owner Meetings

Department: Project Management
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.010 - Conduct Coordination Meetings; 9.4.020 - Conduct Subcontractor Coordination Meetings; 9.4.040 - Conduct Safety Meetings; 9.4.045 - Identify Value Engineering & Prefabrication Opportunities; 9.4.050 - Conduct Prefabrication Coordination Meetings; 9.4.055 - Procurement of Large Feeder Wire; 9.4.060 - Conduct Quality Meetings; 9.4.285 - Manage Client/Owner Communications
Reference: GSL Project Manager Procedures – Coordination

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.6 Project Safety Coordinator

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To conduct meetings with the client/owner to provide project updates, resolve issues, and ensure contractual and performance expectations are met.

Scope

This SOP applies to Project Managers, Branch Managers, and project teams when interfacing with the client/owner.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Leads meetings, presents updates, addresses issues, and records commitments. |
| Branch Manager | Provides executive oversight and represents GSL interests. |
| Client/Owner | Reviews project status, raises concerns, approves changes. |
| Safety Coordinator | Provides safety compliance summary if required. |

Required Documents and Tools

- Client meeting agenda template

- Contract and project schedule

- Project Execution Plan (PEP)

- Risk and issue log

Procedure

- Schedule Meetings – Per contract or as requested by the client.

- Prepare Agenda – Cover scope, schedule, budget, risks, safety, and quality.

- Conduct Meeting – Review progress, open issues, and action items.

- Record Outcomes – Document minutes and owner commitments.

- Distribute Records – Provide copies to client and internal team.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Client Meeting Agenda | Project Manager | Project Folder |
| Meeting Minutes | PM | Project Folder |
| Issue/Commitment Log | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| Client meetings held per contract requirements | 100% |
| Minutes distributed within 48 hrs | ≥95% |
| Owner commitments tracked to closure | 100% |

References

- GSL Project Manager Procedures – Coordination

Appendix

- Client Meeting Agenda Template

- Commitment Tracking Log