SOP 9.4.045 – Identify Value Engineering & Prefabrication Opportunities

Department: Project Management / Prefabrication
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.057 - Identify VE and Prefabrication Opportunities; 9.4.010 - Conduct Coordination Meetings; 9.4.020 - Conduct Subcontractor Coordination Meetings; 9.4.030 - Conduct Client/Owner Meetings; 9.4.040 - Conduct Safety Meetings; 9.4.050 - Conduct Prefabrication Coordination Meetings; 9.4.055 - Procurement of Large Feeder Wire; 9.4.585 - Plan Prefabrication Resources
Reference: GSL Pre-Construction Planning – Value Engineering & Prefabrication

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To identify and evaluate opportunities for value engineering (VE) and prefabrication to reduce cost, improve efficiency, and simplify work without compromising project scope or quality.

Scope

This SOP applies to Project Managers, Field Supervisors, and Prefabrication Leads during the pre-construction planning phase of all awarded projects.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Facilitates identification of VE/prefab opportunities; integrates approved options into PEP. |
| Prefabrication Lead | Reviews drawings for prefab potential; develops prefab strategy sheet. |
| Field Supervisor | Validates constructability and field feasibility of proposals. |
| Estimator | Confirms VE proposals align with bid assumptions and budget. |

Required Documents and Tools

- Current drawings and specifications

- Prefab shop capabilities catalog

- VE proposal log template

- PEP (Project Execution Plan)

Procedure

Step 1: Review Drawings and Specs

- Identify repetitive, modular, or offsite-constructible components.

- Note materials or assemblies that may have VE alternatives.

Step 2: Analyze Opportunities

- Evaluate cost savings, labor efficiency, and schedule benefits.

- Confirm prefab shop capacity and logistics feasibility.

Step 3: Document Proposals

- Record each opportunity in a VE/Prefab Proposal Log.

- Provide cost/benefit analysis and schedule impact notes.

Step 4: Approve and Integrate

- Present opportunities at turnover or planning meetings.

- Integrate approved items into PEP, budget, and procurement plan.

Step 5: Monitor Execution

- Track implementation of approved VE/prefab opportunities.

- Update logs and share with project team.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| VE/Prefab Proposal Log | Project Manager | Project Folder |
| Prefab Strategy Sheet | Prefab Lead | Prefab Subfolder |
| Updated PEP | PM | Project Folder |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of projects reviewed for VE/prefab | 100% |
| Documented proposals with cost/schedule impact | 100% |
| Approved opportunities integrated into PEP | 100% |

References

- GSL Pre-Construction Planning – Section 4.3 VE & Prefabrication

Appendix

- VE/Prefab Proposal Log (sample)

- Prefab Strategy Sheet Template

- Example Cost/Benefit Analysis