SOP 9.4.315 – Develop Project Schedule

Department: Project Management / Scheduling
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.110 - Develop Project Schedule; 9.4.320 - Update Project Schedule; 9.4.325 - Monitor Schedule Performance; 9.4.330 - Develop Schedule Recovery Plans; 9.4.335 - Prepare Lookahead Schedules; 9.4.340 - Manage Resource-Loaded Schedules; 9.4.345 - Conduct Schedule Review Meetings; 9.4.350 - Manage Schedule Change Requests
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To establish a baseline project schedule that reflects contractual milestones, critical path activities, and resource requirements.

Scope

This SOP applies to Project Managers, Superintendents, and Scheduling Coordinators.
All schedules and updates must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Develops baseline schedule, aligns with contract requirements. |
| Superintendent | Provides manpower and field sequencing input. |
| Scheduling Coordinator | Supports PM in software setup and reporting. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Contract schedule requirements

- Scheduling software (Primavera P6, MS Project, or equivalent)

Procedure

- Review contract milestones and scheduling requirements.

- Break down project into phases and activities.

- Define logic ties and critical path.

- Input activities and durations into scheduling software.

- Review with team and finalize baseline.

- File baseline schedule per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Baseline Schedule | Project Manager | Per SOP 190A |
| Schedule Narrative | PM | Per SOP 190A |
| Milestone Log | Scheduling Coordinator | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| Baseline schedule submitted within 30 days of turnover | 100% |
| All critical path activities identified | 100% |
| Owner acceptance of baseline schedule | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Baseline Schedule Example

- Critical Path Diagram