SOP 9.4.350 – Manage Schedule Change Requests

Department: Project Management / Scheduling / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.2.110 - Develop Project Schedule; 9.4.315 - Develop Project Schedule; 9.4.320 - Update Project Schedule; 9.4.325 - Monitor Schedule Performance; 9.4.330 - Develop Schedule Recovery Plans; 9.4.345 - Conduct Schedule Review Meetings; 9.4.360 - Manage Change Orders
Reference: GSL Project Manager Procedures – Scheduling

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To evaluate, document, and process schedule change requests to ensure all modifications are justified, approved, and properly incorporated into the project schedule.

Scope

This SOP applies to Project Managers, Branch Managers, and Site Administrators.
All schedule change requests must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Evaluates change request, prepares analysis, and submits for approval. |
| Branch Manager | Reviews and approves significant changes impacting contract dates. |
| Site Administrator | Logs and files approved change requests. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Change request form template

- Updated project schedule

Procedure

- Receive schedule change request from internal team, subcontractor, or owner.

- Evaluate impact on critical path, milestones, and resources.

- Prepare change request form with supporting analysis.

- Submit to Branch Manager and/or Owner for approval as required.

- Incorporate approved changes into project schedule.

- File change request and revised schedule per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Change Request Form | Project Manager | Per SOP 190A |
| Approval Record | Branch Manager | Per SOP 190A |
| Revised Schedule | PM | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of change requests logged | 100% |
| Evaluations completed within 5 business days | ≥95% |
| Approved changes filed and incorporated | 100% |

References

- GSL Project Manager Procedures – Scheduling

- SOP 9.41.190A – Document Filing Standards

Appendix

- Change Request Form Template

- Example Impact Analysis