SOP 9.4.370 – Manage Owner Directives

Department: Project Management / Contract Administration
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.355 - Manage Project Scope; 9.4.360 - Manage Change Orders; 9.4.365 - Manage Potential Change Orders (PCOs); 9.4.375 - Manage Scope Clarifications; 9.4.380 - Manage Backcharges; 9.4.385 - Manage Force Account Work; 9.4.390 - Manage Claims
Reference: GSL Project Manager Procedures – Scope & Change Control

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.3.3 Estimating

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To document and manage all owner directives that modify or clarify the scope of work, ensuring contractual and financial impacts are tracked.

Scope

This SOP applies to Project Managers, Site Administrators, and Estimators.
All owner directives must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Project Manager | Reviews directive, assesses impact, and communicates to team. |
| Estimator | Prepares cost and schedule impacts. |
| Site Administrator | Logs and files owner directives. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Owner directive log template

- Change order forms

Procedure

- Receive directive from owner in writing.

- Log directive and assign tracking number.

- Assess scope, cost, and schedule impact.

- Process as change order or PCO if required.

- File directive and responses per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Owner Directive Log | Site Administrator | Per SOP 190A |
| Impact Assessment | Estimator | Per SOP 190A |
| Directive & Response | Project Manager | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of directives logged within 24 hrs | 100% |
| Cost/schedule impacts evaluated within 5 days | ≥95% |
| Filed and cross-referenced with COs | 100% |

References

- GSL Project Manager Procedures – Scope & Change Control

- SOP 9.41.190A – Document Filing Standards

Appendix

- Owner Directive Log Template

- Impact Assessment Form