SOP 9.4.630 – Manage Material Receiving

Department: Field Operations / Procurement
Created by: Tom Ewing
Effective Date: [Insert Date]
Version: 1.0
Related SOPs: 9.4.605 - Issue Purchase Orders; 9.4.620 - Manage Expediting; 9.4.625 - Manage Delivery Tracking; 9.4.631 - Release of Large Feeder Wire; 9.4.635 - Manage Material Inspection; 9.4.640 - Manage Storage and Logistics; 9.4.645 - Manage Material Handling; 9.4.650 - Manage Inventory
Reference: GSL Project Manager Procedures – Procurement

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 6: Scheduling

- Tab 8: Change Order Process

- Tab 9: Submittals

- Tab 12: Look Ahead

- Tab 14: Daily Reports

- Tab 22: Document Management

- Tab 41: Material Management

- Tab 57: ProCore

Job Descriptions (Policy Manual Section 7):

- 7.2.4 Foreman

- 7.3.1 Operations Management

- 7.4.4 Purchasing Manager

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

- 9.4 General Superintendents

================================================================================

Purpose

To ensure materials and equipment received on-site are verified for accuracy, quality, and compliance with purchase orders.

Scope

This SOP applies to Field Supervisors, Project Managers, and Purchasing.
All receiving documentation must be filed per SOP 9.41.190A – Document Filing Standards.

Roles and Responsibilities

| Role | Responsibilities |
| --- | --- |
| Field Supervisor | Verifies quantities, condition, and compliance at delivery. |
| Project Manager | Confirms received items match procurement plan. |
| Purchasing | Resolves discrepancies with vendors. |
| Site Administrator | Logs receiving documentation. |

Required Documents and Tools

- SOP 9.41.190A – Document Filing Standards

- Receiving log template

- Packing slips and BOLs

Procedure

- Inspect all deliveries upon arrival.

- Verify quantities and compare against PO.

- Document condition and compliance with specifications.

- Record in receiving log and notify PM of discrepancies.

- File receiving records per SOP 190A.

Deliverables

| Document | Owner | Location |
| --- | --- | --- |
| Receiving Log | Site Administrator | Per SOP 190A |
| Verified Packing Slips | Field Supervisor | Per SOP 190A |
| Discrepancy Reports | PM / Purchasing | Per SOP 190A |

Compliance & Review

| KPI | Target |
| --- | --- |
| 100% of deliveries inspected at arrival | 100% |
| Discrepancies reported within 24 hrs | 100% |
| Records filed daily | 100% |

References

- GSL Project Manager Procedures – Procurement

- SOP 9.41.190A – Document Filing Standards

Appendix

- Receiving Log Template

- Discrepancy Report Example