SOP: 9.5.010 - Conduct Commissioning Meetings

Department: Project Management / Quality

Related SOPs:

- 9.2.080 - Prepare Material Handling Plan

- 9.4.570 - Manage Material Allocation

- 9.4.630 - Manage Material Receiving
- 9.4.635 - Manage Material Inspection
- 9.4.640 - Manage Storage and Logistics
- 9.4.645 - Manage Material Handling
- 9.4.650 - Manage Inventory
- 9.5.550 - Manage Commissioning Activities

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 38: Testing

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4 Business Administration

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for conducting commissioning meetings, ensuring proper coordination between all parties during the testing, verification, and turnover phases of the project.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- Systems require commissioning and testing

- Owner/third-party commissioning agent is involved

- Functional performance testing is required

- System turnover coordination is needed

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Leads meeting coordination; Tracks commissioning progress |

| Commissioning Agent (R) | Conducts testing; Documents results; Identifies deficiencies |

| Field Supervisor (R) | Supports testing activities; Coordinates corrections |

| Quality/QA-QC (C) | Verifies quality requirements; Reviews test results |

| Subcontractors (R) | Participate in testing; Correct deficiencies |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Commissioning plan and schedule

- System testing protocols

- Equipment startup procedures

- Test equipment and instruments

- Deficiency tracking log

- Meeting agenda template

============================================================

PROCEDURE

============================================================

STEP 1 - Schedule Commissioning Meetings

--------------------------------------

PM coordinates meeting schedule:

- Align with commissioning plan milestones

- Schedule kickoff meeting before testing begins

- Plan regular progress meetings during commissioning

- Schedule final commissioning review meeting

- Invite all required participants

STEP 2 - Conduct Kickoff Meeting

--------------------------------------

Initial commissioning meeting covers:

- Review commissioning plan and schedule

- Confirm testing sequences and protocols

- Assign responsibilities for each system

- Establish deficiency tracking process

- Confirm documentation requirements

- Set communication protocols

STEP 3 - Conduct Progress Meetings

--------------------------------------

Regular meetings during commissioning:

- Review testing completed since last meeting

- Discuss test results and findings

- Track deficiency corrections

- Adjust schedule as needed

- Coordinate upcoming tests

- Document decisions and action items

STEP 4 - Track Deficiencies

--------------------------------------

Manage issues identified:

- Log all deficiencies in tracking system

- Assign responsibility for corrections

- Set target completion dates

- Verify corrections are complete

- Document re-testing results

- Close out resolved items

STEP 5 - Conduct Final Review Meeting

--------------------------------------

Closing commissioning meeting:

- Review all test results

- Confirm all deficiencies resolved

- Obtain commissioning agent sign-off

- Review O&M documentation status

- Confirm training requirements

- Transition to closeout phase

STEP 6 - Document and Archive

--------------------------------------

Complete commissioning documentation:

- Compile all test reports

- Document meeting minutes

- Archive deficiency logs

- Obtain required signatures

- Submit to project files

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Kickoff meeting held before testing | 100% |

| Progress meetings held per schedule | 100% |

| All deficiencies tracked and resolved | 100% |

| Final sign-off obtained | 100% |

============================================================

APPENDIX

============================================================

- Commissioning Meeting Agenda Template

- Deficiency Tracking Log

- Test Protocol Checklist

- Sign-off Form Template

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.545 - Conduct Commissioning Meetings

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee