SOP: 9.6.030 - Manage As-Built Drawings

Department: Project Management / Field Operations

Related SOPs:

- 9.6.005 - Prepare for Turnover (Field Perspective)

- 9.6.015 - Manage Project Turnover Documentation

- 9.6.020 - Manage Punch List Closeout
- 9.6.035 - Submit Warranties
- 9.6.040 - Submit O&M Manuals
- 9.6.065 - Archive Project Documentation

============================================================

================================================================================

DOCUMENT REFERENCES

================================================================================

Training Materials (Foreman Training Binder):

- Tab 18: Job Close Out

- Tab 22: Document Management

Job Descriptions (Policy Manual Section 7):

- 7.3.1 Operations Management

- 7.4.5 Administrative Support

Management Directives (Policy Manual Section 9):

- 9.5 Project Management

- 9.3 Field Leadership

================================================================================

PURPOSE

============================================================

To establish a standardized process for managing as-built drawings, ensuring accurate documentation of installed conditions for owner records and future maintenance.

============================================================

SCOPE

============================================================

Applies to all projects / situations where:

- As-built drawings are contractually required

- Field conditions differ from design

- Owner needs accurate facility records

============================================================

ROLES & RESPONSIBILITIES

============================================================

| Role | Responsibility |

|------|----------------|

| Project Manager (A) | Manages as-built process; Submits final drawings |

| Field Supervisor (R) | Reviews markups for accuracy; Coordinates with field |

| Foreman (R) | Creates field markups; Documents actual conditions |

| Project Engineer/APM (R) | Compiles markups; Transfers to final drawings |

RACI: R=Responsible, A=Accountable, C=Consulted, I=Informed

============================================================

REQUIREMENTS

============================================================

- Clean set of contract drawings

- Red/green markup pens

- Field measurement tools

- As-built standards/legend

- CAD/drafting capability

- Final drawing format requirements

============================================================

PROCEDURE

============================================================

STEP 1 - Establish Markup Process

--------------------------------------

At project start:

- Provide clean drawing set to field

- Distribute as-built markup standards

- Train field on documentation requirements

- Establish regular markup review schedule

- Identify who maintains master set

STEP 2 - Document Field Conditions

--------------------------------------

During construction:

- Mark changes as work is installed

- Document routing variations

- Note equipment/device locations

- Record concealed conditions

- Update regularly (not at project end)

STEP 3 - Review Markups for Accuracy

--------------------------------------

FS/PM review field markups:

- Verify changes are documented

- Check for completeness

- Clarify unclear markings

- Confirm measurements accurate

- Identify missing information

STEP 4 - Transfer to Final Drawings

--------------------------------------

Create final as-builts:

- Compile all field markups

- Transfer to CAD or clean drawings

- Include all changes and conditions

- Follow contract format requirements

- Verify accuracy against markups

STEP 5 - Submit for Review

--------------------------------------

Submit draft as-builts:

- Review internally for completeness

- Submit to GC/Owner for review

- Address any comments

- Make required revisions

- Obtain approval

STEP 6 - Finalize and Archive

--------------------------------------

Complete as-built submittal:

- Prepare final format (paper/digital)

- Submit required copies

- Obtain receipt/acceptance

- Archive in project files

- Retain field markups for reference

============================================================

COMPLIANCE & REVIEW

============================================================

| KPI | Target |

|-----|--------|

| Field markups maintained throughout project | 100% |

| All changes documented | 100% |

| As-builts submitted on time | 100% |

| Owner acceptance obtained | 100% |

============================================================

APPENDIX

============================================================

- As-Built Markup Standards

- As-Built Legend/Symbols

- Submittal Format Requirements

- Review Checklist

============================================================

REVISION HISTORY

============================================================

Formerly: SOP 9.41.565 - Manage As-Built Drawings

Revision: 2.0 | Effective Date: 2025-10-10

Owner: Project Management | Approver: Executive Committee