## Coverage Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category
9.41.005 – Team Selection | PM defines staffing needs | Project Manager | Sec. 9.5 PM (manpower plan) | ✔ Covered | No change required. | Team selection and turnover
9.41.005 – Team Selection | GS assigns field supervisors | General Superintendent | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover
9.41.005 – Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover
9.41.005 – Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover
9.41.010 – Project Turnover Meeting | Conduct estimator-led turnover meeting | Estimator | Sec. 9.7 Estimating (turnover participation) | ✔ Covered | No change required. | Team selection and turnover
9.41.010 – Project Turnover Meeting | Participate in turnover meeting | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Sec. 9.5 PM (turnover), Sec. 9.13 BM, Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Team selection and turnover
9.41.010 – Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover
9.41.015 – Review Contract for High-Risk Clauses | Review contract for unfavorable clauses | Project Manager | Sec. 9.5 PM (contract review) | ✔ Covered | No change required. | Scope and contract review
9.41.015 – Review Contract for High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review
9.41.020 – PM Reviews Plans, Specs & Schedule | Review drawings, specs, and schedules | Project Manager | Sec. 9.5 PM (scope & schedule review) | ✔ Covered | No change required. | Scope and contract review
9.41.020 – PM Reviews Plans, Specs & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review
9.41.020 – PM Reviews Plans, Specs & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review
9.41.025 – FS Reviews Plans, Specs & Schedule | Review drawings/specs/schedules for constructability | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Scope and contract review
9.41.025 – FS Reviews Plans, Specs & Schedule | Submit findings to PM & GS | Field Supervisor | Sec. 9.3 Field Leadership (reporting to PM/GS) | ✔ Covered | No change required. | Scope and contract review
9.41.025 – FS Reviews Plans, Specs & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review
9.41.030 – Create Issue List & RFI | Identify constructability/scope issues | Field Supervisor | Sec. 9.3 Field Leadership (report issues) | ✔ Covered | No change required. | Scope and contract review
9.41.030 – Create Issue List & RFI | Maintain RFI log | Project Manager | Sec. 9.5 PM (document scope changes) | ✔ Covered | No change required. | Scope and contract review
9.41.030 – Create Issue List & RFI | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review
9.41.035 – Conduct Site Visit | Perform site walk & complete checklist | Field Supervisor | Sec. 9.3 Field Leadership (site reporting) | ✔ Covered | No change required. | Scope and contract review
9.41.035 – Conduct Site Visit | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (site visits, job planning) | ⚠ Gap – PEP integration not explicit | Add PEP reference in Sec. 9.5. | Scope and contract review
9.41.035 – Conduct Site Visit | Identify site-specific hazards | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ✔ Covered | No change required. | Scope and contract review
9.41.035 – Conduct Site Visit | Review manpower/logistics implications | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Scope and contract review
9.41.040 – Compare Est. vs. Planned | Provide bid documentation | Estimator | Sec. 9.7 Estimating (bid package review) | ✔ Covered | No change required. | Budget preparation
9.41.040 – Compare Est. vs. Planned | Compare assumptions vs. execution plan | Project Manager | Sec. 9.5 PM (job plan updates) | ✔ Covered | No change required. | Budget preparation
9.41.040 – Compare Est. vs. Planned | Validate manpower implications | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation
9.41.040 – Compare Est. vs. Planned | Validate budget alignment | Branch Manager | Sec. 9.6 Branch Mgmt (budget alignment) | ✔ Covered | No change required. | Budget preparation
9.41.045 – VE & Prefab | Facilitate identification of VE/prefab opportunities | Project Manager | Sec. 9.5 PM (prefabrication planning) | ✔ Covered | No change required. | Buyout process
9.41.045 – VE & Prefab | Develop prefab strategy sheet | Prefabrication Lead | Sec. 7.3.7 Prefab JD (prefab strategy) | ✔ Covered | No change required. | Buyout process
9.41.045 – VE & Prefab | Validate constructability/feasibility | Field Supervisor | Sec. 9.3 Field Leadership (field feasibility) | ✔ Covered | No change required. | Buyout process
9.41.045 – VE & Prefab | Confirm VE proposals align with budget | Estimator | Sec. 9.7 Estimating (VE options) | ✔ Covered | No change required. | Buyout process
9.41.045 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process
9.41.050 – Construction Takeoff | Generate detailed material/labor quantities | Project Manager | Sec. 9.5 PM (buyout planning) | ✔ Covered | No change required. | Buyout process
9.41.050 – Construction Takeoff | Provide bid takeoff for reference | Estimator | Sec. 9.7 Estimating (bid takeoff) | ✔ Covered | No change required. | Buyout process
9.41.050 – Construction Takeoff | Review constructability & logistics accuracy | Field Supervisor | Sec. 9.3 Field Leadership (constructability review) | ✔ Covered | No change required. | Buyout process
9.41.050 – Construction Takeoff | Use results for vendor negotiations & procurement | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ✔ Covered | No change required. | Buyout process
9.41.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process
9.41.055 – Procurement of Large Feeder Wire | Prepare BOM & conduit/wire pull schedule | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Buyout process
9.41.055 – Procurement of Large Feeder Wire | Validate lengths and reel assignments | Foreman / Field Supervisor | Sec. 9.3 Field Leadership (materials validation) | ✔ Covered | No change required. | Buyout process
9.41.055 – Procurement of Large Feeder Wire | Confirm manpower/logistics feasibility | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Buyout process
9.41.055 – Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process
9.41.060 – Material Handling Plan | Develop logistics plan for delivery/staging | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Material handling plan
9.41.060 – Material Handling Plan | Align with procurement & project schedule | Project Manager | Sec. 9.5 PM (logistics, procurement alignment) | ✔ Covered | No change required. | Material handling plan
9.41.060 – Material Handling Plan | Review safety compliance of handling plan | Safety Coordinator | Sec. 7.2.6 JD (safety review) | ✔ Covered | No change required. | Material handling plan
9.41.065 – Develop Labor Budget | Develop detailed labor forecast | Project Manager | Sec. 9.5 PM (labor planning) | ✔ Covered | No change required. | Budget preparation
9.41.065 – Develop Labor Budget | Validate manpower feasibility | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation
9.41.065 – Develop Labor Budget | Provide labor assumptions from bid | Estimator | Sec. 9.7 Estimating (labor assumptions) | ✔ Covered | No change required. | Budget preparation
9.41.065 – Develop Labor Budget | Approve labor budget | Branch Manager | Sec. 9.6 Branch Mgmt (budget oversight) | ✔ Covered | No change required. | Budget preparation
9.41.070 – Layout & Sequencing Plan | Develop sequencing plan & integrate into PEP | Project Manager | Sec. 9.5 PM (planning, scheduling) | ✔ Covered | No change required. | Layout and sequencing plan
9.41.070 – Layout & Sequencing Plan | Review constructability & sequencing feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Layout and sequencing plan
9.41.070 – Layout & Sequencing Plan | Confirm manpower allocations & critical path | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Layout and sequencing plan
9.41.070 – Layout & Sequencing Plan | Identify safety risks in layout/sequencing | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Layout and sequencing plan
9.41.075 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM (schedule ownership) | ✔ Covered | No change required. | Schedule development
9.41.075 – Develop Project Schedule | Validate manpower phasing feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Schedule development
9.41.075 – Develop Project Schedule | Confirm long-lead procurement dates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Schedule development
9.41.075 – Develop Project Schedule | Approve baseline schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Schedule development
9.41.080 – Tracking & Control Systems | Establish tracking templates/logs | Project Manager | Sec. 9.5 PM (reporting systems) | ✔ Covered | No change required. | Tracking and control
9.41.080 – Tracking & Control Systems | Report daily manpower/progress | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Tracking and control
9.41.080 – Tracking & Control Systems | Maintain procurement log | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Tracking and control
9.41.080 – Tracking & Control Systems | Submit safety inspection reports | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Tracking and control
9.41.080 – Tracking & Control Systems | Review weekly reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Tracking and control
9.41.085 – Kickoff Meeting | Organize & lead kickoff | Project Manager | Sec. 9.5 PM (turnover/kickoff) | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.085 – Kickoff Meeting | Confirm manpower/sequence feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.085 – Kickoff Meeting | Review site logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.085 – Kickoff Meeting | Provide procurement/delivery updates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.085 – Kickoff Meeting | Present safety plan | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.085 – Kickoff Meeting | Provide branch-level oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Construction execution kickoff meeting
9.41.090 – Office Trailer | Secure trailer & utilities setup | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.41.090 – Office Trailer | Setup furniture & documentation systems | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Mobilization
9.41.090 – Office Trailer | Confirm location/logistics feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Mobilization
9.41.090 – Office Trailer | Ensure phone/internet operational | IT/Communications | Sec. 7.4 Business Admin JD (IT) | ✔ Covered | No change required. | Mobilization
9.41.095 – Storage Trailer | Approve trailer placement | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.41.095 – Storage Trailer | Setup shelving & inventory control | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.095 – Storage Trailer | Verify compliance with fire/access standards | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.100 – Fencing & Access Control | Approve fencing & access plan | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization
9.41.100 – Fencing & Access Control | Oversee fence/gate installation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.100 – Fencing & Access Control | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.100 – Fencing & Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization
9.41.105 – Setup Temporary Power | Coordinate power requirements with utility/owner | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.41.105 – Setup Temporary Power | Oversee installation & verify distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.105 – Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization
9.41.105 – Setup Temporary Power | Verify OSHA/NEC compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.110 – Setup Temporary Water | Coordinate utility connection | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.41.110 – Setup Temporary Water | Oversee installation/distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.110 – Setup Temporary Water | Verify safety/environmental compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.115 – Setup Sanitary Facilities | Contract vendors for sanitary facilities | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization
9.41.115 – Setup Sanitary Facilities | Determine placement & logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.115 – Setup Sanitary Facilities | Maintain inspection log | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.120 – Setup Temporary Lighting | Approve lighting plan & budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.120 – Setup Temporary Lighting | Oversee installation & verify coverage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.120 – Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization
9.41.120 – Setup Temporary Lighting | Inspect OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.125 – Setup Signage | Determine signage requirements | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.125 – Setup Signage | Install signage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.125 – Setup Signage | Ensure OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.130 – Setup Security | Approve security plan & vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.130 – Setup Security | Implement physical security | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.130 – Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization
9.41.130 – Setup Security | Ensure plan aligns with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.135 – Setup Laydown Area | Approve laydown area location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.135 – Setup Laydown Area | Setup & manage laydown area | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.135 – Setup Laydown Area | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.140 – Setup Equipment Staging | Approve staging location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.140 – Setup Equipment Staging | Direct equipment setup | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.140 – Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization
9.41.140 – Setup Equipment Staging | Verify OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.145 – Setup Parking | Approve parking plan | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization
9.41.145 – Setup Parking | Establish parking areas | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization
9.41.145 – Setup Parking | Verify traffic safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization
9.41.150 – Coordination Meetings | Schedule & chair coordination meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.41.150 – Coordination Meetings | Provide field updates & issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.41.150 – Coordination Meetings | Record minutes & action items | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Coordination
9.41.150 – Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination
9.41.155 – Subcontractor Meetings | Prepare and distribute subcontractor agenda | Project Manager | Sec. 9.5 PM (coordination) | ✔ Covered | No change required. | Coordination
9.41.155 – Subcontractor Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination
9.41.155 – Subcontractor Meetings | Report logistics needs | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.41.155 – Subcontractor Meetings | Review safety performance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.160 – Client Meetings | Lead client/owner meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.41.160 – Client Meetings | Provide executive oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination
9.41.160 – Client Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination
9.41.165 – Safety Meetings | Prepare/lead safety meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.165 – Safety Meetings | Ensure scheduling and attendance | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.165 – Safety Meetings | Reinforce safety in daily huddles | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.165 – Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management
9.41.170 – Prefab Meetings | Schedule/facilitate prefab meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.41.170 – Prefab Meetings | Provide prefab schedules/deliverables | Prefab Lead | Sec. 7.3.7 Prefab JD | ✔ Covered | No change required. | Coordination
9.41.170 – Prefab Meetings | Validate constructability feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination
9.41.170 – Prefab Meetings | Confirm manpower sequencing | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.41.175 – Quality Meetings | Schedule/facilitate meetings, track actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Quality Control
9.41.175 – Quality Meetings | Report quality issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Quality Control
9.41.175 – Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control
9.41.175 – Quality Meetings | Confirm overlap with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.180 – Commissioning Meetings | Schedule/facilitate commissioning | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination
9.41.180 – Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control
9.41.180 – Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination
9.41.180 – Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control
9.41.185 – Closeout Meetings | Schedule and lead closeout meeting | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Project Closeout
9.41.185 – Closeout Meetings | Verify completion of punch list | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project Closeout
9.41.185 – Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout
9.41.185 – Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout
9.41.190A – Filing Standards | Maintain field-level docs in Procore | Field Foreman | Not in directives | ⚠ Gap | Add field documentation requirement. | Documentation Management
9.41.190A – Filing Standards | Maintain contractual docs in Windows folders | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.41.190A – Filing Standards | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.41.190A – Filing Standards | Audit compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management
9.41.195 – Documentation System | Ensure compliance with filing standards | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.41.195 – Documentation System | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.41.195 – Documentation System | Audit system compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management
9.41.200 – Submittals | Prepare submittal log & ensure timely submissions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.41.200 – Submittals | Coordinate vendor submittals | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Documentation Management
9.41.200 – Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management
9.41.300 – A/E Communications | Issue RFIs and receive design clarifications | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication
9.41.300 – A/E Communications | Identify conflicts and escalate | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication
9.41.300 – A/E Communications | Log A/E communications | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.41.310 – GC Communications | Lead communications with GC | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication
9.41.310 – GC Communications | Escalate field directives | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication
9.41.310 – GC Communications | Log GC correspondence | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management
9.41.315 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.320 – Update Project Schedule | Update project schedule with progress | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.320 – Update Project Schedule | Provide weekly progress | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling
9.41.325 – Monitor Schedule Performance | Prepare performance reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.325 – Monitor Schedule Performance | Verify progress in field | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.41.330 – Recovery Plans | Develop recovery strategies | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.330 – Recovery Plans | Approve recovery plans | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control
9.41.335 – Lookahead Schedules | Prepare weekly lookaheads | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.335 – Lookahead Schedules | Confirm sequencing | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.41.335 – Lookahead Schedules | Use lookahead for crew planning | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.41.340 – Resource-Loaded Schedules | Integrate resources into schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.340 – Resource-Loaded Schedules | Confirm resource availability | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management
9.41.340 – Resource-Loaded Schedules | Review resource forecasts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Materials Management
9.41.345 – Schedule Review Meetings | Prepare agenda and lead meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.345 – Schedule Review Meetings | Provide field updates | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling
9.41.345 – Schedule Review Meetings | Confirm crew availability | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.41.345 – Schedule Review Meetings | Approve mitigation strategies | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination
9.41.205 – RFIs | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control
9.41.210 – Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication
9.41.215 – Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management
9.41.220 – Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management
9.41.225 – Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management
9.41.230 – Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication
9.41.235 – Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management
9.41.240 – Inspections | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control
9.41.245 – Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout
9.41.315 – Develop Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling
9.41.330 – Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling
9.41.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management
9.41.345 – Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination
9.41.350 – Schedule Change Requests | Review schedule change requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling
9.41.350 – Schedule Change Requests | Approve/reject requests | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scheduling
9.41.350 – Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management
9.41.355 – Project Scope | Define and control project scope | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.355 – Project Scope | Approve scope adjustments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.41.360 – Change Orders | Prepare CO documentation | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.360 – Change Orders | Review CO costs | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.41.360 – Change Orders | Approve COs before submission | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.41.360 – Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management
9.41.365 – PCOs | Identify and document potential COs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.365 – PCOs | Provide cost backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.41.370 – Owner Directives | Implement and log directives | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.370 – Owner Directives | Review directives for cost/schedule impact | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.41.375 – Scope Clarifications | Identify and clarify scope gaps | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.375 – Scope Clarifications | Provide bid data for clarifications | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Scope & Change Control
9.41.380 – Backcharges | Approve backcharges | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.380 – Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing
9.41.385 – Force Account Work | Authorize force account work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.385 – Force Account Work | Track labor/equipment/materials | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management
9.41.385 – Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing
9.41.385 – Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management
9.41.390 – Claims | Identify/prepare claims | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control
9.41.390 – Claims | Provide cost/time analysis | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.41.390 – Claims | Approve claims | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control
9.41.390 – Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control
9.41.390 – Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management
9.41.395 – Project Budget | Prepare project budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.395 – Project Budget | Provide bid/estimate backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing
9.41.395 – Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing
9.41.395 – Project Budget | Approve budget | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.400 – Monitor Project Costs | Monitor project costs vs. budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.400 – Monitor Project Costs | Validate cost reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.400 – Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing
9.41.405 – Manage Cost Forecasts | Prepare updated cost forecasts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.405 – Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing
9.41.410 – Manage Cost Codes | Assign and maintain cost codes | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.410 – Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing
9.41.415 – Manage Committed Costs | Review purchase orders & contracts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Materials Management
9.41.415 – Manage Committed Costs | Approve commitments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.415 – Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing
9.41.420 – Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing
9.41.420 – Manage Actual Costs | Validate costs against budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.425 – Manage Job Cost Reports | Prepare monthly job cost reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.425 – Manage Job Cost Reports | Validate reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.425 – Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing
9.41.430 – Manage Profit Projections | Prepare profit projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.430 – Manage Profit Projections | Review projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.430 – Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing
9.41.435 – Manage Cost-to-Complete | Update cost-to-complete projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.435 – Manage Cost-to-Complete | Validate projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.435 – Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing
9.41.440 – Prepare Billing Schedule | Prepare billing schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.440 – Prepare Billing Schedule | Review billing schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.440 – Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication
9.41.445 – Monthly Pay Applications | Prepare pay application package | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.445 – Monthly Pay Applications | Review and approve pay apps | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.445 – Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing
9.41.445 – Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication
9.41.450 – Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing
9.41.450 – Track Accounts Receivable | Review AR status and escalate non-payment | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.450 – Track Accounts Receivable | Approve escalation actions for delinquent accounts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.455 – Manage Lien Waivers | Collect executed lien waivers from subs/vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management
9.41.455 – Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management
9.41.455 – Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management
9.41.455 – Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management
9.41.460 – Manage Retainage | Track retainage withheld and prepare release requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.460 – Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing
9.41.460 – Manage Retainage | Approve final retainage release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.465 – Manage Final Invoicing | Prepare final invoice and ensure supporting docs complete | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing
9.41.465 – Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing
9.41.465 – Manage Final Invoicing | Approve final invoice prior to release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing
9.41.465 – Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing
9.41.470 – Site-Specific Safety Plan | Draft and maintain SSSP | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.470 – Site-Specific Safety Plan | Review and approve SSSP | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.470 – Site-Specific Safety Plan | Audit SSSP for compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.41.470 – Site-Specific Safety Plan | Implement SSSP in field operations | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.475 – Safety Orientation | Conduct orientation sessions and maintain records | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.475 – Safety Orientation | Ensure all personnel complete orientation before work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.475 – Safety Orientation | Verify crew participation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.480 – Safety Inspections | Conduct inspections and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.480 – Safety Inspections | Correct hazards identified during inspections | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.480 – Safety Inspections | Review reports and ensure corrective action | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.480 – Safety Inspections | Audit safety inspection process | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.41.485 – Safety Meetings | Prepare agenda and conduct meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.485 – Safety Meetings | Ensure meetings are held as scheduled | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.485 – Safety Meetings | Reinforce safety policies with crews | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.490 – Report Safety Incidents | Complete official incident report and submit | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.490 – Report Safety Incidents | Document initial details and notify PM/Safety | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.490 – Report Safety Incidents | Review and escalate incidents as required | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.490 – Report Safety Incidents | Submit report to Branch Manager within 24 hrs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.495 – Investigate Accidents | Lead investigation and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management
9.41.495 – Investigate Accidents | Support investigation and implement corrective actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management
9.41.495 – Investigate Accidents | Provide incident details and ensure crew cooperation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management
9.41.495 – Investigate Accidents | Review investigation and approve corrective measures | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management
9.41.495 – Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management

## RACI Matrix
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | RACI
9.41.005 – Team Selection | PM defines staffing needs | Project Manager | Sec. 9.5 PM (manpower plan) | ✔ Covered | No change required. | Team selection and turnover | A
9.41.005 – Team Selection | GS assigns field supervisors | General Superintendent | Sec. 9.4 GS (manpower assignment) | ✔ Covered | No change required. | Team selection and turnover | I
9.41.005 – Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover | A
9.41.005 – Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover | R
9.41.010 – Project Turnover Meeting | Conduct estimator-led turnover meeting | Estimator | Sec. 9.7 Estimating (turnover participation) | ✔ Covered | No change required. | Team selection and turnover | C
9.41.010 – Project Turnover Meeting | Participate in turnover meeting | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Sec. 9.5 PM (turnover), Sec. 9.13 BM, Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Team selection and turnover | I
9.41.010 – Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover | A
9.41.015 – Review Contract for High-Risk Clauses | Review contract for unfavorable clauses | Project Manager | Sec. 9.5 PM (contract review) | ✔ Covered | No change required. | Scope and contract review | A
9.41.015 – Review Contract for High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review | A
9.41.020 – PM Reviews Plans, Specs & Schedule | Review drawings, specs, and schedules | Project Manager | Sec. 9.5 PM (scope & schedule review) | ✔ Covered | No change required. | Scope and contract review | A
9.41.020 – PM Reviews Plans, Specs & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review | A
9.41.020 – PM Reviews Plans, Specs & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review | A
9.41.025 – FS Reviews Plans, Specs & Schedule | Review drawings/specs/schedules for constructability | Field Supervisor | Sec. 9.3 Field Leadership (pre-planning) | ✔ Covered | No change required. | Scope and contract review | R
9.41.025 – FS Reviews Plans, Specs & Schedule | Submit findings to PM & GS | Field Supervisor | Sec. 9.3 Field Leadership (reporting to PM/GS) | ✔ Covered | No change required. | Scope and contract review | R
9.41.025 – FS Reviews Plans, Specs & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review | A
9.41.030 – Create Issue List & RFI | Identify constructability/scope issues | Field Supervisor | Sec. 9.3 Field Leadership (report issues) | ✔ Covered | No change required. | Scope and contract review | R
9.41.030 – Create Issue List & RFI | Maintain RFI log | Project Manager | Sec. 9.5 PM (document scope changes) | ✔ Covered | No change required. | Scope and contract review | A
9.41.030 – Create Issue List & RFI | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review | I
9.41.035 – Conduct Site Visit | Perform site walk & complete checklist | Field Supervisor | Sec. 9.3 Field Leadership (site reporting) | ✔ Covered | No change required. | Scope and contract review | R
9.41.035 – Conduct Site Visit | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (site visits, job planning) | ⚠ Gap – PEP integration not explicit | Add PEP reference in Sec. 9.5. | Scope and contract review | A
9.41.035 – Conduct Site Visit | Identify site-specific hazards | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ✔ Covered | No change required. | Scope and contract review | R
9.41.035 – Conduct Site Visit | Review manpower/logistics implications | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Scope and contract review | I
9.41.040 – Compare Est. vs. Planned | Provide bid documentation | Estimator | Sec. 9.7 Estimating (bid package review) | ✔ Covered | No change required. | Budget preparation | C
9.41.040 – Compare Est. vs. Planned | Compare assumptions vs. execution plan | Project Manager | Sec. 9.5 PM (job plan updates) | ✔ Covered | No change required. | Budget preparation | A
9.41.040 – Compare Est. vs. Planned | Validate manpower implications | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation | I
9.41.040 – Compare Est. vs. Planned | Validate budget alignment | Branch Manager | Sec. 9.6 Branch Mgmt (budget alignment) | ✔ Covered | No change required. | Budget preparation | A
9.41.045 – VE & Prefab | Facilitate identification of VE/prefab opportunities | Project Manager | Sec. 9.5 PM (prefabrication planning) | ✔ Covered | No change required. | Buyout process | A
9.41.045 – VE & Prefab | Develop prefab strategy sheet | Prefabrication Lead | Sec. 7.3.7 Prefab JD (prefab strategy) | ✔ Covered | No change required. | Buyout process | I
9.41.045 – VE & Prefab | Validate constructability/feasibility | Field Supervisor | Sec. 9.3 Field Leadership (field feasibility) | ✔ Covered | No change required. | Buyout process | R
9.41.045 – VE & Prefab | Confirm VE proposals align with budget | Estimator | Sec. 9.7 Estimating (VE options) | ✔ Covered | No change required. | Buyout process | C
9.41.045 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process | A
9.41.050 – Construction Takeoff | Generate detailed material/labor quantities | Project Manager | Sec. 9.5 PM (buyout planning) | ✔ Covered | No change required. | Buyout process | A
9.41.050 – Construction Takeoff | Provide bid takeoff for reference | Estimator | Sec. 9.7 Estimating (bid takeoff) | ✔ Covered | No change required. | Buyout process | C
9.41.050 – Construction Takeoff | Review constructability & logistics accuracy | Field Supervisor | Sec. 9.3 Field Leadership (constructability review) | ✔ Covered | No change required. | Buyout process | R
9.41.050 – Construction Takeoff | Use results for vendor negotiations & procurement | Purchasing | Sec. 9.16 Purchasing (pre-buyout procurement) | ✔ Covered | No change required. | Buyout process | C
9.41.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process | A
9.41.055 – Procurement of Large Feeder Wire | Prepare BOM & conduit/wire pull schedule | Project Manager | Sec. 9.5 PM (procurement planning); Sec. 9.16 Purchasing | ✔ Covered | No change required. | Buyout process | A
9.41.055 – Procurement of Large Feeder Wire | Validate lengths and reel assignments | Foreman / Field Supervisor | Sec. 9.3 Field Leadership (materials validation) | ✔ Covered | No change required. | Buyout process | R
9.41.055 – Procurement of Large Feeder Wire | Confirm manpower/logistics feasibility | General Superintendent | Sec. 9.4 GS (manpower coordination) | ✔ Covered | No change required. | Buyout process | I
9.41.055 – Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process | A
9.41.060 – Material Handling Plan | Develop logistics plan for delivery/staging | Field Supervisor | Sec. 9.3 Field Leadership (staging/logistics) | ✔ Covered | No change required. | Material handling plan | R
9.41.060 – Material Handling Plan | Align with procurement & project schedule | Project Manager | Sec. 9.5 PM (logistics, procurement alignment) | ✔ Covered | No change required. | Material handling plan | A
9.41.060 – Material Handling Plan | Review safety compliance of handling plan | Safety Coordinator | Sec. 7.2.6 JD (safety review) | ✔ Covered | No change required. | Material handling plan | R
9.41.065 – Develop Labor Budget | Develop detailed labor forecast | Project Manager | Sec. 9.5 PM (labor planning) | ✔ Covered | No change required. | Budget preparation | A
9.41.065 – Develop Labor Budget | Validate manpower feasibility | General Superintendent | Sec. 9.4 GS (workforce oversight) | ✔ Covered | No change required. | Budget preparation | I
9.41.065 – Develop Labor Budget | Provide labor assumptions from bid | Estimator | Sec. 9.7 Estimating (labor assumptions) | ✔ Covered | No change required. | Budget preparation | C
9.41.065 – Develop Labor Budget | Approve labor budget | Branch Manager | Sec. 9.6 Branch Mgmt (budget oversight) | ✔ Covered | No change required. | Budget preparation | A
9.41.070 – Layout & Sequencing Plan | Develop sequencing plan & integrate into PEP | Project Manager | Sec. 9.5 PM (planning, scheduling) | ✔ Covered | No change required. | Layout and sequencing plan | A
9.41.070 – Layout & Sequencing Plan | Review constructability & sequencing feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Layout and sequencing plan | R
9.41.070 – Layout & Sequencing Plan | Confirm manpower allocations & critical path | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Layout and sequencing plan | I
9.41.070 – Layout & Sequencing Plan | Identify safety risks in layout/sequencing | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Layout and sequencing plan | R
9.41.075 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM (schedule ownership) | ✔ Covered | No change required. | Schedule development | A
9.41.075 – Develop Project Schedule | Validate manpower phasing feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Schedule development | I
9.41.075 – Develop Project Schedule | Confirm long-lead procurement dates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Schedule development | C
9.41.075 – Develop Project Schedule | Approve baseline schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Schedule development | A
9.41.080 – Tracking & Control Systems | Establish tracking templates/logs | Project Manager | Sec. 9.5 PM (reporting systems) | ✔ Covered | No change required. | Tracking and control | A
9.41.080 – Tracking & Control Systems | Report daily manpower/progress | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Tracking and control | R
9.41.080 – Tracking & Control Systems | Maintain procurement log | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Tracking and control | C
9.41.080 – Tracking & Control Systems | Submit safety inspection reports | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Tracking and control | R
9.41.080 – Tracking & Control Systems | Review weekly reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Tracking and control | A
9.41.085 – Kickoff Meeting | Organize & lead kickoff | Project Manager | Sec. 9.5 PM (turnover/kickoff) | ✔ Covered | No change required. | Construction execution kickoff meeting | A
9.41.085 – Kickoff Meeting | Confirm manpower/sequence feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Construction execution kickoff meeting | I
9.41.085 – Kickoff Meeting | Review site logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Construction execution kickoff meeting | R
9.41.085 – Kickoff Meeting | Provide procurement/delivery updates | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Construction execution kickoff meeting | C
9.41.085 – Kickoff Meeting | Present safety plan | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Construction execution kickoff meeting | R
9.41.085 – Kickoff Meeting | Provide branch-level oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Construction execution kickoff meeting | A
9.41.090 – Office Trailer | Secure trailer & utilities setup | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.090 – Office Trailer | Setup furniture & documentation systems | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Mobilization | R
9.41.090 – Office Trailer | Confirm location/logistics feasibility | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Mobilization | I
9.41.090 – Office Trailer | Ensure phone/internet operational | IT/Communications | Sec. 7.4 Business Admin JD (IT) | ✔ Covered | No change required. | Mobilization | I
9.41.095 – Storage Trailer | Approve trailer placement | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.095 – Storage Trailer | Setup shelving & inventory control | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.095 – Storage Trailer | Verify compliance with fire/access standards | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.100 – Fencing & Access Control | Approve fencing & access plan | Project Manager | Sec. 9.5 PM (site mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.100 – Fencing & Access Control | Oversee fence/gate installation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.100 – Fencing & Access Control | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.100 – Fencing & Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization | I
9.41.105 – Setup Temporary Power | Coordinate power requirements with utility/owner | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.105 – Setup Temporary Power | Oversee installation & verify distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.105 – Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | R
9.41.105 – Setup Temporary Power | Verify OSHA/NEC compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.110 – Setup Temporary Water | Coordinate utility connection | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.110 – Setup Temporary Water | Oversee installation/distribution | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.110 – Setup Temporary Water | Verify safety/environmental compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.115 – Setup Sanitary Facilities | Contract vendors for sanitary facilities | Project Manager | Sec. 9.5 PM (mobilization) | ✔ Covered | No change required. | Mobilization | A
9.41.115 – Setup Sanitary Facilities | Determine placement & logistics | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.115 – Setup Sanitary Facilities | Maintain inspection log | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.120 – Setup Temporary Lighting | Approve lighting plan & budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.120 – Setup Temporary Lighting | Oversee installation & verify coverage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.120 – Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | R
9.41.120 – Setup Temporary Lighting | Inspect OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.125 – Setup Signage | Determine signage requirements | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.125 – Setup Signage | Install signage | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.125 – Setup Signage | Ensure OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.130 – Setup Security | Approve security plan & vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.130 – Setup Security | Implement physical security | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.130 – Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization | I
9.41.130 – Setup Security | Ensure plan aligns with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.135 – Setup Laydown Area | Approve laydown area location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.135 – Setup Laydown Area | Setup & manage laydown area | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.135 – Setup Laydown Area | Verify safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.140 – Setup Equipment Staging | Approve staging location | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.140 – Setup Equipment Staging | Direct equipment setup | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.140 – Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization | I
9.41.140 – Setup Equipment Staging | Verify OSHA compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.145 – Setup Parking | Approve parking plan | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Mobilization | A
9.41.145 – Setup Parking | Establish parking areas | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Mobilization | R
9.41.145 – Setup Parking | Verify traffic safety compliance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Mobilization | R
9.41.150 – Coordination Meetings | Schedule & chair coordination meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.41.150 – Coordination Meetings | Provide field updates & issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.41.150 – Coordination Meetings | Record minutes & action items | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Coordination | R
9.41.150 – Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination | I
9.41.155 – Subcontractor Meetings | Prepare and distribute subcontractor agenda | Project Manager | Sec. 9.5 PM (coordination) | ✔ Covered | No change required. | Coordination | A
9.41.155 – Subcontractor Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination | R
9.41.155 – Subcontractor Meetings | Report logistics needs | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.41.155 – Subcontractor Meetings | Review safety performance | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.160 – Client Meetings | Lead client/owner meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.41.160 – Client Meetings | Provide executive oversight | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination | A
9.41.160 – Client Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination | C
9.41.165 – Safety Meetings | Prepare/lead safety meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.165 – Safety Meetings | Ensure scheduling and attendance | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.165 – Safety Meetings | Reinforce safety in daily huddles | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.165 – Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management | I
9.41.170 – Prefab Meetings | Schedule/facilitate prefab meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.41.170 – Prefab Meetings | Provide prefab schedules/deliverables | Prefab Lead | Sec. 7.3.7 Prefab JD | ✔ Covered | No change required. | Coordination | I
9.41.170 – Prefab Meetings | Validate constructability feasibility | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Coordination | R
9.41.170 – Prefab Meetings | Confirm manpower sequencing | General Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.41.175 – Quality Meetings | Schedule/facilitate meetings, track actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Quality Control | A
9.41.175 – Quality Meetings | Report quality issues | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Quality Control | R
9.41.175 – Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control | I
9.41.175 – Quality Meetings | Confirm overlap with safety | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.180 – Commissioning Meetings | Schedule/facilitate commissioning | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Coordination | A
9.41.180 – Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control | I
9.41.180 – Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination | R
9.41.180 – Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control | I
9.41.185 – Closeout Meetings | Schedule and lead closeout meeting | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Project Closeout | A
9.41.185 – Closeout Meetings | Verify completion of punch list | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Project Closeout | R
9.41.185 – Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout | R
9.41.185 – Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout | C
9.41.190A – Filing Standards | Maintain field-level docs in Procore | Field Foreman | Not in directives | ⚠ Gap | Add field documentation requirement. | Documentation Management | R
9.41.190A – Filing Standards | Maintain contractual docs in Windows folders | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.41.190A – Filing Standards | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.41.190A – Filing Standards | Audit compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management | A
9.41.195 – Documentation System | Ensure compliance with filing standards | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.41.195 – Documentation System | Organize folders & verify consistency | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.41.195 – Documentation System | Audit system compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Documentation Management | A
9.41.200 – Submittals | Prepare submittal log & ensure timely submissions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.41.200 – Submittals | Coordinate vendor submittals | Purchasing | Sec. 9.16 Purchasing | ✔ Covered | No change required. | Documentation Management | C
9.41.200 – Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management | R
9.41.300 – A/E Communications | Issue RFIs and receive design clarifications | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication | A
9.41.300 – A/E Communications | Identify conflicts and escalate | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication | R
9.41.300 – A/E Communications | Log A/E communications | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.41.310 – GC Communications | Lead communications with GC | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Communication | A
9.41.310 – GC Communications | Escalate field directives | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Communication | R
9.41.310 – GC Communications | Log GC correspondence | Site Administrator | Sec. 7.4 Business Admin JD | ✔ Covered | No change required. | Documentation Management | R
9.41.315 – Develop Project Schedule | Develop baseline schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.320 – Update Project Schedule | Update project schedule with progress | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.320 – Update Project Schedule | Provide weekly progress | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling | I
9.41.325 – Monitor Schedule Performance | Prepare performance reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.325 – Monitor Schedule Performance | Verify progress in field | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.41.330 – Recovery Plans | Develop recovery strategies | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.330 – Recovery Plans | Approve recovery plans | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control | A
9.41.335 – Lookahead Schedules | Prepare weekly lookaheads | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.335 – Lookahead Schedules | Confirm sequencing | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.41.335 – Lookahead Schedules | Use lookahead for crew planning | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.41.340 – Resource-Loaded Schedules | Integrate resources into schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.340 – Resource-Loaded Schedules | Confirm resource availability | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Labor Management | I
9.41.340 – Resource-Loaded Schedules | Review resource forecasts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Materials Management | A
9.41.345 – Schedule Review Meetings | Prepare agenda and lead meetings | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.345 – Schedule Review Meetings | Provide field updates | Superintendent | Sec. 9.4 GS | ✔ Covered | No change required. | Scheduling | I
9.41.345 – Schedule Review Meetings | Confirm crew availability | Field Foreman | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.41.345 – Schedule Review Meetings | Approve mitigation strategies | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Coordination | A
9.41.205 – RFIs | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control | R
9.41.210 – Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication | R
9.41.215 – Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management | R
9.41.220 – Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management | R
9.41.225 – Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management | R
9.41.230 – Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication | R
9.41.235 – Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management | I
9.41.240 – Inspections | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control | R
9.41.245 – Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout | R
9.41.315 – Develop Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling | I
9.41.330 – Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling | I
9.41.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management | R
9.41.345 – Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination | I
9.41.350 – Schedule Change Requests | Review schedule change requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scheduling | A
9.41.350 – Schedule Change Requests | Approve/reject requests | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scheduling | A
9.41.350 – Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management | R
9.41.355 – Project Scope | Define and control project scope | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.355 – Project Scope | Approve scope adjustments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.41.360 – Change Orders | Prepare CO documentation | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.360 – Change Orders | Review CO costs | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.41.360 – Change Orders | Approve COs before submission | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.41.360 – Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management | R
9.41.365 – PCOs | Identify and document potential COs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.365 – PCOs | Provide cost backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.41.370 – Owner Directives | Implement and log directives | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.370 – Owner Directives | Review directives for cost/schedule impact | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.41.375 – Scope Clarifications | Identify and clarify scope gaps | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.375 – Scope Clarifications | Provide bid data for clarifications | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Scope & Change Control | C
9.41.380 – Backcharges | Approve backcharges | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.380 – Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing | R
9.41.385 – Force Account Work | Authorize force account work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.385 – Force Account Work | Track labor/equipment/materials | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Labor Management | R
9.41.385 – Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing | R
9.41.385 – Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management | R
9.41.390 – Claims | Identify/prepare claims | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Scope & Change Control | A
9.41.390 – Claims | Provide cost/time analysis | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.41.390 – Claims | Approve claims | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Scope & Change Control | A
9.41.390 – Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control | C
9.41.390 – Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management | R
9.41.395 – Project Budget | Prepare project budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.395 – Project Budget | Provide bid/estimate backup | Estimator | Sec. 9.7 Estimating | ✔ Covered | No change required. | Cost Control & Billing | C
9.41.395 – Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing | R
9.41.395 – Project Budget | Approve budget | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.400 – Monitor Project Costs | Monitor project costs vs. budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.400 – Monitor Project Costs | Validate cost reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.400 – Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing | R
9.41.405 – Manage Cost Forecasts | Prepare updated cost forecasts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.405 – Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing | R
9.41.410 – Manage Cost Codes | Assign and maintain cost codes | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.410 – Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing | R
9.41.415 – Manage Committed Costs | Review purchase orders & contracts | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Materials Management | A
9.41.415 – Manage Committed Costs | Approve commitments | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.415 – Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing | R
9.41.420 – Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing | R
9.41.420 – Manage Actual Costs | Validate costs against budget | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.425 – Manage Job Cost Reports | Prepare monthly job cost reports | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.425 – Manage Job Cost Reports | Validate reports | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.425 – Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing | R
9.41.430 – Manage Profit Projections | Prepare profit projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.430 – Manage Profit Projections | Review projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.430 – Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing | R
9.41.435 – Manage Cost-to-Complete | Update cost-to-complete projections | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.435 – Manage Cost-to-Complete | Validate projections | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.435 – Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing | R
9.41.440 – Prepare Billing Schedule | Prepare billing schedule | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.440 – Prepare Billing Schedule | Review billing schedule | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.440 – Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication | C
9.41.445 – Monthly Pay Applications | Prepare pay application package | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.445 – Monthly Pay Applications | Review and approve pay apps | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.445 – Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing | R
9.41.445 – Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication | C
9.41.450 – Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing | R
9.41.450 – Track Accounts Receivable | Review AR status and escalate non-payment | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.450 – Track Accounts Receivable | Approve escalation actions for delinquent accounts | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.455 – Manage Lien Waivers | Collect executed lien waivers from subs/vendors | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Documentation Management | A
9.41.455 – Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management | R
9.41.455 – Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management | R
9.41.455 – Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management | R
9.41.460 – Manage Retainage | Track retainage withheld and prepare release requests | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.460 – Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing | R
9.41.460 – Manage Retainage | Approve final retainage release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.465 – Manage Final Invoicing | Prepare final invoice and ensure supporting docs complete | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.465 – Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing | R
9.41.465 – Manage Final Invoicing | Approve final invoice prior to release | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Cost Control & Billing | A
9.41.465 – Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing | R
9.41.470 – Site-Specific Safety Plan | Draft and maintain SSSP | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.470 – Site-Specific Safety Plan | Review and approve SSSP | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.470 – Site-Specific Safety Plan | Audit SSSP for compliance | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.41.470 – Site-Specific Safety Plan | Implement SSSP in field operations | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.475 – Safety Orientation | Conduct orientation sessions and maintain records | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.475 – Safety Orientation | Ensure all personnel complete orientation before work | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.475 – Safety Orientation | Verify crew participation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.480 – Safety Inspections | Conduct inspections and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.480 – Safety Inspections | Correct hazards identified during inspections | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.480 – Safety Inspections | Review reports and ensure corrective action | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.480 – Safety Inspections | Audit safety inspection process | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.41.485 – Safety Meetings | Prepare agenda and conduct meetings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.485 – Safety Meetings | Ensure meetings are held as scheduled | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.485 – Safety Meetings | Reinforce safety policies with crews | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.490 – Report Safety Incidents | Complete official incident report and submit | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.490 – Report Safety Incidents | Document initial details and notify PM/Safety | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.490 – Report Safety Incidents | Review and escalate incidents as required | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.490 – Report Safety Incidents | Submit report to Branch Manager within 24 hrs | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.495 – Investigate Accidents | Lead investigation and document findings | Safety Coordinator | Sec. 7.2.6 JD | ✔ Covered | No change required. | Safety Management | R
9.41.495 – Investigate Accidents | Support investigation and implement corrective actions | Project Manager | Sec. 9.5 PM | ✔ Covered | No change required. | Safety Management | A
9.41.495 – Investigate Accidents | Provide incident details and ensure crew cooperation | Field Supervisor | Sec. 9.3 Field Leadership | ✔ Covered | No change required. | Safety Management | R
9.41.495 – Investigate Accidents | Review investigation and approve corrective measures | Branch Manager | Sec. 9.6 Branch Mgmt | ✔ Covered | No change required. | Safety Management | A
9.41.495 – Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management | C

## Redline Recs
SOP Title | SOP Action | Responsible Role | Directive Section | Coverage Status | Gap Closure Recommendation | Category | Redline Proposal
9.41.005 – Team Selection | Branch Manager approves staffing plan | Branch Manager | Sec. 9.6 Branch Mgmt (operations control) | ⚠ Gap – approval not explicit | Add approval language to Sec. 9.6. | Team selection and turnover | Amend Sec. 9.6 Branch Mgmt (operations control) to include: Add approval language to Sec. 9.6.
9.41.005 – Team Selection | Safety Coordinator advises on assignments | Safety Coordinator | Sec. 7.2.6 JD (safety hazard identification) | ⚠ Gap – advisory role not explicit | Add cross-check with Safety Coordinator. | Team selection and turnover | Amend Sec. 7.2.6 JD (safety hazard identification) to include: Add cross-check with Safety Coordinator.
9.41.010 – Project Turnover Meeting | Prepare meeting agenda and minutes | Project Manager | Sec. 9.5 PM (meeting leadership) | ⚠ Gap – agenda/minutes not required | Add to Sec. 9.5: PM must issue minutes within 48 hrs. | Team selection and turnover | Amend Sec. 9.5 PM (meeting leadership) to include: Add to Sec. 9.5: PM must issue minutes within 48 hrs.
9.41.015 – Review Contract for High-Risk Clauses | Escalate risks and prepare mitigation plan | PM, Branch Manager | Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) | ⚠ Gap – mitigation plan not explicit | Add checklist/mitigation step. | Scope and contract review | Amend Sec. 9.14 Contract Mgr (risk oversight), Sec. 9.13 BM (contracts) to include: Add checklist/mitigation step.
9.41.020 – PM Reviews Plans, Specs & Schedule | Complete Scope & Schedule Checklist | Project Manager | Not explicit in directives | ⚠ Gap – checklist requirement | Add checklist reference to Sec. 9.5. | Scope and contract review | Amend Not explicit in directives to include: Add checklist reference to Sec. 9.5.
9.41.020 – PM Reviews Plans, Specs & Schedule | Integrate results into PEP | Project Manager | Sec. 7.3.1 PM JD (planning & PEP) | ⚠ Gap – explicit PEP update not required | Add to PM JD/Directive 9.5. | Scope and contract review | Amend Sec. 7.3.1 PM JD (planning & PEP) to include: Add to PM JD/Directive 9.5.
9.41.025 – FS Reviews Plans, Specs & Schedule | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (job planning) | ⚠ Gap – PEP update not explicit | Add to Sec. 9.5: PM integrates FS findings. | Scope and contract review | Amend Sec. 9.5 PM (job planning) to include: Add to Sec. 9.5: PM integrates FS findings.
9.41.030 – Create Issue List & RFI | Escalate major issues to Branch Manager | PM & GS | Sec. 9.14 Contract Mgr (notice requirements) | ⚠ Gap – escalation step not explicit | Add escalation language to Sec. 9.5. | Scope and contract review | Amend Sec. 9.14 Contract Mgr (notice requirements) to include: Add escalation language to Sec. 9.5.
9.41.035 – Conduct Site Visit | Integrate findings into PEP | Project Manager | Sec. 9.5 PM (site visits, job planning) | ⚠ Gap – PEP integration not explicit | Add PEP reference in Sec. 9.5. | Scope and contract review | Amend Sec. 9.5 PM (site visits, job planning) to include: Add PEP reference in Sec. 9.5.
9.41.045 – VE & Prefab | Record opportunities in VE log | Project Manager | Not explicit in directives | ⚠ Gap – VE log not required | Add VE log requirement in Sec. 9.5. | Buyout process | Amend Not explicit in directives to include: Add VE log requirement in Sec. 9.5.
9.41.050 – Construction Takeoff | Finalize & upload takeoff results | Project Manager | Not explicit in directives | ⚠ Gap – upload requirement | Add takeoff upload requirement to Sec. 9.5. | Buyout process | Amend Not explicit in directives to include: Add takeoff upload requirement to Sec. 9.5.
9.41.055 – Procurement of Large Feeder Wire | Approve submittals before release | Project Manager | Not explicit in directives | ⚠ Gap – submittal approval requirement | Add to Sec. 9.5: PM must verify submittals before release. | Buyout process | Amend Not explicit in directives to include: Add to Sec. 9.5: PM must verify submittals before release.
9.41.100 – Fencing & Access Control | Monitor access control | Security Personnel | Not explicit in directives | ⚠ Gap – role not formalized | Add security monitoring responsibility to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add security monitoring responsibility to Sec. 9.5.
9.41.105 – Setup Temporary Power | Install panels/wiring/grounding | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add subcontractor accountability to Sec. 9.5.
9.41.120 – Setup Temporary Lighting | Install temporary lighting | Electrical Subcontractor | Not explicit in directives | ⚠ Gap – subcontractor role not formalized | Add subcontractor accountability to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add subcontractor accountability to Sec. 9.5.
9.41.130 – Setup Security | Daily monitoring of access points | Security Personnel | Not explicit in directives | ⚠ Gap – security personnel not formalized | Add security responsibilities to Sec. 9.5. | Mobilization | Amend Not explicit in directives to include: Add security responsibilities to Sec. 9.5.
9.41.140 – Setup Equipment Staging | Position equipment safely | Equipment Operators | Not explicit in directives | ⚠ Gap – equipment operator role not formalized | Add operator role into mobilization directive. | Mobilization | Amend Not explicit in directives to include: Add operator role into mobilization directive.
9.41.150 – Coordination Meetings | Provide design clarifications | Design Team / Consultants | Not explicit in directives | ⚠ Gap – design consultant role not formalized | Add consultant clarification role to Sec. 9.5. | Coordination | Amend Not explicit in directives to include: Add consultant clarification role to Sec. 9.5.
9.41.155 – Subcontractor Meetings | Provide progress/manpower updates | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor reporting requirements. | Coordination | Amend Not explicit in directives to include: Add subcontractor reporting requirements.
9.41.160 – Client Meetings | Approve changes/raise concerns | Client/Owner | Not in directives | ⚠ Gap | Owner role external to GSL; clarify interface protocols. | Coordination | Amend Not in directives to include: Owner role external to GSL; clarify interface protocols.
9.41.165 – Safety Meetings | Participate in meetings | All Employees | Not in directives | ⚠ Gap | Include participation expectation in JD handbook. | Safety Management | Amend Not in directives to include: Include participation expectation in JD handbook.
9.41.175 – Quality Meetings | Review quality inspections | Quality Inspector | Not in directives | ⚠ Gap | Add inspector responsibilities into QA directive. | Quality Control | Amend Not in directives to include: Add inspector responsibilities into QA directive.
9.41.180 – Commissioning Meetings | Define testing requirements | Commissioning Agent | Not in directives | ⚠ Gap | Add commissioning agent scope reference. | Quality Control | Amend Not in directives to include: Add commissioning agent scope reference.
9.41.180 – Commissioning Meetings | Provide documentation/manpower | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor commissioning duties. | Coordination | Amend Not in directives to include: Add subcontractor commissioning duties.
9.41.180 – Commissioning Meetings | Ensure commissioning compliance | Quality Inspector | Not in directives | ⚠ Gap | Add QA/QC commissioning accountability. | Quality Control | Amend Not in directives to include: Add QA/QC commissioning accountability.
9.41.185 – Closeout Meetings | Submit closeout docs | Subcontractors | Not in directives | ⚠ Gap | Include subcontractor closeout requirements. | Project Closeout | Amend Not in directives to include: Include subcontractor closeout requirements.
9.41.185 – Closeout Meetings | Confirm acceptance of deliverables | Client/Owner | Not in directives | ⚠ Gap | Owner external – clarify acceptance protocols. | Project Closeout | Amend Not in directives to include: Owner external – clarify acceptance protocols.
9.41.190A – Filing Standards | Maintain field-level docs in Procore | Field Foreman | Not in directives | ⚠ Gap | Add field documentation requirement. | Documentation Management | Amend Not in directives to include: Add field documentation requirement.
9.41.200 – Submittals | Provide shop drawings/product data | Subcontractors | Not in directives | ⚠ Gap | Add subcontractor submittal duties. | Documentation Management | Amend Not in directives to include: Add subcontractor submittal duties.
9.41.205 – RFIs | Subcontractors required to draft/support RFIs | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor RFI responsibilities to directives. | Scope & Change Control | Amend Not explicit in directives to include: Add subcontractor RFI responsibilities to directives.
9.41.210 – Meeting Minutes | Minutes responsibility clarity | Site Administrator | Not explicit in directives | ⚠ Gap | Explicitly assign Site Admin responsibility for meeting minutes. | Communication | Amend Not explicit in directives to include: Explicitly assign Site Admin responsibility for meeting minutes.
9.41.215 – Daily Reports | Foremen/Subcontractors required to submit daily reports | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor daily report requirement. | Labor Management | Amend Not explicit in directives to include: Add subcontractor daily report requirement.
9.41.220 – Drawing Logs | Subcontractors to submit updated drawings | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor drawing log submission. | Documentation Management | Amend Not explicit in directives to include: Add subcontractor drawing log submission.
9.41.225 – Specifications | Subcontractor input on spec compliance | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor compliance review of specs. | Documentation Management | Amend Not explicit in directives to include: Require subcontractor compliance review of specs.
9.41.230 – Correspondence | Subcontractors required to provide written correspondence trail | Subcontractors | Not explicit in directives | ⚠ Gap | Include subcontractor correspondence duty. | Communication | Amend Not explicit in directives to include: Include subcontractor correspondence duty.
9.41.235 – Permits | Authority responsibility for inspections | Regulatory Authorities | External role | ⚠ Gap | Clarify external agency responsibility protocol. | Safety Management | Amend External role to include: Clarify external agency responsibility protocol.
9.41.240 – Inspections | Subcontractors must close open deficiencies | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor inspection compliance duties. | Quality Control | Amend Not explicit in directives to include: Add subcontractor inspection compliance duties.
9.41.245 – Punch Lists | Subcontractors provide completion evidence | Subcontractors | Not explicit in directives | ⚠ Gap | Add subcontractor punch list responsibilities. | Project Closeout | Amend Not explicit in directives to include: Add subcontractor punch list responsibilities.
9.41.315 – Develop Schedule | Superintendent role not explicit in directives | Superintendent | Not explicit in directives | ⚠ Gap | Clarify Superintendent role in directive 9.4 for schedule input. | Scheduling | Amend Not explicit in directives to include: Clarify Superintendent role in directive 9.4 for schedule input.
9.41.330 – Recovery Plans | Superintendent adjustments not explicit | Superintendent | Not explicit in directives | ⚠ Gap | Add Superintendent labor/equipment adjustment duties. | Scheduling | Amend Not explicit in directives to include: Add Superintendent labor/equipment adjustment duties.
9.41.340 – Resource-Loaded | Foreman role missing for crew-level validation | Field Foreman | Not explicit in directives | ⚠ Gap | Add Foreman resource feedback duty. | Labor Management | Amend Not explicit in directives to include: Add Foreman resource feedback duty.
9.41.345 – Schedule Review Meetings | Consultant participation not explicit | Consultants | Not explicit in directives | ⚠ Gap | Add consultant role in review meetings if applicable. | Coordination | Amend Not explicit in directives to include: Add consultant role in review meetings if applicable.
9.41.350 – Schedule Change Requests | Log requests | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty to maintain change request log. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty to maintain change request log.
9.41.360 – Change Orders | Maintain CO log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for CO logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for CO logs.
9.41.380 – Backcharges | Process financial impacts | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for backcharge tracking. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for backcharge tracking.
9.41.385 – Force Account Work | Process billing | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for force account billing. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for force account billing.
9.41.385 – Force Account Work | File and log records | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for FA logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for FA logs.
9.41.390 – Claims | Assist with disputes | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role. | Scope & Change Control | Amend Not explicit in directives to include: Add Legal Counsel advisory role.
9.41.390 – Claims | Maintain claim log | Site Administrator | Not explicit in directives | ⚠ Gap | Add Site Admin duty for claim logs. | Documentation Management | Amend Not explicit in directives to include: Add Site Admin duty for claim logs.
9.41.395 – Project Budget | Review/input budget | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to record project budget. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to record project budget.
9.41.400 – Monitor Project Costs | Maintain detailed cost tracking | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for cost monitoring. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for cost monitoring.
9.41.405 – Manage Cost Forecasts | Provide backup and adjustments | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting responsibility for forecast inputs. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting responsibility for forecast inputs.
9.41.410 – Manage Cost Codes | Ensure alignment with company standards | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to align cost codes with financial systems. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to align cost codes with financial systems.
9.41.415 – Manage Committed Costs | Maintain records | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting duty for committed cost records. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting duty for committed cost records.
9.41.420 – Manage Actual Costs | Track invoices and payroll | Accounting | Not explicit in directives | ⚠ Gap | Add explicit Accounting role for actual costs. | Cost Control & Billing | Amend Not explicit in directives to include: Add explicit Accounting role for actual costs.
9.41.425 – Manage Job Cost Reports | Provide accounting input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for job cost reports. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for job cost reports.
9.41.430 – Manage Profit Projections | Verify financial data | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify data for projections. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to verify data for projections.
9.41.435 – Manage Cost-to-Complete | Provide actual data input | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty for actuals in cost-to-complete. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty for actuals in cost-to-complete.
9.41.440 – Prepare Billing Schedule | Confirm owner agreement | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for billing schedule. | Communication | Amend Not explicit in directives to include: Add client approval protocol for billing schedule.
9.41.445 – Monthly Pay Applications | Provide invoices/payment records | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to provide records for pay apps. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to provide records for pay apps.
9.41.445 – Monthly Pay Applications | Approve payment | Client/Owner | Not explicit in directives | ⚠ Gap | Add client approval protocol for pay applications. | Communication | Amend Not explicit in directives to include: Add client approval protocol for pay applications.
9.41.450 – Track Accounts Receivable | Track AR aging and follow up on collections | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to maintain AR aging and collections follow-up. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to maintain AR aging and collections follow-up.
9.41.455 – Manage Lien Waivers | Track lien waivers and verify with pay apps | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to track lien waivers with pay apps. | Documentation Management | Amend Not explicit in directives to include: Add Accounting duty to track lien waivers with pay apps.
9.41.455 – Manage Lien Waivers | Maintain lien waiver log | Site Administrator | Not explicit in directives | ⚠ Gap | Assign Site Admin to maintain lien waiver log. | Documentation Management | Amend Not explicit in directives to include: Assign Site Admin to maintain lien waiver log.
9.41.455 – Manage Lien Waivers | Provide executed lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor submission of lien waivers before payment. | Documentation Management | Amend Not explicit in directives to include: Require subcontractor submission of lien waivers before payment.
9.41.460 – Manage Retainage | Verify amounts withheld and released | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to verify retainage withheld/released. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to verify retainage withheld/released.
9.41.465 – Manage Final Invoicing | Review final invoice and submit for payment | Accounting | Not explicit in directives | ⚠ Gap | Add Accounting duty to review and submit final invoice. | Cost Control & Billing | Amend Not explicit in directives to include: Add Accounting duty to review and submit final invoice.
9.41.465 – Manage Final Invoicing | Submit final pay apps and lien waivers | Subcontractors | Not explicit in directives | ⚠ Gap | Require subcontractor final pay apps and lien waivers. | Cost Control & Billing | Amend Not explicit in directives to include: Require subcontractor final pay apps and lien waivers.
9.41.495 – Investigate Accidents | Advise on legal implications as needed | Legal Counsel | Not explicit in directives | ⚠ Gap | Add Legal Counsel advisory role in accident investigations. | Safety Management | Amend Not explicit in directives to include: Add Legal Counsel advisory role in accident investigations.

## Conflict Matrix
SOP Title | Conflict Description | Conflict Type | Resolution Recommendation
9.41.005 – Team Selection | Staffing responsibility split between PM, GS, Branch Manager | Cadence Clash / Authority Chain | Clarify final approver in Directive 9.6.
9.41.010 – Project Turnover Meeting | Agenda/minutes responsibility unclear between Estimator and PM | Document Control | Assign PM as A, Estimator as R.
9.41.015 – Review Contract | Contract risk review split across PM, BM, CM | Authority Chain / Financial Accountability | Define PM as R, CM as C, BM as A.
9.41.020 – Plan Review | PM and GS both reviewing manpower/schedule | Schedule Ownership | PM = A, GS = C.
9.41.025 – FS Plan Review | FS and PM both reviewing constructability | Schedule Ownership | FS = R, PM = A.
9.41.030 – RFI Process | PM, FS, BM all involved in escalation | Authority Chain / Document Control | Define PM = A, FS = R, BM = I.
9.41.035 – Site Visit | FS, PM, GS, Safety Coordinator all reviewing site conditions | Cadence Clash / Safety Accountability | FS = R, Safety = C, PM = A.
9.41.040 – Est. vs. Planned | PM, GS, BM all validating manpower/budget | Financial Accountability | PM = A, GS = C, BM = I.
9.41.045 – VE & Prefab | PM, Estimator, Prefab Lead, FS all inputting | Authority Chain / Document Control | PM = A, Prefab = R, Estimator = C, FS = I.
9.41.050 – Takeoff | PM, Estimator, FS, Purchasing all using takeoff | Document Control / Financial Accountability | PM = A, Estimator = C, FS = C, Purchasing = R.
9.41.105 – Temporary Power | PM, FS, and Subcontractor roles overlap in installation oversight | Authority Chain / Safety Accountability | Define Subcontractor = R, FS = C, PM = A, Safety = C.
9.41.110 – Temporary Water | PM vs. FS overlap on utility coordination | Authority Chain | PM = A (coordination), FS = R (execution).
9.41.115 – Sanitary Facilities | PM contracts vendors, FS decides placement | Authority Chain | PM = A, FS = R, Safety = C.
9.41.120 – Temporary Lighting | FS and Subcontractor both installing/verifying lighting | Authority Chain | Subcontractor = R, FS = C.
9.41.130 – Security | PM, FS, Safety, Security Personnel all involved in monitoring | Authority Chain / Cadence Clash | PM = A, FS = C, Safety = C, Security = R.
9.41.140 – Equipment Staging | FS and Operators overlap in positioning equipment | Authority Chain | Operators = R, FS = A.
9.41.150 – Coordination Meetings | PM leads, FS contributes, Site Admin records, Consultant clarifies | Document Control | PM = A, FS = C, Site Admin = R (minutes), Consultants = I.
9.41.155 – Subcontractor Meetings | PM, FS, and subcontractors overlap on logistics & manpower reporting | Authority Chain | PM = A, Subcontractors = R, FS = C.
9.41.160 – Client Meetings | PM and BM both leading/representing GSL to client | Authority Chain | PM = R, BM = A.
9.41.165 – Safety Meetings | PM, FS, Safety all reinforcing messages | Cadence Clash | Safety = R, PM = A, FS = C.
9.41.170 – Prefab Meetings | PM, Prefab Lead, FS, GS all validating strategies | Authority Chain | Prefab Lead = R, PM = A, FS/GS = C.
9.41.175 – Quality Meetings | PM, FS, Safety, Quality Inspector all reviewing compliance | Authority Chain | Quality Inspector = R, PM = A, FS/Safety = C.
9.41.180 – Commissioning Meetings | PM, Commissioning Agent, Subs, QA all accountable for deliverables | Authority Chain | Commissioning Agent = R, PM = A, QA/Subs = C.
9.41.185 – Closeout Meetings | PM, FS, Subs, Client all determining readiness | Authority Chain / Client Interface | PM = A, Subs = R, FS = C, Client = I.
9.41.190A – Filing Standards | PM vs. Site Admin vs. Branch Mgr all accountable for documentation | Document Control | PM = A, Site Admin = R, BM = C.
9.41.200 – Submittals | PM, Purchasing, Subs all responsible for submittal flow | Document Control | PM = A, Purchasing = C, Subs = R.
9.41.300 – A/E Communications | PM and FS both addressing design issues | Authority Chain | PM = A, FS = C, SA = R (logging).
9.41.310 – GC Communications | PM vs. Site Admin overlap in correspondence control | Document Control | PM = A, SA = R.
9.41.320 – Update Schedule | PM and Superintendent roles overlap in schedule updates | Schedule Ownership | PM = A, Superintendent = C.
9.41.325 – Monitor Performance | PM and BM overlap in review authority | Authority Chain | PM = R, BM = A, Superintendent = C.
9.41.335 – Lookahead Schedules | PM, Superintendent, and Foreman overlap in short-term planning | Cadence Clash | PM = A, Superintendent = C, Foreman = R.
9.41.340 – Resource-Loaded | PM, Superintendent, BM all approving resources | Authority Chain | PM = A, Superintendent = C, BM = C.
9.41.350 – Schedule Change Requests | PM vs. Branch Manager overlap in approval authority | Authority Chain | PM = R, BM = A.
9.41.360 – Change Orders | PM, Estimator, BM all touching COs | Authority Chain | PM = R, Estimator = C, BM = A.
9.41.380 – Backcharges | PM approves, Accounting tracks — overlap risk | Financial Accountability | PM = A, Accounting = R.
9.41.385 – Force Account Work | PM, FS, Accounting, SA all handling documents | Document Control | PM = A, FS = R, Accounting = C, SA = C.
9.41.390 – Claims | PM, Estimator, BM, Legal all involved | Authority Chain | PM = R, BM = A, Estimator = C, Legal = C, SA = I.
9.41.395 – Project Budget | PM, Estimator, Accounting, BM overlap on budget ownership | Financial Accountability | PM = R, BM = A, Estimator = C, Accounting = C.
9.41.400 – Monitor Costs | PM and Accounting both monitoring costs | Financial Accountability | PM = A, Accounting = R.
9.41.410 – Cost Codes | PM vs. Accounting overlap on maintaining codes | Document Control | PM = A, Accounting = C.
9.41.415 – Committed Costs | PM, BM, and Accounting all approving/recording commitments | Financial Accountability | PM = R, BM = A, Accounting = C.
9.41.425 – Job Cost Reports | PM, BM, Accounting overlap in preparing/validating reports | Authority Chain | PM = R, BM = A, Accounting = C.
9.41.430 – Profit Projections | PM, BM, Accounting overlap in projections | Financial Accountability | PM = R, BM = A, Accounting = C.
9.41.440 – Billing Schedule | PM prepares, BM reviews, Owner approves | Authority Chain / Client Interface | PM = R, BM = A, Owner = I.
9.41.445 – Pay Applications | PM, BM, Accounting, and Owner all involved in approvals | Financial Accountability | PM = R, BM = A, Accounting = C, Owner = I.
9.41.450 – Accounts Receivable | PM vs. Accounting escalation vs. tracking | Financial Accountability | PM = A (escalation), Accounting = R (tracking), BM = C.
9.41.455 – Lien Waivers | PM, Accounting, Site Admin, Subs all touching waivers | Document Control | PM = A, Site Admin = R (log), Accounting = C, Subs = R (submission).
9.41.460 – Retainage | PM, Accounting, BM overlap on release | Financial Accountability | PM = R, Accounting = C, BM = A.
9.41.465 – Final Invoicing | PM prepares, Accounting submits, BM approves | Authority Chain | PM = R, Accounting = C, BM = A, Subs = R (final pay apps).
9.41.470 – SSSP | Safety drafts, PM approves, BM audits, FS implements | Authority Chain / Safety Accountability | Safety = R, PM = A, BM = C, FS = R (implementation).
9.41.490 – Incident Reporting | FS initial report vs. Safety official report vs. PM escalation | Document Control / Safety Accountability | Safety = R, FS = R (initial), PM = A, BM = I.
9.41.495 – Accident Investigation | Safety leads, PM/FS support, BM approves, Legal advises | Authority Chain | Safety = R, PM = C, FS = C, BM = A, Legal = C.

## Closeout Checklist
Role | Closeout Task | Directive Section | Coverage Status
Project Manager | Submit O&M manuals and warranty letters | Sec. 9.13 PM Directives | ✔ Covered
Project Manager | Ensure all RFIs, Submittals, and Change Orders are closed | Sec. 9.5 PM Directives | ✔ Covered
Field Supervisor | Submit daily reports and as-built drawings | Sec. 9.3 Field Leadership | ✔ Covered
General Superintendent | Confirm apprentice/journeyman ratios and manpower demobilization | Sec. 9.4 GS | ✔ Covered
Safety Coordinator | Conduct final site safety audit and turnover report | Sec. 7.2.6 JD | ✔ Covered
Branch Manager | Approve final project closeout package | Sec. 9.6 Branch Mgmt | ✔ Covered
Purchasing | Ensure all POs and vendor accounts are closed | Sec. 9.16 Purchasing | ✔ Covered
Business Manager | Submit retention billings and financial closeout | Sec. 9.13 BM | ✔ Covered
Contract Manager | Confirm all notices and claims are resolved | Sec. 9.14 CM | ✔ Covered
Project Manager | Compile and submit final As-Built Drawings to Owner | SOP 9.41.250 | ✔ Covered
Field Supervisor | Record field changes and update redline drawings | SOP 9.41.250 | ✔ Covered
Subcontractors | Provide redline markups of installed work | SOP 9.41.250 | ⚠ Gap – not explicit in directives
Project Manager | Review and confirm completeness of O&M Manuals | SOP 9.41.255 | ✔ Covered
Subcontractors | Submit O&M manuals per specifications | SOP 9.41.255 | ⚠ Gap – not explicit in directives
Project Manager | Review warranty requirements and ensure compliance | SOP 9.41.260 | ✔ Covered
Subcontractors | Submit warranty certificates | SOP 9.41.260 | ⚠ Gap – not explicit in directives
Site Administrator | Log and organize warranty documentation | SOP 9.41.260 | ✔ Covered
Project Manager | Oversee full closeout documentation package | SOP 9.41.265 | ✔ Covered
Site Administrator | Compile documents into closeout package | SOP 9.41.265 | ✔ Covered
Subcontractors | Provide final deliverables for closeout | SOP 9.41.265 | ⚠ Gap – not explicit in directives
Owner/Client | Review and accept final closeout documentation | SOP 9.41.265 | ⚠ Gap – external role, requires protocol
Project Manager | Ensure final billing aligns with contract | SOP 9.41.440 / 445 | ✔ Covered
Branch Manager | Approve final pay applications | SOP 9.41.445 | ✔ Covered
Accounting | Process and record final invoices | SOP 9.41.445 | ⚠ Gap – not explicit in directives
Client/Owner | Approve final payment | SOP 9.41.445 | ⚠ Gap – external role, requires protocol
Project Manager | Collect and confirm all lien waivers before final payment | SOP 9.41.455 / 465 | ✔ Covered
Accounting | Verify lien waivers with each pay app and track retainage balances | SOP 9.41.455 / 460 | ⚠ Gap – add directive coverage
Branch Manager | Approve final retainage release and final invoice | SOP 9.41.460 / 465 | ✔ Covered

## Role Alignment Matrix
SOP Title | Category | Accounting | All Employees | Branch Manager | Client/Owner | Commissioning Agent | Consultants | Design Team / Consultants | Electrical Subcontractor | Equipment Operators | Estimator | Field Foreman | Field Supervisor | Foreman / Field Supervisor | General Superintendent | IT/Communications | Legal Counsel | PM & GS | PM, Branch Manager | PM, Branch Mgr, GS, Field Leadership, Prefab, Safety | Prefab Lead | Prefabrication Lead | Project Manager | Purchasing | Quality Inspector | Regulatory Authorities | Safety Coordinator | Security Personnel | Site Administrator | Subcontractors | Superintendent
9.41.005 – Team Selection | Team selection and turnover |  |  | X | [10 empty] | X | [7 empty] | X |  |  |  | X
9.41.010 – Project Turnover Meeting | Team selection and turnover | [9 empty] | X | [8 empty] | X |  |  | X
9.41.015 – Review Contract for High-Risk Clauses | Scope and contract review | [17 empty] | X |  |  |  | X
9.41.020 – PM Reviews Plans, Specs & Schedule | Scope and contract review | [21 empty] | X
9.41.025 – FS Reviews Plans, Specs & Schedule | Scope and contract review | [11 empty] | X | [9 empty] | X
9.41.030 – Create Issue List & RFI | Scope and contract review | [11 empty] | X |  |  |  |  | X |  |  |  |  | X
9.41.035 – Conduct Site Visit | Scope and contract review | [11 empty] | X |  | X | [7 empty] | X |  |  |  | X
9.41.040 – Compare Est. vs. Planned | Budget preparation |  |  | X | [6 empty] | X |  |  |  | X | [7 empty] | X
9.41.045 – VE & Prefab | Buyout process | [9 empty] | X |  | X | [8 empty] | X | X
9.41.050 – Construction Takeoff | Buyout process | [9 empty] | X |  | X | [9 empty] | X | X
9.41.055 – Procurement of Large Feeder Wire | Buyout process | [12 empty] | X | X | [7 empty] | X
9.41.060 – Material Handling Plan | Material handling plan | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.065 – Develop Labor Budget | Budget preparation |  |  | X | [6 empty] | X |  |  |  | X | [7 empty] | X
9.41.070 – Layout & Sequencing Plan | Layout and sequencing plan | [11 empty] | X |  | X | [7 empty] | X |  |  |  | X
9.41.075 – Develop Project Schedule | Schedule development |  |  | X | [10 empty] | X | [7 empty] | X | X
9.41.080 – Tracking & Control Systems | Tracking and control |  |  | X | [8 empty] | X | [9 empty] | X | X |  |  | X
9.41.085 – Kickoff Meeting | Construction execution kickoff meeting |  |  | X | [8 empty] | X |  | X | [7 empty] | X | X |  |  | X
9.41.090 – Office Trailer | Mobilization | [13 empty] | X | X | [6 empty] | X | [5 empty] | X
9.41.095 – Storage Trailer | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.100 – Fencing & Access Control | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X | X
9.41.105 – Setup Temporary Power | Mobilization | [7 empty] | X |  |  |  | X | [9 empty] | X |  |  |  | X
9.41.110 – Setup Temporary Water | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.115 – Setup Sanitary Facilities | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.120 – Setup Temporary Lighting | Mobilization | [7 empty] | X |  |  |  | X | [9 empty] | X |  |  |  | X
9.41.125 – Setup Signage | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.130 – Setup Security | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X | X
9.41.135 – Setup Laydown Area | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.140 – Setup Equipment Staging | Mobilization | [8 empty] | X |  |  | X | [9 empty] | X |  |  |  | X
9.41.145 – Setup Parking | Mobilization | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.150 – Coordination Meetings | Coordination | [6 empty] | X |  |  |  |  | X | [9 empty] | X | [5 empty] | X
9.41.155 – Subcontractor Meetings | Coordination | [11 empty] | X | [9 empty] | X | [6 empty] | X
9.41.155 – Subcontractor Meetings | Safety Management | [25 empty] | X
9.41.160 – Client Meetings | Coordination |  |  | X | X | [17 empty] | X
9.41.165 – Safety Meetings | Safety Management |  | X | [9 empty] | X | [9 empty] | X |  |  |  | X
9.41.170 – Prefab Meetings | Coordination | [11 empty] | X | [7 empty] | X |  | X
9.41.170 – Prefab Meetings | Labor Management | [13 empty] | X
9.41.175 – Quality Meetings | Quality Control | [11 empty] | X | [9 empty] | X |  | X
9.41.175 – Quality Meetings | Safety Management | [25 empty] | X
9.41.180 – Commissioning Meetings | Coordination | [21 empty] | X | [6 empty] | X
9.41.180 – Commissioning Meetings | Quality Control |  |  |  |  | X | [18 empty] | X
9.41.185 – Closeout Meetings | Project Closeout |  |  |  | X | [7 empty] | X | [9 empty] | X | [6 empty] | X
9.41.190A – Filing Standards | Documentation Management |  |  | X | [7 empty] | X | [10 empty] | X | [5 empty] | X
9.41.195 – Documentation System | Documentation Management |  |  | X | [18 empty] | X | [5 empty] | X
9.41.200 – Submittals | Documentation Management | [21 empty] | X | X | [5 empty] | X
9.41.205 – RFIs | Scope & Change Control | [28 empty] | X
9.41.210 – Meeting Minutes | Communication | [27 empty] | X
9.41.215 – Daily Reports | Labor Management | [28 empty] | X
9.41.220 – Drawing Logs | Documentation Management | [28 empty] | X
9.41.225 – Specifications | Documentation Management | [28 empty] | X
9.41.230 – Correspondence | Communication | [28 empty] | X
9.41.235 – Permits | Safety Management | [24 empty] | X
9.41.240 – Inspections | Quality Control | [28 empty] | X
9.41.245 – Punch Lists | Project Closeout | [28 empty] | X
9.41.300 – A/E Communications | Communication | [11 empty] | X | [9 empty] | X
9.41.300 – A/E Communications | Documentation Management | [27 empty] | X
9.41.310 – GC Communications | Communication | [11 empty] | X | [9 empty] | X
9.41.310 – GC Communications | Documentation Management | [27 empty] | X
9.41.315 – Develop Project Schedule | Scheduling | [21 empty] | X
9.41.315 – Develop Schedule | Scheduling | [29 empty] | X
9.41.320 – Update Project Schedule | Scheduling | [21 empty] | X | [7 empty] | X
9.41.325 – Monitor Schedule Performance | Labor Management | [29 empty] | X
9.41.325 – Monitor Schedule Performance | Scheduling | [21 empty] | X
9.41.330 – Recovery Plans | Cost Control |  |  | X
9.41.330 – Recovery Plans | Scheduling | [21 empty] | X | [7 empty] | X
9.41.335 – Lookahead Schedules | Labor Management | [10 empty] | X | [18 empty] | X
9.41.335 – Lookahead Schedules | Scheduling | [21 empty] | X
9.41.340 – Resource-Loaded | Labor Management | [10 empty] | X
9.41.340 – Resource-Loaded Schedules | Labor Management | [29 empty] | X
9.41.340 – Resource-Loaded Schedules | Materials Management |  |  | X
9.41.340 – Resource-Loaded Schedules | Scheduling | [21 empty] | X
9.41.345 – Schedule Review Meetings | Coordination |  |  | X |  |  | X
9.41.345 – Schedule Review Meetings | Labor Management | [10 empty] | X
9.41.345 – Schedule Review Meetings | Scheduling | [21 empty] | X | [7 empty] | X
9.41.350 – Schedule Change Requests | Documentation Management | [27 empty] | X
9.41.350 – Schedule Change Requests | Scheduling |  |  | X | [18 empty] | X
9.41.355 – Project Scope | Scope & Change Control |  |  | X | [18 empty] | X
9.41.360 – Change Orders | Cost Control & Billing | [9 empty] | X
9.41.360 – Change Orders | Documentation Management | [27 empty] | X
9.41.360 – Change Orders | Scope & Change Control |  |  | X | [18 empty] | X
9.41.365 – PCOs | Cost Control & Billing | [9 empty] | X
9.41.365 – PCOs | Scope & Change Control | [21 empty] | X
9.41.370 – Owner Directives | Scope & Change Control |  |  | X | [18 empty] | X
9.41.375 – Scope Clarifications | Scope & Change Control | [9 empty] | X | [11 empty] | X
9.41.380 – Backcharges | Cost Control & Billing | X | [20 empty] | X
9.41.385 – Force Account Work | Cost Control & Billing | X
9.41.385 – Force Account Work | Documentation Management | [27 empty] | X
9.41.385 – Force Account Work | Labor Management | [11 empty] | X
9.41.385 – Force Account Work | Scope & Change Control | [21 empty] | X
9.41.390 – Claims | Cost Control & Billing | [9 empty] | X
9.41.390 – Claims | Documentation Management | [27 empty] | X
9.41.390 – Claims | Scope & Change Control |  |  | X | [12 empty] | X | [5 empty] | X
9.41.395 – Project Budget | Cost Control & Billing | X |  | X | [6 empty] | X | [11 empty] | X
9.41.400 – Monitor Project Costs | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.405 – Manage Cost Forecasts | Cost Control & Billing | X | [20 empty] | X
9.41.410 – Manage Cost Codes | Cost Control & Billing | X | [20 empty] | X
9.41.415 – Manage Committed Costs | Cost Control & Billing | X |  | X
9.41.415 – Manage Committed Costs | Materials Management | [21 empty] | X
9.41.420 – Manage Actual Costs | Cost Control & Billing | X | [20 empty] | X
9.41.425 – Manage Job Cost Reports | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.430 – Manage Profit Projections | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.435 – Manage Cost-to-Complete | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.440 – Prepare Billing Schedule | Communication |  |  |  | X
9.41.440 – Prepare Billing Schedule | Cost Control & Billing |  |  | X | [18 empty] | X
9.41.445 – Monthly Pay Applications | Communication |  |  |  | X
9.41.445 – Monthly Pay Applications | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.450 – Track Accounts Receivable | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.455 – Manage Lien Waivers | Documentation Management | X | [20 empty] | X | [5 empty] | X | X
9.41.460 – Manage Retainage | Cost Control & Billing | X |  | X | [18 empty] | X
9.41.465 – Manage Final Invoicing | Cost Control & Billing | X |  | X | [18 empty] | X | [6 empty] | X
9.41.470 – Site-Specific Safety Plan | Safety Management |  |  | X | [8 empty] | X | [9 empty] | X |  |  |  | X
9.41.475 – Safety Orientation | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.480 – Safety Inspections | Safety Management |  |  | X | [8 empty] | X | [9 empty] | X |  |  |  | X
9.41.485 – Safety Meetings | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.490 – Report Safety Incidents | Safety Management | [11 empty] | X | [9 empty] | X |  |  |  | X
9.41.495 – Investigate Accidents | Safety Management |  |  | X | [8 empty] | X |  |  |  | X | [5 empty] | X |  |  |  | X