## Administrative Setup
Table 4.9: Administrative Setup Checklist |  |  |  | 9.2.007 - Administrative Setup | Appedix
Project Number: ________________________________________________________________________________
Project Name: ________________________________________________________________________________
Location: ________________________________________________________________________________
Project Manager: ________________________________________________________________________________
Start Date: ________________________________________________________________________________
ADMINISTRATIVE SETUP CHECKLIST FOR PRE-CONSTRUCTION PLANNING
ACT. | COMPLETION DATE | ITEM NO. | SUB-ACTIVITIES
13. Set up project files and create contact list.
☐ |  | 1 | Use the File System Checklist (Table 4.11) to create paper files. | Request Job Number | Job Number Request Form
☐ |  | 2 | Create a contact sheet that lists all team members and their company contact information. | Set up Project in Pro Core
14. Set up computerized tracking and control system (forms, database, schedule and tracking).
☐ |  | 1 | Verify the accounting department has assigned a project number and entered initial information in the cost control center.
☐ |  | 2 | Use the File System Checklist (Table 4.11) to create computer files.
☐ |  | 3 | If a separate project management software system is used, set up the project in the system.
☐ |  | 4 | If a separate project management software system is used, set up the project in the system.
15. Initiate a change management system.
☐ |  | 1 | Review the contract to identify required change order, field change, and time-and-materials procedures.
☐ |  | 2 | Review your company's standard procedures for initiating, requesting, and processing change orders and field changes.
☐ |  | 3 | Develop a log with sequential numbering to track all changes, including change orders, field changes and time-and-materials requests (Table 4.12).
16. Initiate a request for information (RFI) tracking and processing system.
☐ |  | 1 | Develop a log with sequential numbering to track all requests for information (RFIs) (Table 4.13).
☐ |  | 2 | Determine whether RFIs will be submitted by e-mail, fax or postal mail.
☐ |  | 3 | Review your company's standard procedures for processing RFIs, and use a company standard form for submitting RFIs.
☐ |  | 4 | Ensure each RFI also identifies a proposed solution.
17. Initiate a submittal tracking and processing system.
☐ |  | 1 | Develop a log with sequential numbering to track all submittals, including those of vendors and subcontractors (Table 4.14).
☐ |  | 2 | Review your company's standard procedures for processing submittals, and use a company standard form for submissions.
☐ |  | 3 | Verify that each submittal processing form identifies a respond-no-later-than date, which is associated with timely ordering and delivery of materials and equipment.
18. Develop a "Labor Requirements/Expectation" letter (for background check, etc.) (performance recommended)
☐ |  | 1 | For projects that have special requirements such as drug testing, background check or special safety training, develop an "expectations" letter that must be reviewed and signed by crew members (see Figure 4.8).
☐ |  | 2 | For projects that will require hiring workers from the union hall, develop an "expectations" letter that must be reviewed and signed by crew members.